## Timeline - Monthly (hidden)
| 2026-01-01 | [34 empty] | 2027-01-01 | [51 empty] | 2028-01-01
| 2026-05-06 |  |  |  | 2026-06-01 |  |  |  |  | 2026-07-06 |  |  |  | 2026-08-03 |  |  |  |  | 2026-09-07 |  |  |  | 2026-10-05 |  |  |  | 2026-11-02 |  |  |  |  | 2026-12-07 |  |  |  | 2027-01-04 |  |  |  | 2027-02-01 |  |  |  | 2027-03-01 |  |  |  |  | 2027-04-05 |  |  |  | 2027-05-03 |  |  |  |  | 2027-06-05 |  |  |  | 2027-07-05 |  |  |  | 2027-08-03 |  |  |  |  | 2027-09-05 |  |  |  | 2027-10-05 |  |  |  | 2027-11-03 |  |  |  |  | 2027-12-05 |  |  |  | 2028-01-03 |  |  |  |  | 2028-02-05 |  |  |  | 2028-03-05 |  |  |  | 2028-04-05 |  |  |  | 2028-05-03 |  |  |  |  | 2028-06-05 |  |  |  | 2028-07-03 |  |  |  |  | 2028-08-05 |  |  |  | 2028-09-05 |  |  |  | 2028-10-03 |  |  |  |  | 2028-11-05 |  |  |  | 2028-12-05 |  |  |  | 2029-01-03
 | time axis 2026-05-04 to 2029-03-05
Ending | time axis 2026-05-22 to 2027-12-31
Week# | time axis 2026-05-22 to 2027-12-31
Edison |  |  | 2026-05-22: Edison
ROM for S/4 Enterprise implementation
Global Design |  |  | 2026-06-05: Global Design; 2026-09-25: Cross OpCo - Phase 0; 2026-11-20: High Level Scoping, KDDs, Harmonization Opportunities
ABT Implementation |  |  | 2026-06-26: AlphaBio Implementaiton; 2026-08-28: Prep; 2026-09-11: 1; 2026-10-09: 2; 2026-11-06: 3; 2026-12-04: 4; 2027-03-05: MC1; 2027-04-16: MC2; 2027-05-28: CS; 2027-07-23: FC; 2027-08-13: HYC
[32 empty] | 1 | [5 empty] | 2 |  |  | 3 |  |  |  |  | SIT 1 | [5 empty] | SIT 2 | [6 empty] | UAT/OQ/PQ
Assessment Phase
S4 Implementation
Assessment
|  |  | 2026-09-18: Prep; 2026-10-02: 1; 2026-11-13: 2; 2027-01-08: 3; 2027-02-19: 4; 2027-04-02: 5; 2027-09-17: MC1; 2027-11-19: MC2 |  |  |  |  | CS | [9 empty] | FPC |  |  |  | HYC
|  |  | 2026-10-23: 1; 2027-04-02: 1; 2027-05-14: 2; 2027-06-25: 3; 2027-08-06: 4; 2027-10-15: SIT 1; 2027-12-17: SIT 2 | SIT 2 | [7 empty] | UAT/OQ/PQ

## Timeline
Year | 2026-01-01 | [43 empty] | 2027-01-01 | [51 empty] | 2028-01-01
Month | 2026-03-01 |  |  |  |  | 2026-04-06 |  |  |  | 2026-05-06 |  |  |  | 2026-06-01 |  |  |  |  | 2026-07-06 |  |  |  | 2026-08-03 |  |  |  |  | 2026-09-07 |  |  |  | 2026-10-05 |  |  |  | 2026-11-02 |  |  |  |  | 2026-12-07 |  |  |  | 2027-01-04 |  |  |  | 2027-02-01 |  |  |  | 2027-03-01 |  |  |  |  | 2027-04-05 |  |  |  | 2027-05-03 |  |  |  |  | 2027-06-05 |  |  |  | 2027-07-05 |  |  |  | 2027-08-03 |  |  |  |  | 2027-09-05 |  |  |  | 2027-10-05 |  |  |  | 2027-11-03 |  |  |  |  | 2027-12-05 |  |  |  | 2028-01-03 |  |  |  |  | 2028-02-05 |  |  |  | 2028-03-05 |  |  |  | 2028-04-05 |  |  |  | 2028-05-03 |  |  |  |  | 2028-06-05 |  |  |  | 2028-07-03 |  |  |  |  | 2028-08-05 |  |  |  | 2028-09-05 |  |  |  | 2028-10-03 |  |  |  |  | 2028-11-05 |  |  |  | 2028-12-05 |  |  |  | 2029-01-03
Week Start | 2026-03-02 | 2026-03-09 | 2026-03-16 | 2026-03-23 | 2026-03-30 | 2026-04-06 | 2026-04-13 | 2026-04-20 | 2026-04-27 | 2026-05-04 | 2026-05-11 | 2026-05-18 | 2026-05-25 | 2026-06-01 | 2026-06-08 | 2026-06-15 | 2026-06-22 | 2026-06-29 | 2026-07-06 | 2026-07-13 | 2026-07-20 | 2026-07-27 | 2026-08-03 | 2026-08-10 | 2026-08-17 | 2026-08-24 | 2026-08-31 | 2026-09-07 | 2026-09-14 | 2026-09-21 | 2026-09-28 | 2026-10-05 | 2026-10-12 | 2026-10-19 | 2026-10-26 | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-07 | 2026-12-14 | 2026-12-21 | 2026-12-28 | 2027-01-04 | 2027-01-11 | 2027-01-18 | 2027-01-25 | 2027-02-01 | 2027-02-08 | 2027-02-15 | 2027-02-22 | 2027-03-01 | 2027-03-08 | 2027-03-15 | 2027-03-22 | 2027-03-29 | 2027-04-05 | 2027-04-12 | 2027-04-19 | 2027-04-26 | 2027-05-03 | 2027-05-10 | 2027-05-17 | 2027-05-24 | 2027-05-31 | 2027-06-07 | 2027-06-14 | 2027-06-21 | 2027-06-28 | 2027-07-05 | 2027-07-12 | 2027-07-19 | 2027-07-26 | 2027-08-02 | 2027-08-09 | 2027-08-16 | 2027-08-23 | time axis 2027-08-30 to 2029-03-05
Week End | 2026-03-06 | 2026-03-13 | 2026-03-20 | 2026-03-27 | 2026-04-03 | 2026-04-10 | 2026-04-17 | 2026-04-24 | 2026-05-01 | 2026-05-08 | 2026-05-15 | 2026-05-22 | 2026-05-29 | 2026-06-05 | 2026-06-12 | 2026-06-19 | 2026-06-26 | 2026-07-03 | 2026-07-10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | 2026-08-07 | 2026-08-14 | 2026-08-21 | 2026-08-28 | 2026-09-04 | 2026-09-11 | 2026-09-18 | 2026-09-25 | 2026-10-02 | 2026-10-09 | 2026-10-16 | 2026-10-23 | 2026-10-30 | 2026-11-06 | 2026-11-13 | 2026-11-20 | 2026-11-27 | 2026-12-04 | 2026-12-11 | 2026-12-18 | 2026-12-25 | 2027-01-01 | 2027-01-08 | 2027-01-15 | 2027-01-22 | 2027-01-29 | 2027-02-05 | 2027-02-12 | 2027-02-19 | 2027-02-26 | 2027-03-05 | 2027-03-12 | 2027-03-19 | 2027-03-26 | 2027-04-02 | 2027-04-09 | 2027-04-16 | 2027-04-23 | 2027-04-30 | 2027-05-07 | 2027-05-14 | 2027-05-21 | 2027-05-28 | 2027-06-04 | 2027-06-11 | 2027-06-18 | 2027-06-25 | 2027-07-02 | 2027-07-09 | 2027-07-16 | 2027-07-23 | 2027-07-30 | 2027-08-06 | 2027-08-13 | 2027-08-20 | 2027-08-27 | time axis 2027-09-03 to 2029-02-02
Week# | [11 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | time axis 2027-09-03 to 2029-02-02
Original
S4 Implementation | [9 empty] | Readiness | [12 empty] | 1 |  |  |  | 2 |  |  |  | 3 |  |  |  | 4 |  |  |  | 5 | [5 empty] | 6 |  |  |  | 7 | [23 empty] | MC1 | [5 empty] | 2027-09-24: MC2; 2027-11-26: MC3; 2028-02-11: CS; 2028-04-14: FPC; 2028-05-12: HYC
[21 empty] | Prep |  |  |  |  | 1 | [18 empty] | 1 |  |  |  | 2 |  |  |  | 3 |  |  |  | 4 |  |  |  | 5 |  |  |  | 6 |  |  |  | 7 | [7 empty] | SIT 1 |  | 2027-10-22: SIT 2; 2028-01-07: UAT/Val test; 2028-03-10: Dry Run
Go-Live: 21 Months
[23 empty] | Non-Prod Hardware Deployment | [49 empty] | Prod Hardware Deployment
Updated
Assessment Phase | [27 empty] | Assessment
S4 Implementation | [37 empty] | Prep |  | 1 |  |  |  | 2 | [5 empty] | 3 |  |  |  | 4 |  |  |  | 5 |  |  |  | 6 |  |  |  | 7 | [12 empty] | 2027-11-19: MC1; 2028-02-04: MC2; 2028-04-07: MC3; 2028-06-09: CS; 2028-08-11: FPC; 2028-09-08: HYC
[43 empty] | 1 | [18 empty] | 1 |  |  |  | 2 |  |  |  | 3 |  |  |  | 4 |  |  |  | 5 | 2027-09-24: 6; 2027-10-22: 7; 2027-12-17: SIT 1; 2028-03-03: SIT 2; 2028-05-05: UAT/Val test; 2028-07-07: Dry Run
Go-Live: 21 Months | [39 empty] | Non-Prod Hardware Deployment
[28 empty] | PLAN | [11 empty] | Imagine
[54 empty] | Deliver - Build | [23 empty] | Deliver - Test | 2028-04-07: Run (Deploy / Run)
S4 Implementation | [27 empty] | Scoping and Planning Phase | [25 empty] | Build 1 |  |  |  | Build 2 |  |  |  | Build 3 |  |  |  | Build 4 |  |  |  | Build 5 |  |  |  | Build 6 |  |  |  |  | 2027-09-17: SIT 1; 2027-11-19: SIT 2; 2028-02-04: UAT/Val Test; 2028-04-07: Dry Run
[38 empty] | Prep |  | Design 1 | [5 empty] | Design 2 |  |  |  | Design 3 |  |  |  | Design 4 |  |  |  | Design 5 | [17 empty] | MC1 |  |  | 2027-10-15: MC2; 2028-01-14: MC3; 2028-03-17: CS; 2028-05-19: FPC; 2028-06-09: HYC
PMO | [39 empty] | Ongoing project execution activities and status reporting | [25 empty] | MC1 Plan | [9 empty] | Mock Cutover 1 |  |  | 2027-10-15: Mock Cutover 2; 2028-01-14: MC 3; 2028-03-17: Cutover Simulation; 2028-05-19: Final Cutover
[38 empty] | Sprint plan | [15 empty] | Test Strategy | [11 empty] | SIT 1 Plan | [7 empty] | SIT 1 Scripts |  |  |  |  | 2027-09-17: SIT 1 Execution; 2027-11-19: SIT 2 Execution; 2028-02-04: UAT Execution; 2028-04-07: Dry Run Execution; 2028-05-19: AMS KT; 2028-06-09: Hypercare Support
[87 empty] | SIT 2 Scripts | [10 empty] | UAT/CSV scripts Scripts
golden copy
Brownfield/Tech
[36 empty] | Upgrade Prep |  |  |  | Sandbox Upgrade | [5 empty] | Dev Build |  | Dev SPAU |  |  | Dev Code Rem | [10 empty] | SBX Build |  |  |  |  | Pre-Prod Build |  |  |  | QA Build | [7 empty] | 2027-09-24: Pre-Prod Build; 2027-12-03: QA Build; 2028-02-18: Pre-Prod Build; 2028-04-07: Prod Build; 2028-06-09: Hypercare Support
Process | [35 empty] | WS Prep |  |  |  |  | Innov. Design WS | [8 empty] | Fit/Gap |  |  |  |  | Configuration, WRICEF Development, Unit Testing | [23 empty] | 2027-09-17: Execute SIT 1; 2027-11-19: Execute SIT 2; 2028-02-04: Support UAT; 2028-04-07: Support Dry Run; 2028-06-09: Support HYP
[48 empty] | SDT Review | [8 empty] | Support SDT & Remediation Activities | [14 empty] | SIT Prep |  |  |  |  | Support MC1 |  | 2027-10-15: Support MC2; 2028-01-14: Support MC2; 2028-03-17: Support CS; 2028-05-19: Support FC
Data | [52 empty] | SDT Setup |  |  | SDT Blueprint |  |  |  | SDT Build |  |  |  | SDT DDR1 |  |  |  | Def Fix
[38 empty] | Profiling Tool Setup | [5 empty] | Data Profling build |  |  |  | Profiling results review & Cleansing plan | [5 empty] | Finalize FI structure
[40 empty] | Data Profilng wkshp | [7 empty] | Fin Data restructuring analysis | [8 empty] | Data Validation Tool Build | [10 empty] | Data Validation Tool execution
Training translations & LMS uploads
OCM | [27 empty] | OCM Scans |  |  |  | OCM Project Plans | [7 empty] | Change Impact Analysis | [22 empty] | Training Strategy | [6 empty] | Training curriculum | [8 empty] | 2027-09-03: Training material development; 2028-01-14: Train the Trainer; 2028-03-10: End User Training delivery
[30 empty] | Plan for Project Team Training | [6 empty] | Stakeholder Identification & Analysis | [15 empty] | OCM Strategy | [25 empty] | 2027-12-31: Training delivery planning and logistics
[57 empty] | Comms Strategy & Comms Plan | [8 empty] | Foundational Comms & Adoption Assistant Stand-up | [8 empty] | Communication and engagement deployment per plan | bar: 2027-09-03 to 2028-05-26
[75 empty] | Awareness Campaign |  |  |  | 2027-11-05: Understanding Campaign; 2028-02-11: Readiness Campaign; 2028-05-05: Cutover & Go-Live Campaign
[86 empty] | Change Readiness Survey | [14 empty] | Change Readiness Survey | [11 empty] | Change Readiness Survey
[71 empty] | Change Network Identification & Stand-up | [6 empty] | Change Network Engagement | bar: 2027-09-03 to 2028-06-16
Analytics | [28 empty] | Data Source Impact | [10 empty] | Fit-to-standard workshops | [6 empty] | Rationalization | [6 empty] | Migrate and re-point data sources | [7 empty] | Extractor Remediation | [7 empty] | New CDS view Developments | [8 empty] | 2027-09-03: MC1; 2027-09-17: Analytics SIT 1 Support; 2027-11-05: MC2; 2027-11-19: Analytics SIT 2 Support; 2028-01-21: MC3; 2028-02-04: UAT/Val Test Support; 2028-04-07: Dry Run Support; 2028-06-09: Hypercare Support
[29 empty] | Analytics Scope & BDC Decision | [12 empty] | Fit Gap of Data Sources | [6 empty] | FDS for reimagine | [5 empty] | Technical Design | [8 empty] | Data Model Remediation | [5 empty] | New Data Sources | [5 empty] | Test Scripts for SIT |  |  | 2027-12-10: Test Scripts for UAT
Security | [29 empty] | Cyber Risk Assessment | [10 empty] | Conduct Security Workshops for Reimagine Processes | [17 empty] | Build and Unit Test Security Design
[30 empty] | Security and Controls Assessment | [19 empty] | Define Security Strategy and Approach
[41 empty] | Review of Impacted Risks and Controls | [21 empty] | Review Risk and Control Matrix | [15 empty] | 2027-09-24: Support Testing and Resolve Security Defects
Validation | [28 empty] | Finalize Validation Approach | [8 empty] | Review of User Requirements | [37 empty] | an you
[46 empty] | Develop Validation Plan | [7 empty] | Conduct Functional Risk Assessment | [24 empty] | 2028-01-14: IQ/CQ/DQ - QA; 2028-03-17: IQ/CQ/DQ - CS; 2028-05-19: IQ/CQ/DQ - Prod
[54 empty] | Review of Impacted Functional, Technical & Configuration Design Documents | [24 empty] | 2028-02-04: OQ/PQ & Regression Test Execution : Validation; 2028-05-19: RTM & VSR Sign Offs
Review & Approval of IQ/CQ/OQ/PQ/ Data Migration Qualification test cases | bar: 2027-09-03 to 2027-12-17
Note on CA30: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Author 6 in the mock plans we need to clearly call out data validation activity. It cannot be within the 3 week of MC window
Note on B39: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Author 3 @Author 7 - please update the brownfield phases
Note on B49: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Author 4 - Detailed activities Reply: @Author 2 I have added the activities in the Data swim lane
Note on B66: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Author 1 - Security detailed activities
Note on B71: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Author 5 - Please update the detailed activities that need to happen for Validation over the course of the project

## Pivot
Sum of Total Fees | Location
Team | India | Mexico | US | Total Result |  |  | Current % | Proposed % | Proposed Fee | Reduction Fees | Comments
Analytics | 911250 |  | 269280 | 1180530 |  |  | #REF! | 5.7% | 2451000 | #REF!
Data | 515340 |  | 1126080 | 1641420 |  |  | #REF! | 3% | 1290000 | #REF!
Deployment | 371340 |  | 685440 | 1056780 |  |  | #REF! | 3% | 1290000 | #REF!
OCM | 936896 | 512358 | 3060974 | 4510228 |  |  | #REF! | 10% | 4300000 | #REF!
OTC | 1164420 |  | 1546830 | 2711250 |  |  | #REF! | 6% | 2580000 | #REF!
PMO | 737936 |  | 2584144 | 3322080 |  |  | #REF! | 8% | 3440000 | #REF!
PTD | 4541850 |  | 2202480 | 6744330 |  |  | #REF! | 12% | 5160000 | #REF! | Plan 2%; Mfg 4%; Logistics 6%
PTP | 1416960 |  | 1101600 | 2518560 |  |  | #REF! | 5% | 2150000 | #REF!
RTR | 2692215 |  | 1839060 | 4531275 |  |  | #REF! | 10% | 4300000 | #REF!
S&R | 626400 |  | 889200 | 1515600 |  |  | #REF! | 3% | 1290000 | #REF!
Security | 871750 |  | 2257035 | 3128785 |  |  | #REF! | 6% | 2580000 | #REF!
Solution Architecture | 277965 |  | 979488 | 1257453 |  |  | #REF! | 2% | 860000 | #REF!
TAX | 2512200 |  | 1643700 | 4155900 |  |  | #REF! | 8% | 3440000 | #REF! | Vertex Upgrade; E-Invoice 4 Countries
Technology | 5913530 |  | 4122162 | 10035692 |  |  | #REF! | 18% | 7740000 | #REF!
Validation | 36225 |  | 91742 | 127967 |  |  | #REF! | 0.3% | 129000 | #REF!
Total Result | 23526277 | 512358 | 24399215 | 48437850 |  |  | #REF! | 100% | 43000000 | #REF!
|  |  | Target Fees | 43000000
Sum of Planning Fees | Geography
Team | India | Mexico | US | US - Project | Total Result | [8 empty] | PTD % | Total %
Analytics | 56250 |  | 122400 |  | 178650 | [6 empty] | PTD Total | 6240000 |  | 14.51%
Data | 43740 |  | 146880 |  | 190620 | [6 empty] | LOG | 2430000 | 38.94% | 5.651%
Deployment | 0 |  | 0 |  | 0 | [6 empty] | MFG | 3420000 | 54.81% | 7.953%
OCM | 0 | 24114 | 157264 |  | 181378 | [6 empty] | PLAN | 488340 | 7.826% | 1.136%
OTC | 44550 |  | 134640 |  | 179190
PMO | 92496 |  | 322284 |  | 414780
PTD | 209385 |  | 287280 |  | 496665 | [6 empty] | Total | 43000000
PTP | 115965 |  | 134640 |  | 250605
RTR | 84330 |  | 109440 |  | 193770
S&R | 21600 |  | 117000 |  | 138600
Security | 72850 |  | 193460 |  | 266310
Solution Architecture | 31950 |  | 131328 |  | 163278
TAX | 32850 |  | 139500 |  | 172350
Technology | 51900 |  | 305280 | 0 | 357180
Validation | 36225 |  | 91742 |  | 127967
Total Result | 894091 | 24114 | 2393138 | 0 | 3311343
Team | Sum of Total Hours
Analytics | 15640
Data | 11510
Deployment | 8405
OCM | 27025
OTC | 22725
PMO | 15923
PTD | 80270
PTP | 26415
RTR | 48465
S&R | 13860
Security | 19475
Solution Architecture | 6779
TAX | 15371
Technology | 102981
Validation | 366
Total Result | 415210
(empty) | Location
Row Labels | US | India | Location | Mexico | Total Result
PMO
PMO
RTR
RTR
OTC
Order Management
PTD
Delivery Warehouse
Logistics
Manufacturing - PM
Manufacturing - PP
Manufacturing - QM
Plan
PTP | [15 empty] | 0.5
Accounts Payable
Procurement
OCM
Training
OCM
Deployment
Cutover
Testing
Column Labels
| Roles |  |  |  | Fees |  |  |  | Total Roles | Total Fees
Row Labels | US | India | Location | Mexico | US | India | Location | Mexico
PMO | 4 | 3 |  |  | 2584144 | 737936 |  |  | 7 | 3322080
PMO | 4 | 3 |  |  | 2584144 | 737936 |  |  | 7 | 3322080
RTR | 2 | 12 |  |  | 1839060 | 2692215 |  |  | 14 | 4531275
RTR | 2 | 12 |  |  | 1839060 | 2692215 |  |  | 14 | 4531275
OTC | 2 | 5 |  |  | 1546830 | 1164420 |  |  | 7 | 2711250
Order Management | 2 | 5 |  |  | 1546830 | 1164420 |  |  | 7 | 2711250
PTD | 2 | 30 |  |  | 2202480 | 4541850 |  |  | 32 | 6744330
Delivery Warehouse | 1 | 8 |  |  | 1076400 | 1515195 |  |  | 9 | 2591595
Logistics |  | 3 |  |  |  | 354645 |  |  | 3 | 354645
Manufacturing - PM |  | 2 |  |  |  | 314280 |  |  | 2 | 314280
Manufacturing - PP | 1 | 13 |  |  | 1126080 | 1530270 |  |  | 14 | 2656350
Manufacturing - QM |  | 2 |  |  |  | 378000 |  |  | 2 | 378000
Plan |  | 2 |  |  |  | 449460 |  |  | 2 | 449460
PTP | 1 | 7 |  |  | 1101600 | 1416960 |  |  | 8 | 2518560
Accounts Payable |  | 4 |  |  |  | 618030 |  |  | 4 | 618030
Procurement | 1 | 3 |  |  | 1101600 | 798930 |  |  | 4 | 1900530
OCM | 8 | 15 |  | 3 | 3060974 | 936896 |  | 512358 | 26 | 4510228
Training | 1 | 14 |  |  | 396090 | 922424 |  |  | 15 | 1318514
OCM | 7 | 1 |  | 3 | 2664884 | 14472 |  | 512358 | 11 | 3191714
Deployment | 2 | 4 |  |  | 685440 | 371340 |  |  | 6 | 1056780
Cutover |  | 2 |  |  |  | 263340 |  |  | 2 | 263340
Testing |  | 1 |  |  |  | 108000 |  |  | 1 | 108000
Release Management |  | 1 |  |  |  | 0 |  |  | 1 | 0
Testing Support | 2 |  |  |  | 685440 |  |  |  | 2 | 685440
Data | 1 | 2 |  |  | 1126080 | 515340 |  |  | 3 | 1641420
Data |  | 2 |  |  |  | 515340 |  |  | 2 | 515340
Data | 1 |  |  |  | 1126080 |  |  |  | 1 | 1126080
Validation | 2 | 1 |  |  | 91742 | 36225 |  |  | 3 | 127967
Validation | 2 | 1 |  |  | 91742 | 36225 |  |  | 3 | 127967
Security | 6 | 5 |  |  | 2257035 | 871750 |  |  | 11 | 3128785
Security | 6 | 5 |  |  | 2257035 | 871750 |  |  | 11 | 3128785
Agile Coach | 5 | [7 empty] | 5
Intermediate | 1 | [7 empty] | 1
Junior | 1 | [7 empty] | 1
Lead | 1 | [7 empty] | 1
Principal | 1 | [7 empty] | 1
Senior | 1 | [7 empty] | 1
Analytics | 1 | 5 |  |  | 269280 | 911250 |  |  | 6 | 1180530
Analytics | 1 | 5 |  |  | 269280 | 911250 |  |  | 6 | 1180530
Application Architect |  | 5 | [6 empty] | 5
Intermediate |  | 1 | [6 empty] | 1
Junior |  | 1 | [6 empty] | 1
Lead |  | 1 | [6 empty] | 1
Principal |  | 1 | [6 empty] | 1
Senior |  | 1 | [6 empty] | 1
Application Developer |  | 5 | [6 empty] | 5
Intermediate |  | 1 | [6 empty] | 1
Junior |  | 1 | [6 empty] | 1
Lead |  | 1 | [6 empty] | 1
Principal |  | 1 | [6 empty] | 1
Senior |  | 1 | [6 empty] | 1
Artificial Intelligence Architect |  | 5 | [6 empty] | 5
Intermediate |  | 1 | [6 empty] | 1
Junior |  | 1 | [6 empty] | 1
Lead |  | 1 | [6 empty] | 1
Principal |  | 1 | [6 empty] | 1
Senior |  | 1 | [6 empty] | 1
Artificial Intelligence Developer |  | 5 | [6 empty] | 5
Intermediate |  | 1 | [6 empty] | 1
Junior |  | 1 | [6 empty] | 1
Lead |  | 1 | [6 empty] | 1
Principal |  | 1 | [6 empty] | 1
Senior |  | 1 | [6 empty] | 1
Business Analyst |  | 5 | [6 empty] | 5
Intermediate |  | 1 | [6 empty] | 1
Junior |  | 1 | [6 empty] | 1
Lead |  | 1 | [6 empty] | 1
Principal |  | 1 | [6 empty] | 1
Senior |  | 1 | [6 empty] | 1
Business Architect |  | 1 | [6 empty] | 1
Intermediate |  | 1 | [6 empty] | 1
Role |  |  | 1 | [5 empty] | 1
Role Experience |  |  | 1 | [5 empty] | 1
S&R | 1 | 3 |  |  | 889200 | 626400 |  |  | 4 | 1515600
Service Management | 1 | 3 |  |  | 889200 | 626400 |  |  | 4 | 1515600
ServiceNow Architect |  | 1 | [6 empty] | 1
Junior |  | 1 | [6 empty] | 1
Solution Architecture | 1 | 1 |  |  | 979488 | 277965 |  |  | 2 | 1257453
Solution Delivery | 1 | 1 |  |  | 979488 | 277965 |  |  | 2 | 1257453
TAX | 3 | 4 |  |  | 1643700 | 2512200 |  |  | 7 | 4155900
TAX | 3 | 4 |  |  | 1643700 | 2512200 |  |  | 7 | 4155900
Technology | 5 | 11 |  |  | 4122162 | 5913530 |  |  | 16 | 10035692
Development | 4 | 9 |  |  | 3045042 | 5283710 |  |  | 13 | 8328752
Basis | 1 |  |  |  | 1077120 |  |  |  | 1 | 1077120
Basis SME 1 |  | 1 |  |  |  | 374220 |  |  | 1 | 374220
Basis SME 2 |  | 1 |  |  |  | 255600 |  |  | 1 | 255600
Total Result | 46 | 135 | 1 | 3 | 24399215 | 23526277 |  | 512358 | 185 | 48437850

## Staffing
Fees | 96875700 |  | Technology | #VALUE! | [47 empty] | Scoping and Planning Phase | [25 empty] | Build 1 |  |  |  | Build 2 |  |  |  | Build 3 |  |  |  | Build 4 |  |  |  | Build 5 |  |  |  | Build 6 | [6 empty] | SIT 1 | [8 empty] | SIT 2 | [10 empty] | UAT/Val Test | [8 empty] | Dry Run
Hours | #VALUE! |  | Consulting | #VALUE! | [57 empty] | Prep |  | Design 1 | [5 empty] | Design 2 |  |  |  | Design 3 |  |  |  | Design 4 |  |  |  | Design 5 | [19 empty] | MC1 | [8 empty] | MC2 | [10 empty] | MC3 | [8 empty] | CS | [8 empty] | FPC |  |  | HYC
RPH | #VALUE! |  | Tax | #VALUE!
[171 empty] | P9 | P10 | P11 | P12 | P13 | P1 | P2 | P3 | P4 | P5 | P6 | P7 | P8 | P9 | P10 | P11 | P12 | P13 | P1 | P2 | P3 | P4 | P5 | P6 | P7 | P8 | P9 | P10 | P11 | P12 | P13 | P1 | P2 | P3 | P4 | P5 | P6 | P7 | P8 | P9 | P10
[26 empty] | FY26 | FY26 | FY26 | FY26 | FY26 | FY26 | FY26 | FY26 | FY26 | FY26 | FY26 | FY26 | FY26 | FY26 | FY26 | FY26 | FY26 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY29-P1 | FY29 | FY29 | FY29 | FY29 | FY29 | FY29 | FY29 | FY29 | FY29 | FY29 | FY29 | FY29 | FY29 | FY29 | FY29 | FY29 | FY29 | FY29 | FY29 | FY29 | FY29 | FY29 | FY29 | FY29 | FY29 | FY29 | FY29 | Start Date | 2026-01-11 | 2026-02-08 | 2026-03-08 | 2026-04-05 | 2026-05-03 | 2026-05-31 | 2026-06-28 | 2026-07-26 | 2026-08-23 | 2026-09-20 | 2026-10-18 | 2026-11-15 | 2026-12-13 | 2027-01-10 | 2027-02-07 | 2027-03-07 | 2027-04-04 | 2027-05-02 | 2027-05-30 | 2027-06-27 | 2027-07-25 | 2027-08-22 | 2027-09-19 | 2027-10-17 | 2027-11-14 | 2027-12-12
[15 empty] | 96875700 |  | #VALUE! |  |  |  |  | Rate Information |  |  |  | FY26-P09 | FY26-P10 | FY26-P10 | FY26-P10 | FY26-P10 | FY26-P11 | FY26-P11 | FY26-P11 | FY26-P11 | FY26-P12 | FY26-P12 | FY26-P12 | FY26-P12 | FY26-P13 | FY26-P13 | FY26-P13 | FY26-P13 | FY27-P01 | FY27-P01 | FY27-P2 | FY27-P3 | FY27-P3 | FY27-P3 | FY27-P3 | FY27-P4 | FY27-P4 | FY27-P4 | FY27-P4 | FY27-P5 | FY27-P5 | FY27-P5 | FY27-P5 | FY27-P6 | FY27-P6 | FY27-P6 | FY27-P6 | FY27-P7 | FY27-P7 | FY27-P7 | FY27-P7 | FY27-P8 | FY27-P8 | FY27-P8 | FY27-P8 | FY27-P9 | FY27-P9 | FY27-P9 | FY27-P9 | FY27-P10 | FY27-P10 | FY27-P10 | FY27-P10 | FY27-P11 | FY27-P11 | FY27-P11 | FY27-P11 | FY27-P12 | FY27-P12 | FY27-P12 | FY27-P12 | FY27-P13 | FY27-P13 | FY27-P13 | FY27-P13 | FY28-P1 | FY28-P1 | FY28-P1 | FY28-P1 | FY28-P2 | FY28-P2 | FY28-P2 | FY28-P2 | FY28-P3 | FY28-P3 | FY28-P3 | FY28-P3 | FY28-P4 | FY28-P4 | FY28-P4 | FY28-P4 | FY28-P5 | FY28-P5 | FY28-P5 | FY28-P5 | FY28-P6 | FY28-P6 | FY28-P6 | FY28-P6 | FY28-P7 | FY28-P7 | FY28-P7 | FY28-P7 | FY28-P8 | FY28-P8 | FY28-P8 | FY28-P8 | FY28-P9 | FY28-P9 | FY28-P9 | FY28-P9 | FY28-P10 | FY28-P10 | FY28-P10 | FY28-P10 | FY28-P11 | FY28-P11 | FY28-P11 | FY28-P11 | FY28-P12 | FY28-P12 | FY28-P12 | FY28-P12 | FY28-P13 | FY28-P13 | FY28-P13 | FY28-P13 | FY29-P1 | FY29-P1 | FY29-P1 | FY29-P1 | FY29-P2 | FY29-P2 | FY29-P2 | FY29-P2 | FY29-P3 | FY29-P3 | FY29-P3 | FY29-P3 | FY29-P4 | FY29-P4 | FY29-P4 | FY29-P4 | FY29-P5 | FY29-P5 | FY29-P5 | FY29-P5 | FY29-P6 | FY29-P6 | FY29-P6 | FY29-P6 | FY29-P7 | FY29-P7 | FY29-P7 | FY29-P7 | End Date | 2026-02-07 | 2026-03-07 | 2026-04-04 | 2026-05-02 | 2026-05-30 | 2026-06-27 | 2026-07-25 | 2026-08-22 | 2026-09-19 | 2026-10-17 | 2026-11-14 | 2026-12-12 | 2027-01-09 | 2027-02-06 | 2027-03-06 | 2027-04-03 | 2027-05-01 | 2027-05-29 | 2027-06-26 | 2027-07-24 | 2027-08-21 | 2027-09-18 | 2027-10-16 | 2027-11-13 | 2027-12-11 | 2028-01-08 | [15 empty] | #VALUE! | #VALUE!
Process or Enabling | Team | Sub-Team | Role Name | Location | Business | Offering Portfolio | Offering | Geography | Job Family | Sub Family | Deloitte Level | Phase / Work Team | Rate Helper (do not delete) | Client Role | Total Fees | Planning Fees | CV Total Hrs Not Actual Total Hours | Total Hours | Staffing Role | Years of Experience | Staffing Location | Rate Type | Role | Rate Card Level | PM Avg Rates | Rate Card Yr2 Rates | 2026-03-09 | 2026-03-16 | 2026-03-23 | 2026-03-30 | 2026-04-06 | 2026-04-13 | 2026-04-20 | 2026-04-27 | 2026-05-04 | 2026-05-11 | 2026-05-18 | 2026-05-25 | 2026-06-01 | 2026-06-08 | 2026-06-15 | 2026-06-22 | 2026-06-29 | 2026-07-06 | 2026-07-13 | 2026-07-20 | 2026-07-27 | 2026-08-03 | 2026-08-10 | 2026-08-17 | 2026-08-24 | 2026-08-31 | 2026-09-07 | 2026-09-14 | 2026-09-21 | 2026-09-28 | 2026-10-05 | 2026-10-12 | 2026-10-19 | 2026-10-26 | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-07 | 2026-12-14 | 2026-12-21 | 2026-12-28 | 2027-01-04 | 2027-01-11 | 2027-01-18 | 2027-01-25 | 2027-02-01 | 2027-02-08 | 2027-02-15 | 2027-02-22 | 2027-03-01 | 2027-03-08 | 2027-03-15 | 2027-03-22 | 2027-03-29 | 2027-04-05 | 2027-04-12 | 2027-04-19 | 2027-04-26 | 2027-05-03 | 2027-05-10 | 2027-05-17 | 2027-05-24 | 2027-05-31 | 2027-06-07 | 2027-06-14 | 2027-06-21 | 2027-06-28 | 2027-07-05 | 2027-07-12 | 2027-07-19 | 2027-07-26 | 2027-08-02 | 2027-08-09 | 2027-08-16 | 2027-08-23 | 2027-08-30 | 2027-09-06 | 2027-09-13 | 2027-09-20 | 2027-09-27 | 2027-10-04 | 2027-10-11 | 2027-10-18 | 2027-10-25 | 2027-11-01 | 2027-11-08 | 2027-11-15 | 2027-11-22 | 2027-11-29 | 2027-12-06 | 2027-12-13 | 2027-12-20 | 2027-12-27 | 2028-01-03 | 2028-01-10 | 2028-01-17 | 2028-01-24 | 2028-01-31 | 2028-02-07 | 2028-02-14 | 2028-02-21 | 2028-02-28 | 2028-03-06 | 2028-03-13 | 2028-03-20 | 2028-03-27 | 2028-04-03 | 2028-04-10 | 2028-04-17 | 2028-04-24 | 2028-05-01 | 2028-05-08 | 2028-05-15 | 2028-05-22 | 2028-05-29 | 2028-06-05 | 2028-06-12 | 2028-06-19 | 2028-06-26 | 2028-07-03 | 2028-07-10 | 2028-07-17 | 2028-07-24 | 2028-07-31 | 2028-08-07 | 2028-08-14 | 2028-08-21 | 2028-08-28 | 2028-09-04 | 2028-09-11 | 2028-09-18 | 2028-09-25 | 2028-10-02 | 2028-10-09 | 2028-10-16 | 2028-10-23 | 2028-10-30 | 2028-11-06 | 2028-11-13 | 2028-11-20 | 2028-11-27 | 2028-12-04 | FY27-P4 | FY27-P5 | FY27-P6 | FY27-P7 | FY27-P8 | FY27-P9 | FY27-P10 | FY27-P11 | FY27-P12 | FY27-P13 | FY28-P1 | FY28-P2 | FY28-P3 | FY28-P4 | FY28-P5 | FY28-P6 | FY28-P7 | FY28-P8 | FY28-P9 | FY28-P10 | FY28-P11 | FY28-P12 | FY28-P13 | FY29-P1 | FY29-P2 | FY28-P8 | FY28-P9 | FY28-P10 | FY28-P11 | FY28-P12 | FY28-P13 | FY29-P1 | FY29-P2 | FY29-P3 | FY29-P4 | FY29-P5 | FY29-P6 | FY29-P7 | FY29-P8 | FY29-P9 | FY29-P10 | Total | Check
Enabling | PMO | PMO | Project Sponsor | US | Consulting Services | Enterprise Performance | SAP | US | Package and Technology Enablement | Package Program and Solution Management | LMD - Managing Director | PMO-PMO | Technology-Principal-US-Consulting | PMO - Technology | 62046 | 4596 | #VALUE! | 162 | Technology - Principal | 15+ years | Onshore | Consulting | Technology | Principal | 0 | 383 | [26 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | [27 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 4 | 8 | 8 | 8 | 8 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE!
Enabling | PMO | PMO | Engagement Lead | US | Consulting Services | Enterprise Performance | SAP | US | Package and Technology Enablement | Package Program and Solution Management | LMD - Managing Director | PMO-PMO | Technology-Managing Director-US-Consulting | PMO - Technology | 524710 | 45960 | #VALUE! | 1370 | Technology - Managing Director | 10-15 years | Onshore | Consulting | Technology | Managing Director | 0 | 383 | [26 empty] | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 16 | 16 | 16 |  |  | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 |  |  | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 10 | 10 | 10 | 10 | 10 | [22 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 32 | 64 | 64 | 64 | 64 | 64 | 52 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE!
Enabling | PMO | PMO | Program Manager | US | Consulting Services | Enterprise Performance | SAP | US | Package and Technology Enablement | Package Functional Transformation | L65 - Senior Manager | PMO-PMO | Technology-Senior Manager-US-Consulting | PMO - Technology | 979488 | 131328 | #VALUE! | 2864 | Technology - Senior Manager | 7-10 years | Onshore | Consulting | Technology | Senior Manager | 0 | 342 | [26 empty] | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 |  |  | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 |  |  | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 16 | 16 | 16 | 16 | 16 | [22 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 64 | 128 | 128 | 128 | 128 | 128 | 96 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE!
Enabling | PMO | PMO | PMO Consultant | US | Consulting Services | Enterprise Performance | SAP | US | Package and Technology Enablement | Package Functional Transformation | L25 - Analyst | PMO-PMO | Technology-Senior Consultant-US-Consulting | PMO - Technology | 1017900 | 140400 | #VALUE! | 3915 | Technology - Senior Consultant | 3-5 years | Onshore | Consulting | Technology | Senior Consultant | 402.1604 | 260 | [26 empty] | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 |  |  | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 |  |  | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | [27 empty] | 90 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 90 | 180 | 180 | 180 | 180 | 180 | 90 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE!
Enabling | PMO | PMO | Offshore Lead | India | Consulting Services | Enterprise Performance | SAP | India | Package and Technology Enablement | Package Program and Solution Management | LMD - Managing Director | PMO-PMO | Technology-Principal-India-Consulting | PMO - Technology | 95040 | 8640 | #VALUE! | 528 | Technology - Principal | 15+ years | Offshore | Consulting | Technology | Principal | 403.1006 | 180 | [26 empty] | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 6 | 6 | 6 |  |  | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 |  |  | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | [22 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 12 | 24 | 24 | 24 | 24 | 24 | 24 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE!
Enabling | PMO | PMO | Offshore GDM | India | Consulting Services | Enterprise Performance | SAP | India | Package and Technology Enablement | Package Functional Transformation | L65 - Senior Manager | PMO-PMO | Technology-Senior Manager-India-Consulting | PMO - Technology | 394496 | 51456 | #VALUE! | 2944 | Technology - Senior Manager | 7-10 years | Offshore | Consulting | Technology | Senior Manager | 380.1173 | 134 | [26 empty] | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 |  |  | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 |  |  | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | [22 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 64 | 128 | 128 | 128 | 128 | 128 | 128 | 96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE!
Enabling | PMO | PMO | PMO Consultant | India | Consulting Services | Enterprise Performance | SAP | India | Package and Technology Enablement | Package Functional Transformation | L35 - Consultant | PMO-PMO | Technology-Consultant-India-Consulting | PMO - Technology | 248400 | 32400 | #VALUE! | 4140 | Technology - Consultant | 1-3 years | Offshore | Consulting | Technology | Consultant | 264.5474 | 60 | [26 empty] | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 |  |  | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 |  |  | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | [22 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 90 | 180 | 180 | 180 | 180 | 180 | 180 | 135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE!
[15 empty] | 0 | 0 |  | 0 | [6 empty] | 179.3132 | [145 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Process | Solution Architecture | Solution Delivery | Solution Architect | US | Consulting Services | Enterprise Performance | SAP | US | Package and Technology Enablement | Package Functional Transformation | L65 - Senior Manager | Solution Architecture-Solution Delivery | Technology-Senior Manager-US-Consulting | Solution Architecture - Technology | 979488 | 131328 | 0 | 2864 | Technology - Senior Manager | 7-10 years | Onshore | Consulting | Technology | Senior Manager | 126.9617 | 342 | [26 empty] | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 |  |  | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 |  |  | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 16 | 16 | 16 | 16 | 16 | [22 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Process | Solution Architecture | Solution Delivery | Solution Lead - offshore | India | Consulting Services | Enterprise Performance | SAP | India | Package and Technology Enablement | Package Functional Transformation | L55 - Manager | Solution Architecture-Solution Delivery | Technology-Senior Consultant-India-Consulting | Solution Architecture - Technology | 277965 | 31950 | #VALUE! | 3915 | Technology - Senior Consultant | 3-5 years | Offshore | Consulting | Technology | Senior Consultant | 53.0739 | 71 | [28 empty] | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 |  |  | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 |  |  | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | [25 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 90 | 180 | 180 | 180 | 180 | 180 | 180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE!
[15 empty] | 0 | 0 |  | 0 | [6 empty] | 0 | [145 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE!
Process | RTR | RTR | RTR Overall Lead | US | Consulting Services | Enterprise Performance | SAP | US | Package and Technology Enablement | Package Functional Transformation | L65 - Senior Manager | RTR-RTR | Technology-Senior Manager-US-Consulting | RTR - Technology | 984960 | 109440 | 0 | 2880 | Technology - Senior Manager | 7-10 years | Onshore | Consulting | Technology | Senior Manager | 380.1173 | 342 | [28 empty] | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 |  |  | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 |  |  | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | [22 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Process | RTR | RTR | RTR CO Lead | US | Consulting Services | Enterprise Performance | SAP | US | Package and Technology Enablement | Package Functional Transformation | L45 - Senior Consultant | RTR-RTR | Technology-Senior Consultant-US-Consulting | RTR - Technology | 854100 | 0 | 990 | 3285 | Technology - Senior Consultant | 3-5 years | Onshore | Consulting | Technology | Senior Consultant | 85.1772 | 260 | [38 empty] | 45 | 45 | 45 |  |  | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 |  |  | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | [29 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 90 | 180 | 180 | 180 | 180 | 180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Process | RTR | RTR | RTR Offshore Lead (GL/Intercompany) | India | Consulting Services | Enterprise Performance | SAP | India | Package and Technology Enablement | Package Functional Transformation | L55 - Manager | RTR-RTR | Technology-Manager-India-Consulting | RTR - Technology | 400950 | 44550 | 1305 | 4050 | Technology - Manager | 5-7 years | Offshore | Consulting | Technology | Manager | 0 | 99 | [28 empty] | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 |  |  | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 |  |  | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | [22 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 90 | 180 | 180 | 180 | 180 | 180 | 180 | 135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Process | RTR | RTR | RTR AR/FSCM Lead - Offshore | India | Consulting Services | Enterprise Performance | SAP | India | Package and Technology Enablement | Package Functional Transformation | L45 - Senior Consultant | RTR-RTR | Technology-Consultant-India-Consulting | RTR - Technology | 210600 | 0 | 1215 | 3510 | Technology - Consultant | 1-3 years | Offshore | Consulting | Technology | Consultant | 381.296 | 60 | [38 empty] | 45 | 45 | 45 |  |  | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 |  |  | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | [24 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 90 | 180 | 180 | 180 | 180 | 180 | 180 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Process | RTR | RTR | RTR Fixed Assets Lead - Offshore | India | Consulting Services | Enterprise Performance | SAP | India | Package and Technology Enablement | Package Functional Transformation | L45 - Senior Consultant | RTR-RTR | Technology-Senior Consultant-India-Consulting | RTR - Technology | 268380 | 12780 | 1305 | 3780 | Technology - Senior Consultant | 3-5 years | Offshore | Consulting | Technology | Senior Consultant | 322.5349 | 71 | [34 empty] | 45 | 45 | 45 | 45 | 45 | 45 | 45 |  |  | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 |  |  | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | [22 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 90 | 180 | 180 | 180 | 180 | 180 | 180 | 135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Process | RTR | RTR | RTR RAR Lead | India | Consulting Services | Enterprise Performance | SAP | India | Package and Technology Enablement | Package Functional Transformation | L45 - Senior Consultant | RTR-RTR | Technology-Senior Consultant-India-Consulting | RTR - Technology | 207675 | 0 | 630 | 2925 | Technology - Senior Consultant | 3-5 years | Offshore | Consulting | Technology | Senior Consultant | 85.4093 | 71 | [38 empty] | 45 | 45 | 45 |  |  | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 |  |  | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | [37 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 90 | 180 | 180 | 180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Process | RTR | RTR | RTR TRM Lead | India | Consulting Services | Enterprise Performance | SAP | India | Package and Technology Enablement | Package Functional Transformation | L45 - Senior Consultant | RTR-RTR | Technology-Senior Consultant-India-Consulting | RTR - Technology | 249210 | 0 | 1215 | 3510 | Technology - Senior Consultant | 3-5 years | Offshore | Consulting | Technology | Senior Consultant | 62.6882 | 71 | [38 empty] | 45 | 45 | 45 |  |  | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 |  |  | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | [24 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 90 | 180 | 180 | 180 | 180 | 180 | 180 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Process | RTR | RTR | RTR CO Support - Offshore | India | Consulting Services | Enterprise Performance | SAP | India | Package and Technology Enablement | Package Functional Transformation | L35 - Consultant | RTR-RTR | Technology-Consultant-India-Consulting | RTR - Technology | 243000 | 27000 | 1305 | 4050 | Technology - Consultant | 1-3 years | Offshore | Consulting | Technology | Consultant | 62.6729 | 60 | [28 empty] | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 |  |  | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 |  |  | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | [22 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 90 | 180 | 180 | 180 | 180 | 180 | 180 | 135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Process | RTR | RTR | RTR Intercompany/Close Support | India | Consulting Services | Enterprise Performance | SAP | India | Package and Technology Enablement | Package Functional Transformation | L35 - Consultant | RTR-RTR | Technology-Consultant-India-Consulting | RTR - Technology | 216000 | 0 | 1305 | 3600 | Technology - Consultant | 1-3 years | Offshore | Consulting | Technology | Consultant | 62.2708 | 60 | [38 empty] | 45 | 45 | 45 |  |  | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 |  |  | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | [22 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 90 | 180 | 180 | 180 | 180 | 180 | 180 | 135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Process | RTR | RTR | RTR GL Support | India | Consulting Services | Enterprise Performance | SAP | India | Package and Technology Enablement | Package Functional Transformation | L35 - Consultant | RTR-RTR | Technology-Analyst-India-Consulting | RTR - Technology | 166320 | 0 | 1305 | 3465 | Technology - Analyst | 0-1 years | Offshore | Consulting | Technology | Analyst | 62.6882 | 48 | [43 empty] | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 |  |  | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | [22 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 90 | 180 | 180 | 180 | 180 | 180 | 180 | 135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Process | RTR | RTR | RTR RAR Support | India | Consulting Services | Enterprise Performance | SAP | India | Package and Technology Enablement | Package Functional Transformation | L35 - Consultant | RTR-RTR | Technology-Consultant-India-Consulting | RTR - Technology | 216000 | 0 | 1305 | 3600 | Technology - Consultant | 1-3 years | Offshore | Consulting | Technology | Consultant | 53.12 | 60 | [38 empty] | 45 | 45 | 45 |  |  | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 |  |  | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | [22 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 90 | 180 | 180 | 180 | 180 | 180 | 180 | 135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Process | RTR | RTR | RTR TRM Support | India | Consulting Services | Enterprise Performance | SAP | India | Package and Technology Enablement | Package Functional Transformation | L35 - Consultant | RTR-RTR | Technology-Consultant-India-Consulting | RTR - Technology | 216000 | 0 | 1305 | 3600 | Technology - Consultant | 1-3 years | Offshore | Consulting | Technology | Consultant | 53.385 | 60 | [38 empty] | 45 | 45 | 45 |  |  | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 |  |  | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | [22 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 90 | 180 | 180 | 180 | 180 | 180 | 180 | 135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Process | RTR | RTR | RTR EBS Support | India | Consulting Services | Enterprise Performance | SAP | India | Package and Technology Enablement | Package Functional Transformation | L25 - Analyst | RTR-RTR | Technology-Analyst-India-Consulting | RTR - Technology | 153360 | 0 | 1305 | 3195 | Technology - Analyst | 0-1 years | Offshore | Consulting | Technology | Analyst | 53.4779 | 48 | [49 empty] | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 |  |  | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | [22 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 90 | 180 | 180 | 180 | 180 | 180 | 180 | 135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Process | RTR | RTR | RTR FA Support | India | Consulting Services | Enterprise Performance | SAP | India | Package and Technology Enablement | Package Functional Transformation | L25 - Analyst | RTR-RTR | Technology-Analyst-India-Consulting | RTR - Technology | 144720 | 0 | 1125 | 3015 | Technology - Analyst | 0-1 years | Offshore | Consulting | Technology | Analyst | 53.385 | 48 | [49 empty] | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 |  |  | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | [26 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 90 | 180 | 180 | 180 | 180 | 180 | 135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[15 empty] | 0 | 0 |  | 0 | [6 empty] | 53.385 | [145 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Process | TAX | TAX | Tax Global Quality Lead - SAP / Vertex / DRC | US | TAX | Tax Technology Consulting | Tax Technology Consulting | US | Tax Services | Tax Technology Consulting | LMD - Managing Director | TAX-TAX | Tax Advisory-Managing Director-US-Tax | TAX - Tax Advisory | 108100 | 13800 | 0 | 188 | Tax Advisory - Managing Director | 12+ years | Onshore | Tax | Tax Advisory | Managing Director | 43.1608 | 575 | [24 empty] | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2.5 | 2.5 | 2.5 | 2.5 | 1 | 1 | [22 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Process | TAX | TAX | Tax Global Engagement Lead - SAP / Vertex / DRC | US | TAX | Tax Technology Consulting | Tax Technology Consulting | US | Tax Services | Tax Technology Consulting | L65 - Senior Manager | TAX-TAX | Tax Advisory-Senior Manager-US-Tax | TAX - Tax Advisory | 920000 | 120000 | 580 | 1840 | Tax Advisory - Senior Manager | 9-12 years | Onshore | Tax | Tax Advisory | Senior Manager | 42.9872 | 500 | [26 empty] | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 |  |  | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 |  |  | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | [22 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 40 | 80 | 80 | 80 | 80 | 80 | 80 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Process | TAX | TAX | Tax SAP / Vertex Team Lead | India | TAX | Tax Technology Consulting | Tax Technology Consulting | India | Tax Services | Tax Technology Consulting | L55 - Manager | TAX-TAX | Tax Advisory-Manager-India-Tax | TAX - Tax Advisory | 785040 | 10800 | 931 | 3271 | Tax Advisory - Manager | 6-9 years | Offshore | Tax | Tax Advisory | Manager | 0 | 240 | [37 empty] | 45 | 45 | 45 | 45 |  |  | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 |  |  | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | [22 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 90 | 180 | 180 | 136 | 92 | 92 | 92 | 69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Process | TAX | TAX | Tax SAP / Vertex Offshore Team Member | India | TAX | Tax Technology Consulting | Tax Technology Consulting | India | Tax Services | Core Tax | L45 - Senior | TAX-TAX | Tax Advisory-Senior Consultant-India-Tax | TAX - Tax Advisory | 530280 | 3600 | 931 | 2946 | Tax Advisory - Senior Consultant | 3-6 years | Offshore | Tax | Tax Advisory | Senior Consultant | 358.683 | 180 | [37 empty] | 20 | 20 | 20 | 20 |  |  | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 |  |  | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | [22 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 90 | 180 | 180 | 136 | 92 | 92 | 92 | 69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Process | TAX | TAX | Tax DRC Architect | India | TAX | Tax Technology Consulting | Tax Technology Consulting | India | Tax Services | Tax Technology Consulting | L65 - Senior Manager | TAX-TAX | Tax Advisory-Senior Manager-India-Tax | TAX - Tax Advisory | 666600 | 14850 | 300 | 2020 | Tax Advisory - Senior Manager | 9-12 years | Offshore | Tax | Tax Advisory | Senior Manager | 321.7533 | 330 | [37 empty] | 45 | 45 | 45 | 45 |  |  | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 |  |  | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | [39 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 50 | 100 | 100 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Process | TAX | TAX | Tax DRC Offshore Team Member | India | TAX | Tax Technology Consulting | Tax Technology Consulting | India | Tax Services | Core Tax | L45 - Senior | TAX-TAX | Tax Advisory-Senior Consultant-India-Tax | TAX - Tax Advisory | 530280 | 3600 | 931 | 2946 | Tax Advisory - Senior Consultant | 3-6 years | Offshore | Tax | Tax Advisory | Senior Consultant | 98.2425 | 180 | [37 empty] | 20 | 20 | 20 | 20 |  |  | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 |  |  | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 23 | [22 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 90 | 180 | 180 | 136 | 92 | 92 | 92 | 69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Process | TAX | TAX | Tax SAP / Vertex / DRC Onshore Team Member | US | TAX | Tax Technology Consulting | Tax Technology Consulting | US | Tax Services | Core Tax | L45 - Senior | TAX-TAX | Tax Advisory-Senior Consultant-US-Tax | TAX - Tax Advisory | 615600 | 5700 | 820 | 2160 | Tax Advisory - Senior Consultant | 3-6 years | Onshore | Tax | Tax Advisory | Senior Consultant | 77.8422 | 285 | [37 empty] | 20 | 20 | 20 | 20 |  |  | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 |  |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | [22 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 80 | 160 | 160 | 120 | 80 | 80 | 80 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[15 empty] | 0 | 0 |  | 0 | [6 empty] | 122.896 | [145 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Process | OTC | Order Management | Overall OTC Lead | US | Consulting Services | Enterprise Performance | SAP | US | Package and Technology Enablement | Package Functional Transformation | L55 - Manager | OTC-Order Management | Technology-Manager-US-Consulting | OTC - Technology | 1101600 | 134640 | 0 | 3600 | Technology - Manager | 5-7 years | Onshore | Consulting | Technology | Manager | 77.8422 | 306 | [27 empty] | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 |  |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 |  |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | [23 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Process | OTC | Order Management | Order Management & Pricing SME | US | Consulting Services | Enterprise Performance | SAP | US | Package and Technology Enablement | Package Functional Transformation | L35 - Consultant | OTC-Order Management | Technology-Consultant-US-Consulting | OTC - Technology | 445230 | 0 | #VALUE! | 2295 | Technology - Consultant | 1-3 years | Onshore | Consulting | Technology | Consultant | 227.0168 | 194 | [43 empty] | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 |  |  | 45 | [48 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 90 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE!
Process | OTC | Order Management | Order Mgmt Offshore Lead | India | Consulting Services | Enterprise Performance | SAP | India | Package and Technology Enablement | Package Functional Transformation | L55 - Manager | OTC-Order Management | Technology-Manager-India-Consulting | OTC - Technology | 392040 | 44550 | 1215 | 3960 | Technology - Manager | 5-7 years | Offshore | Consulting | Technology | Manager | 0 | 99 | [28 empty] | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 |  |  | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 |  |  | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | [24 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 90 | 180 | 180 | 180 | 180 | 180 | 180 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Process | OTC | Order Management | Pricing & Vistex Integration | India | Consulting Services | Enterprise Performance | SAP | India | Package and Technology Enablement | Package Functional Transformation | L45 - Senior Consultant | OTC-Order Management | Technology-Senior Consultant-India-Consulting | OTC - Technology | 255600 | 0 | 1305 | 3600 | Technology - Senior Consultant | 3-5 years | Offshore | Consulting | Technology | Senior Consultant | 358.7928 | 71 | [38 empty] | 45 | 45 | 45 |  |  | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 |  |  | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | [22 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 90 | 180 | 180 | 180 | 180 | 180 | 180 | 135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Process | OTC | Order Management | Billing | India | Consulting Services | Enterprise Performance | SAP | India | Package and Technology Enablement | Package Functional Transformation | L35 - Consultant | OTC-Order Management | Technology-Consultant-India-Consulting | OTC - Technology | 191700 | 0 | 1215 | 3195 | Technology - Consultant | 1-3 years | Offshore | Consulting | Technology | Consultant | 285.1176 | 60 | [47 empty] | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 |  |  | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | [24 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 90 | 180 | 180 | 180 | 180 | 180 | 180 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Process | OTC | Order Management | Order Processing -Master Data | India | Consulting Services | Enterprise Performance | SAP | India | Package and Technology Enablement | Package Functional Transformation | L25 - Analyst | OTC-Order Management | Technology-Analyst-India-Consulting | OTC - Technology | 157680 | 0 | 1305 | 3285 | Technology - Analyst | 0-1 years | Offshore | Consulting | Technology | Analyst | 85.2564 | 48 | [47 empty] | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 |  |  | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | [22 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 90 | 180 | 180 | 180 | 180 | 180 | 180 | 135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Process | OTC | Order Management | Order Processing aATP | India | Consulting Services | Enterprise Performance | SAP | India | Package and Technology Enablement | Package Functional Transformation | L35 - Consultant | OTC-Order Management | Technology-Consultant-India-Consulting | OTC - Technology | 167400 | 0 | 810 | 2790 | Technology - Consultant | 1-3 years | Offshore | Consulting | Technology | Consultant | 62.8065 | 60 | [47 empty] | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 |  |  | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | [33 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 90 | 180 | 180 | 180 | 180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Process | S&R | Service Management | Service Management Lead | US | Consulting Services | Enterprise Performance | SAP | US | Package and Technology Enablement | Package Functional Transformation | L45 - Senior Consultant | S&R-Service Management | Technology-Senior Consultant-US-Consulting | S&R - Technology | 889200 | 117000 | 0 | 3420 | Technology - Senior Consultant | 3-5 years | Onshore | Consulting | Technology | Senior Consultant | 53.5099 | 260 | [28 empty] | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 |  |  | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 |  |  | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | [36 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Process | S&R | Service Management | Service-Inhouse Repair | India | Consulting Services | Enterprise Performance | SAP | India | Package and Technology Enablement | Package Functional Transformation | L45 - Senior Consultant | S&R-Service Management | Technology-Consultant-India-Consulting | S&R - Technology | 237600 | 21600 | 1305 | 3960 | Technology - Consultant | 1-3 years | Offshore | Consulting | Technology | Consultant | 43.1016 | 60 | [30 empty] | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 |  |  | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 |  |  | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | [22 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 90 | 180 | 180 | 180 | 180 | 180 | 180 | 135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Process | S&R | Service Management | Service - Loaners & Field Service | India | Consulting Services | Enterprise Performance | SAP | India | Package and Technology Enablement | Package Functional Transformation | L25 - Analyst | S&R-Service Management | Technology-Consultant-India-Consulting | S&R - Technology | 191700 | 0 | 1215 | 3195 | Technology - Consultant | 1-3 years | Offshore | Consulting | Technology | Consultant | 53.221 | 60 | [47 empty] | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 |  |  | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | [24 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 90 | 180 | 180 | 180 | 180 | 180 | 180 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Process | S&R | Service Management | EAM - Installed base & Asset Management | India | Consulting Services | Enterprise Performance | SAP | India | Package and Technology Enablement | Package Functional Transformation | L35 - Consultant | S&R-Service Management | Technology-Consultant-India-Consulting | S&R - Technology | 197100 | 0 | 1305 | 3285 | Technology - Consultant | 1-3 years | Offshore | Consulting | Technology | Consultant | 320.3289 | 60 | [47 empty] | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 |  |  | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | [22 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 90 | 180 | 180 | 180 | 180 | 180 | 180 | 135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[15 empty] | 0 | 0 |  | 0 | [6 empty] | 62.5514 | [145 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Process | PTP | Procurement | PTP Overall Lead | US | Consulting Services | Enterprise Performance | SAP | US | Package and Technology Enablement | Package Functional Transformation | L55 - Manager | PTP-Procurement | Technology-Manager-US-Consulting | PTP - Technology | 1101600 | 134640 | 0 | 3600 | Technology - Manager | 5-7 years | Onshore | Consulting | Technology | Manager | 43.018 | 306 | [27 empty] | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 |  |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 |  |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | [23 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Process | PTP | Procurement | PTP Offshore Lead | India | Consulting Services | Enterprise Performance | SAP | India | Package and Technology Enablement | Package Functional Transformation | L45 - Senior Consultant | PTP-Procurement | Technology-Senior Consultant-India-Consulting | PTP - Technology | 287550 | 35145 | #VALUE! | 4050 | Technology - Senior Consultant | 3-5 years | Offshore | Consulting | Technology | Senior Consultant | 53.6137 | 71 | [27 empty] | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 |  |  | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 |  |  | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | [23 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 90 | 180 | 180 | 180 | 180 | 180 | 180 | 90 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #REF!
Process | PTP | Accounts Payable | PTP Offshore AP/Banking SME | India | Consulting Services | Enterprise Performance | SAP | India | Package and Technology Enablement | Package Functional Transformation | L45 - Senior Consultant | PTP-Accounts Payable | Technology-Senior Consultant-India-Consulting | PTP - Technology | 287550 | 35145 | #VALUE! | 4050 | Technology - Senior Consultant | 3-5 years | Offshore | Consulting | Technology | Senior Consultant | 0 | 71 | [27 empty] | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 |  |  | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 |  |  | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | [23 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 90 | 180 | 180 | 180 | 180 | 180 | 180 | 90 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE!
Process | PTP | Procurement | PTP Offshore Procurement Support | India | Consulting Services | Enterprise Performance | SAP | India | Package and Technology Enablement | Package Functional Transformation | L35 - Consultant | PTP-Procurement | Technology-Consultant-India-Consulting | PTP - Technology | 243000 | 29700 | #VALUE! | 4050 | Technology - Consultant | 1-3 years | Offshore | Consulting | Technology | Consultant | 358.7928 | 60 | [27 empty] | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 |  |  | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 |  |  | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | [23 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 90 | 180 | 180 | 180 | 180 | 180 | 180 | 90 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE!
Process | PTP | Procurement | PTP Offshore Indirect SME | India | Consulting Services | Enterprise Performance | SAP | India | Package and Technology Enablement | Package Functional Transformation | L45 - Senior Consultant | PTP-Procurement | Technology-Senior Consultant-India-Consulting | PTP - Technology | 268380 | 15975 | #VALUE! | 3780 | Technology - Senior Consultant | 3-5 years | Offshore | Consulting | Technology | Senior Consultant | 62.4122 | 71 | [33 empty] | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 |  |  | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 |  |  | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | [23 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 90 | 180 | 180 | 180 | 180 | 180 | 180 | 90 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE!
Process | PTP | Accounts Payable | PTP Offshore AP Support | India | Consulting Services | Enterprise Performance | SAP | India | Package and Technology Enablement | Package Functional Transformation | L25 - Analyst | PTP-Accounts Payable | Technology-Analyst-India-Consulting | PTP - Technology | 157680 | 0 | #VALUE! | 3285 | Technology - Analyst | 0-1 years | Offshore | Consulting | Technology | Analyst | 62.4122 | 48 | [43 empty] | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 |  |  | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | [26 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 90 | 180 | 180 | 180 | 180 | 180 | 135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE!
Process | PTP | Accounts Payable | PTP Offshore Ariba Support | India | Consulting Services | Enterprise Performance | SAP | India | Package and Technology Enablement | Package Functional Transformation | L25 - Analyst | PTP-Accounts Payable | Technology-Analyst-India-Consulting | PTP - Technology | 86400 | 0 | #VALUE! | 1800 | Technology - Analyst | 0-1 years | Offshore | Consulting | Technology | Analyst | 53.05 | 48 | [53 empty] | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | [51 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 90 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #REF!
Process | PTP | Accounts Payable | PTP Offshore Support | India | Consulting Services | Enterprise Performance | SAP | India | Package and Technology Enablement | Package Functional Transformation | L25 - Analyst | PTP-Accounts Payable | Technology-Analyst-India-Consulting | PTP - Technology | 86400 | 0 | #VALUE! | 1800 | Technology - Analyst | 0-1 years | Offshore | Consulting | Technology | Analyst | 62.5845 | 48 | [72 empty] | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 |  |  | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | [30 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 90 | 180 | 180 | 180 | 180 | 135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE!
[15 empty] | 0 | 0 |  | 0 | [6 empty] | 42.8238 | [145 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE!
Process | PTD | Delivery Warehouse | Logistics Lead (WM/TM/3PL) | US | Consulting Services | Enterprise Performance | SAP | US | Package and Technology Enablement | Package Functional Transformation | L55 - Manager | PTD-Delivery Warehouse | Technology-Senior Consultant-US-Consulting | PTD - Technology | 1076400 | 140400 | 0 | 4140 | Technology - Senior Consultant | 3-5 years | Onshore | Consulting | Technology | Senior Consultant | 42.7835 | 260 | [26 empty] | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 |  |  | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 |  |  | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | [22 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Process | PTD | Delivery Warehouse | Logistics Lead (WM/TM/3PL) | India | Consulting Services | Enterprise Performance | SAP | India | Package and Technology Enablement | Package Functional Transformation | L55 - Manager | PTD-Delivery Warehouse | Technology-Senior Consultant-India-Consulting | PTD - Technology | 293940 | 38340 | #VALUE! | 4140 | Technology - Senior Consultant | 3-5 years | Offshore | Consulting | Technology | Senior Consultant | 43.46 | 71 | [26 empty] | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 |  |  | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 |  |  | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | [22 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 90 | 180 | 180 | 180 | 180 | 180 | 180 | 135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE!
Process | PTD | Delivery Warehouse | Warehouse - Automation / Production Logistics | India | Consulting Services | Enterprise Performance | SAP | India | Package and Technology Enablement | Package Functional Transformation | L35 - Consultant | PTD-Delivery Warehouse | Technology-Consultant-India-Consulting | PTD - Technology | 240300 | 24300 | #VALUE! | 4005 | Technology - Consultant | 1-3 years | Offshore | Consulting | Technology | Consultant | 0 | 60 | [29 empty] | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 |  |  | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 |  |  | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | [22 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 90 | 180 | 180 | 180 | 180 | 180 | 180 | 135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE!
Process | PTD | Delivery Warehouse | Warehouse - Outbound | India | Consulting Services | Enterprise Performance | SAP | India | Package and Technology Enablement | Package Functional Transformation | L35 - Consultant | PTD-Delivery Warehouse | Technology-Consultant-India-Consulting | PTD - Technology | 156600 | 0 | 630 | 2610 | Technology - Consultant | 1-3 years | Offshore | Consulting | Technology | Consultant | 358.9548 | 60 | [47 empty] | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 |  |  | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | [37 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 90 | 180 | 180 | 180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Process | PTD | Delivery Warehouse | Warehouse - Inbound + Internal | India | Consulting Services | Enterprise Performance | SAP | India | Package and Technology Enablement | Package Functional Transformation | L35 - Consultant | PTD-Delivery Warehouse | Technology-Consultant-India-Consulting | PTD - Technology | 162000 | 0 | 1305 | 2700 | Technology - Consultant | 1-3 years | Offshore | Consulting | Technology | Consultant | 85.3352 | 60 | [48 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 |  |  | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | [22 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 90 | 180 | 180 | 180 | 180 | 180 | 180 | 135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Process | PTD | Delivery Warehouse | Warehouse - Internal | India | Consulting Services | Enterprise Performance | SAP | India | Package and Technology Enablement | Package Functional Transformation | L25 - Analyst | PTD-Delivery Warehouse | Technology-Analyst-India-Consulting | PTD - Technology | 155520 | 0 | 1305 | 3240 | Technology - Analyst | 0-1 years | Offshore | Consulting | Technology | Analyst | 53.1438 | 48 | [48 empty] | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 |  |  | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | [22 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 90 | 180 | 180 | 180 | 180 | 180 | 180 | 135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Process | PTD | Delivery Warehouse | 3PL + XPS lead | India | Consulting Services | Enterprise Performance | SAP | India | Package and Technology Enablement | Package Functional Transformation | L45 - Senior Consultant | PTD-Delivery Warehouse | Technology-Senior Consultant-India-Consulting | PTD - Technology | 284355 | 28755 | 1305 | 4005 | Technology - Senior Consultant | 3-5 years | Offshore | Consulting | Technology | Senior Consultant | 53.1631 | 71 | [29 empty] | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 |  |  | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 |  |  | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | [22 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 90 | 180 | 180 | 180 | 180 | 180 | 180 | 135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Process | PTD | Delivery Warehouse | 3PL + XPS Consultant | India | Consulting Services | Enterprise Performance | SAP | India | Package and Technology Enablement | Package Functional Transformation | L35 - Consultant | PTD-Delivery Warehouse | Technology-Consultant-India-Consulting | PTD - Technology | 162000 | 0 | 1305 | 2700 | Technology - Consultant | 1-3 years | Offshore | Consulting | Technology | Consultant | 54.18 | 60 | [48 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 |  |  | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | [22 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 90 | 180 | 180 | 180 | 180 | 180 | 180 | 135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Process | PTD | Delivery Warehouse | 3PL Analyst | India | Consulting Services | Enterprise Performance | SAP | India | Package and Technology Enablement | Package Functional Transformation | L25 - Analyst | PTD-Delivery Warehouse | Technology-Analyst-India-Consulting | PTD - Technology | 60480 | 0 | 630 | 1260 | Technology - Analyst | 0-1 years | Offshore | Consulting | Technology | Analyst | 43.1308 | 48 | [48 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 |  |  | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | [37 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 90 | 180 | 180 | 180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Process | PTD | Logistics | PTD LATAM Regional Lead | India | Consulting Services | Enterprise Performance | SAP | India | Package and Technology Enablement | Package Functional Transformation | L45 - Senior Consultant | PTD-Logistics | Technology-Senior Consultant-India-Consulting | PTD - Technology | 118215 | 0 | 1080 | 1665 | Technology - Senior Consultant | 3-5 years | Offshore | Consulting | Technology | Senior Consultant | 62.5227 | 71 | [78 empty] | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 |  |  | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | [27 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 90 | 180 | 180 | 180 | 180 | 180 | 90 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Process | PTD | Logistics | PTD EMEA Regional Lead | India | Consulting Services | Enterprise Performance | SAP | India | Package and Technology Enablement | Package Functional Transformation | L45 - Senior Consultant | PTD-Logistics | Technology-Senior Consultant-India-Consulting | PTD - Technology | 118215 | 0 | 0 | 1665 | Technology - Senior Consultant | 3-5 years | Offshore | Consulting | Technology | Senior Consultant | 54.18 | 71 | [78 empty] | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 |  |  | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | [27 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Process | PTD | Logistics | PTD APAC Regional Lead | India | Consulting Services | Enterprise Performance | SAP | India | Package and Technology Enablement | Package Functional Transformation | L45 - Senior Consultant | PTD-Logistics | Technology-Senior Consultant-India-Consulting | PTD - Technology | 118215 | 0 | 0 | 1665 | Technology - Senior Consultant | 3-5 years | Offshore | Consulting | Technology | Senior Consultant | 43.46 | 71 | [78 empty] | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 |  |  | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | [27 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[15 empty] | 0 | 0 |  | 0 | [6 empty] | 63.7032 | [145 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Process | PTD | Manufacturing - PP | PTD Overall Lead | US | Consulting Services | Enterprise Performance | SAP | US | Package and Technology Enablement | Package Functional Transformation | L55 - Manager | PTD-Manufacturing - PP | Technology-Manager-US-Consulting | PTD - Technology | 1126080 | 146880 | 0 | 3680 | Technology - Manager | 5-7 years | Onshore | Consulting | Technology | Manager | 63.7032 | 306 | [26 empty] | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 |  |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 |  |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | [22 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Process | PTD | Manufacturing - PP | PTD Offshore Lead - Overall | India | Consulting Services | Enterprise Performance | SAP | India | Package and Technology Enablement | Package Functional Transformation | L55 - Manager | PTD-Manufacturing - PP | Technology-Manager-India-Consulting | PTD - Technology | 365310 | 8910 | 1305 | 3690 | Technology - Manager | 5-7 years | Offshore | Consulting | Technology | Manager | 63.7032 | 99 | [36 empty] | 45 | 45 | 45 | 45 | 45 |  |  | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 |  |  | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | [22 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 90 | 180 | 180 | 180 | 180 | 180 | 180 | 135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Process | PTD | Manufacturing - PP | Offshore Team Member - Production Planning + MRP | India | Consulting Services | Enterprise Performance | SAP | India | Package and Technology Enablement | Package Functional Transformation | L45 - Senior Consultant | PTD-Manufacturing - PP | Technology-Consultant-India-Consulting | PTD - Technology | 194400 | 0 | 0 | 3240 | Technology - Consultant | 1-3 years | Offshore | Consulting | Technology | Consultant | 0 | 60 | [48 empty] | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 |  |  | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | [22 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Process | PTD | Manufacturing - PP | Offshore Team Member - Production Execution | India | Consulting Services | Enterprise Performance | SAP | India | Package and Technology Enablement | Package Functional Transformation | L45 - Senior Consultant | PTD-Manufacturing - PP | Technology-Senior Consultant-India-Consulting | PTD - Technology | 293940 | 38340 | 0 | 4140 | Technology - Senior Consultant | 3-5 years | Offshore | Consulting | Technology | Senior Consultant | 358.9548 | 71 | [26 empty] | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 |  |  | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 |  |  | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | [22 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Process | PTD | Manufacturing - PP | Offshore Team Member - Production Execution | India | Consulting Services | Enterprise Performance | SAP | India | Package and Technology Enablement | Package Functional Transformation | L35 - Consultant | PTD-Manufacturing - PP | Technology-Analyst-India-Consulting | PTD - Technology | 120960 | 0 | 0 | 2520 | Technology - Analyst | 0-1 years | Offshore | Consulting | Technology | Analyst | 85.742 | 48 | [64 empty] | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 |  |  | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | [22 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Process | PTD | Manufacturing - PP | Offshore Team Member - Production Execution | India | Consulting Services | Enterprise Performance | SAP | India | Package and Technology Enablement | Package Functional Transformation | L35 - Consultant | PTD-Manufacturing - PP | Technology-Analyst-India-Consulting | PTD - Technology | 45360 | 0 | 0 | 945 | Technology - Analyst | 0-1 years | Offshore | Consulting | Technology | Analyst | 63.1183 | 48 | [76 empty] | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 |  |  | 45 | 45 | 45 | 45 | [45 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Process | PTD | Manufacturing - PP | Offshore Team Member - MES Integration | India | Consulting Services | Enterprise Performance | SAP | India | Package and Technology Enablement | Package Functional Transformation | L45 - Senior Consultant | PTD-Manufacturing - PP | Technology-Consultant-India-Consulting | PTD - Technology | 183600 | 0 | 0 | 3060 | Technology - Consultant | 1-3 years | Offshore | Consulting | Technology | Consultant | 62.4404 | 60 | [30 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 |  |  | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | [22 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Process | PTD | Manufacturing - PP | Offshore Team Member - MES Integration | India | Consulting Services | Enterprise Performance | SAP | India | Package and Technology Enablement | Package Functional Transformation | L35 - Consultant | PTD-Manufacturing - PP | Technology-Consultant-India-Consulting | PTD - Technology | 140400 | 0 | 0 | 2340 | Technology - Consultant | 1-3 years | Offshore | Consulting | Technology | Consultant | 54.4071 | 60 | [64 empty] | 0 | 0 | 0 | 0 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 |  |  | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | [22 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Process | PTD | Manufacturing - PP | Offshore Team Member - MES Integration | India | Consulting Services | Enterprise Performance | SAP | India | Package and Technology Enablement | Package Functional Transformation | L25 - Analyst | PTD-Manufacturing - PP | Technology-Consultant-India-Consulting | PTD - Technology | 56700 | 0 | 0 | 945 | Technology - Consultant | 1-3 years | Offshore | Consulting | Technology | Consultant | 54.06 | 60 | [76 empty] | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 |  |  | 45 | 45 | 45 | 45 | [45 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Process | PTD | Manufacturing - PP | Offshore Team Member - Production Master Data | India | Consulting Services | Enterprise Performance | SAP | India | Package and Technology Enablement | Package Functional Transformation | L35 - Consultant | PTD-Manufacturing - PP | Technology-Analyst-India-Consulting | PTD - Technology | 84240 | 0 | 0 | 1755 | Technology - Analyst | 0-1 years | Offshore | Consulting | Technology | Analyst | 63.3018 | 48 | [76 empty] | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 |  |  | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | [27 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Process | PTD | Manufacturing - PP | Offshore Team Member - Production Master Data | India | Consulting Services | Enterprise Performance | SAP | India | Package and Technology Enablement | Package Functional Transformation | L25 - Analyst | PTD-Manufacturing - PP | Technology-Analyst-India-Consulting | PTD - Technology | 45360 | 0 | 0 | 945 | Technology - Analyst | 0-1 years | Offshore | Consulting | Technology | Analyst | 54.4338 | 48 | [76 empty] | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 |  |  | 45 | 45 | 45 | 45 | [45 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Process | PTD | Manufacturing - QM | Offshore Team Member - Quality Mgmt SME | India | Consulting Services | Enterprise Performance | SAP | India | Package and Technology Enablement | Package Functional Transformation | L45 - Senior Consultant | PTD-Manufacturing - QM | Technology-Consultant-India-Consulting | PTD - Technology | 248400 | 32400 | 0 | 4140 | Technology - Consultant | 1-3 years | Offshore | Consulting | Technology | Consultant | 43.46 | 60 | [26 empty] | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 |  |  | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 |  |  | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | [22 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Process | PTD | Manufacturing - QM | Offshore Team Member - Quality Mgmt SME | India | Consulting Services | Enterprise Performance | SAP | India | Package and Technology Enablement | Package Functional Transformation | L25 - Analyst | PTD-Manufacturing - QM | Technology-Analyst-India-Consulting | PTD - Technology | 129600 | 0 | 0 | 2700 | Technology - Analyst | 0-1 years | Offshore | Consulting | Technology | Analyst | 54.1431 | 48 | [48 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 |  |  | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | [22 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Process | PTD | Manufacturing - PP | PTD - PP/QM LATAM Regional Lead | India | Consulting Services | Enterprise Performance | SAP | India | Package and Technology Enablement | Package Functional Transformation | L55 - Manager | PTD-Manufacturing - PP | Technology-Consultant-India-Consulting | PTD - Technology | 0 | 0 | 0 | 0 | Technology - Consultant | 1-3 years | Offshore | Consulting | Technology | Consultant | 43.46 | 60 | [144 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Process | PTD | Manufacturing - PP | PTD - PP/QM EMEA Regional Lead | India | Consulting Services | Enterprise Performance | SAP | India | Package and Technology Enablement | Package Functional Transformation | L55 - Manager | PTD-Manufacturing - PP | Technology-Consultant-India-Consulting | PTD - Technology | 0 | 0 | 0 | 0 | Technology - Consultant | 1-3 years | Offshore | Consulting | Technology | Consultant | 62.4404 | 60 | [144 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Process | PTD | Manufacturing - PP | PTD - PP/QM APAC Regional Lead | India | Consulting Services | Enterprise Performance | SAP | India | Package and Technology Enablement | Package Functional Transformation | L55 - Manager | PTD-Manufacturing - PP | Technology-Consultant-India-Consulting | PTD - Technology | 0 | 0 | 0 | 0 | Technology - Consultant | 1-3 years | Offshore | Consulting | Technology | Consultant | 43.557 | 60 | [144 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Process | PTD | Manufacturing - PM | Offshore Team Member - Plant Maintenance SME | India | Consulting Services | Enterprise Performance | SAP | India | Package and Technology Enablement | Package Functional Transformation | L35 - Consultant | PTD-Manufacturing - PM | Technology-Senior Consultant-India-Consulting | PTD - Technology | 230040 | 0 | 0 | 3240 | Technology - Senior Consultant | 3-5 years | Offshore | Consulting | Technology | Senior Consultant | 0 | 71 | [48 empty] | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 |  |  | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | [22 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Process | PTD | Manufacturing - PM | Offshore Team Member - Plant Maintenance Master Data | India | Consulting Services | Enterprise Performance | SAP | India | Package and Technology Enablement | Package Functional Transformation | L25 - Analyst | PTD-Manufacturing - PM | Technology-Analyst-India-Consulting | PTD - Technology | 84240 | 0 | 0 | 1755 | Technology - Analyst | 0-1 years | Offshore | Consulting | Technology | Analyst | 0 | 48 | [76 empty] | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 |  |  | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | [27 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Process | PTD | Plan | Offshore Team Member - Planning SME | India | Consulting Services | Enterprise Performance | SAP | India | Package and Technology Enablement | Package Functional Transformation | L45 - Senior Consultant | PTD-Plan | Technology-Senior Consultant-India-Consulting | PTD - Technology | 293940 | 38340 | 0 | 4140 | Technology - Senior Consultant | 3-5 years | Offshore | Consulting | Technology | Senior Consultant | 0 | 71 | [26 empty] | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 |  |  | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 |  |  | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | [22 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Process | PTD | Plan | Offshore Team Member - Planning SME | India | Consulting Services | Enterprise Performance | SAP | India | Package and Technology Enablement | Package Functional Transformation | L25 - Analyst | PTD-Plan | Technology-Analyst-India-Consulting | PTD - Technology | 155520 | 0 | 0 | 3240 | Technology - Analyst | 0-1 years | Offshore | Consulting | Technology | Analyst | 53.65 | 48 | [48 empty] | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 |  |  | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | [22 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
[15 empty] | 0 | 0 |  | 0 | [6 empty] | 43.5269 | [145 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Enabling | Technology | Development | Technology Lead | US | Consulting Services | Enterprise Performance | SAP | US | Package and Technology Enablement | Package Functional Transformation | L65 - Senior Manager | Technology -Development | Technology-Senior Manager-US-Consulting | Technology - Technology | 880992 | 109440 | 0 | 2576 | Technology - Senior Manager | 7-10 years | Onshore | Consulting | Technology | Senior Manager | 62.4404 | 342 | [28 empty] | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 |  |  | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 |  |  | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 32 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | [27 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Enabling | Technology | Development | Development Lead | US | Consulting Services | Enterprise Performance | SAP | US | Package and Technology Enablement | Package Functional Transformation | L55 - Manager | Technology -Development | Technology-Manager-US-Consulting | Technology - Technology | 1077120 | 97920 | 1160 | 3520 | Technology - Manager | 5-7 years | Onshore | Consulting | Technology | Manager | 43.1308 | 306 | [30 empty] | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 |  |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 |  |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | [22 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 80 | 160 | 160 | 160 | 160 | 160 | 160 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Enabling | Technology | Development | Dev Coordinator - ABAP (USDC) | US | Consulting Services | Enterprise Performance | SAP | US - Project | Package and Technology Enablement | Package Technical Transformation | L45 - Senior Consultant | Technology -Development | Technology-Senior Consultant-US-Consulting | Technology - Technology | 795600 | 0 | 1215 | 3060 | Technology - Senior Consultant | 3-5 years | Onshore | Consulting | Technology | Senior Consultant | 0 | 260 | [50 empty] | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 |  |  | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | [24 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 90 | 180 | 180 | 180 | 180 | 180 | 180 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Enabling | Technology | Development | Dev Coordinator - ABAP/Middleware | US | Consulting Services | Enterprise Performance | SAP | US | Package and Technology Enablement | Package Functional Transformation | L45 - Senior Consultant | Technology -Development | Tech Consultant-Senior-US-Technology | Technology - Tech Consultant | 291330 | 0 | 180 | 1755 | Tech Consultant - Senior | 6-9 years | Onshore | Technology | Tech Consultant | Senior | 378.9096 | 166 | [56 empty] | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 |  |  | 45 | 45 | [47 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 90 | 90 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Enabling | Technology | Basis | Basis Lead | US | Consulting Services | Enterprise Performance | SAP | US | Package and Technology Enablement | Package Functional Transformation | L55 - Manager | Technology -Basis | Technology-Manager-US-Consulting | Technology - Technology | 1077120 | 97920 | 1160 | 3520 | Technology - Manager | 5-7 years | Onshore | Consulting | Technology | Manager | 359.5923 | 306 | [30 empty] | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 |  |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 |  |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | [22 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 80 | 160 | 160 | 160 | 160 | 160 | 160 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Enabling | Technology | Development | Development Lead - India | India | Consulting Services | Enterprise Performance | SAP | India | Package and Technology Enablement | Package Functional Transformation | L45 - Senior Consultant | Technology -Development | Technology-Senior Consultant-India-Consulting | Technology - Technology | 261280 | 34080 | 1160 | 3680 | Technology - Senior Consultant | 3-5 years | Offshore | Consulting | Technology | Senior Consultant | 881.1609 | 71 | [26 empty] | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 |  |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 |  |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | [22 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 80 | 160 | 160 | 160 | 160 | 160 | 160 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Enabling | Technology | Development | Development - Innovation Pool of hours - M | India | Consulting Services | Enterprise Performance | SAP | India | Package and Technology Enablement | Package Functional Transformation | L55 - Manager | Technology -Development | Technology-Manager-India-Consulting | Technology - Technology | 367290 | 0 | 1643 | 3710 | Technology - Manager | 5-7 years | Offshore | Consulting | Technology | Manager | 324.8346 | 99 | [52 empty] | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | [22 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 212 | 212 | 212 | 212 | 212 | 212 | 212 | 159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Enabling | Technology | Development | Development - Innovation Pool of hours - SC | India | Consulting Services | Enterprise Performance | SAP | India | Package and Technology Enablement | Package Functional Transformation | L45 - Senior Consultant | Technology -Development | Technology-Senior Consultant-India-Consulting | Technology - Technology | 790230 | 0 | 4929 | 11130 | Technology - Senior Consultant | 3-5 years | Offshore | Consulting | Technology | Senior Consultant | 359.5923 | 71 | [52 empty] | 159 | 159 | 159 | 159 | 159 | 159 | 159 | 159 | 159 | 159 | 159 | 159 | 159 | 159 | 159 | 159 | 159 | 159 | 159 | 159 | 159 | 159 | 159 | 159 | 159 | 159 | 159 | 159 | 159 | 159 | 159 | 159 | 159 | 159 | 159 | 159 | 159 | 159 | 159 | 159 | 159 | 159 | 159 | 159 | 159 | 159 | 159 | 159 | 159 | 159 | 159 | 159 | 159 | 159 | 159 | 159 | 159 | 159 | 159 | 159 | 159 | 159 | 159 | 159 | 159 | 159 | 159 | 159 | 159 | 159 | [22 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 636 | 636 | 636 | 636 | 636 | 636 | 636 | 477 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Enabling | Technology | Development | Development - Innovation Pool of hours - C | India | Consulting Services | Enterprise Performance | SAP | India | Package and Technology Enablement | Package Functional Transformation | L35 - Consultant | Technology -Development | Technology-Consultant-India-Consulting | Technology - Technology | 894600 | 0 | 6603 | 14910 | Technology - Consultant | 1-3 years | Offshore | Consulting | Technology | Consultant | 62.4404 | 60 | [52 empty] | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | 213 | [22 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 852 | 852 | 852 | 852 | 852 | 852 | 852 | 639 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Enabling | Technology | Development | Development - Innovation Pool of hours - A | India | Consulting Services | Enterprise Performance | SAP | India | Package and Technology Enablement | Package Functional Transformation | L25 - Analyst | Technology -Development | Technology-Analyst-India-Consulting | Technology - Technology | 356160 | 0 | 3286 | 7420 | Technology - Analyst | 0-1 years | Offshore | Consulting | Technology | Analyst | 86.524 | 48 | [52 empty] | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | [22 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 424 | 424 | 424 | 424 | 424 | 424 | 424 | 318 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Enabling | Technology | Development | Development - Remidiation Pool of hours - M | India | Consulting Services | Enterprise Performance | SAP | India | Package and Technology Enablement | Package Functional Transformation | L55 - Manager | Technology -Development | Technology-Manager-India-Consulting | Technology - Technology | 401940 | 0 | 1798 | 4060 | Technology - Manager | 5-7 years | Offshore | Consulting | Technology | Manager | 63.3103 | 99 | [52 empty] | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | [22 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 232 | 232 | 232 | 232 | 232 | 232 | 232 | 174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Enabling | Technology | Development | Development - Remidiation Pool of hours - SC | India | Consulting Services | Enterprise Performance | SAP | India | Package and Technology Enablement | Package Functional Transformation | L45 - Senior Consultant | Technology -Development | Technology-Senior Consultant-India-Consulting | Technology - Technology | 859810 | 0 | 5363 | 12110 | Technology - Senior Consultant | 3-5 years | Offshore | Consulting | Technology | Senior Consultant | 53.8131 | 71 | [52 empty] | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | [22 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 692 | 692 | 692 | 692 | 692 | 692 | 692 | 519 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Enabling | Technology | Development | Development - Remidiation Pool of hours - C | India | Consulting Services | Enterprise Performance | SAP | India | Package and Technology Enablement | Package Functional Transformation | L35 - Consultant | Technology -Development | Technology-Consultant-India-Consulting | Technology - Technology | 966000 | 0 | 7130 | 16100 | Technology - Consultant | 1-3 years | Offshore | Consulting | Technology | Consultant | 43.262 | 60 | [52 empty] | 230 | 230 | 230 | 230 | 230 | 230 | 230 | 230 | 230 | 230 | 230 | 230 | 230 | 230 | 230 | 230 | 230 | 230 | 230 | 230 | 230 | 230 | 230 | 230 | 230 | 230 | 230 | 230 | 230 | 230 | 230 | 230 | 230 | 230 | 230 | 230 | 230 | 230 | 230 | 230 | 230 | 230 | 230 | 230 | 230 | 230 | 230 | 230 | 230 | 230 | 230 | 230 | 230 | 230 | 230 | 230 | 230 | 230 | 230 | 230 | 230 | 230 | 230 | 230 | 230 | 230 | 230 | 230 | 230 | 230 | [22 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 920 | 920 | 920 | 920 | 920 | 920 | 920 | 690 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Enabling | Technology | Development | Development - Remidiation Pool of hours - A | India | Consulting Services | Enterprise Performance | SAP | India | Package and Technology Enablement | Package Functional Transformation | L25 - Analyst | Technology -Development | Technology-Analyst-India-Consulting | Technology - Technology | 386400 | 0 | 3565 | 8050 | Technology - Analyst | 0-1 years | Offshore | Consulting | Technology | Analyst | 86.524 | 48 | [52 empty] | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 115 | [22 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 460 | 460 | 460 | 460 | 460 | 460 | 460 | 345 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Enabling | Technology | Basis SME 1 | Basis SME | India | Consulting Services | Enterprise Performance | SAP | India | Package and Technology Enablement | Package Functional Transformation | L55 - Manager | Technology -Basis SME 1 | Technology-Manager-India-Consulting | Technology - Technology | 374220 | 17820 | 1305 | 3780 | Technology - Manager | 5-7 years | Offshore | Consulting | Technology | Manager | 63.3103 | 99 | [34 empty] | 45 | 45 | 45 | 45 | 45 | 45 | 45 |  |  | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 |  |  | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | [22 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 90 | 180 | 180 | 180 | 180 | 180 | 180 | 135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Enabling | Technology | Basis SME 2 | Basis SME | India | Consulting Services | Enterprise Performance | SAP | India | Package and Technology Enablement | Package Functional Transformation | L45 - Senior Consultant | Technology -Basis SME 2 | Technology-Senior Consultant-India-Consulting | Technology - Technology | 255600 | 0 | 1305 | 3600 | Technology - Senior Consultant | 3-5 years | Offshore | Consulting | Technology | Senior Consultant | 53.8131 | 71 | [38 empty] | 45 | 45 | 45 |  |  | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 |  |  | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | [22 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 90 | 180 | 180 | 180 | 180 | 180 | 180 | 135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Enabling | Data | Data | Data Lead / Migration Lead | US | Consulting Services | Enterprise Performance | SAP | US | Package and Technology Enablement | Package Functional Transformation | L55 - Manager | Data-Data | Technology-Manager-US-Consulting | Data - Technology | 1126080 | 146880 | 1160 | 3680 | Technology - Manager | 5-7 years | Onshore | Consulting | Technology | Manager | 43.262 | 306 | [26 empty] | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 |  |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 |  |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | [22 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 80 | 160 | 160 | 160 | 160 | 160 | 160 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Enabling | Data | Data | Data SME1 | India | Consulting Services | Enterprise Performance | SAP | India | Package and Technology Enablement | Package Functional Transformation | L45 - Senior Consultant | Data-Data | Technology-Senior Consultant-India-Consulting | Data - Technology | 293940 | 38340 | 1305 | 4140 | Technology - Senior Consultant | 3-5 years | Offshore | Consulting | Technology | Senior Consultant | 85.6529 | 71 | [26 empty] | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 |  |  | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 |  |  | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | [22 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 90 | 180 | 180 | 180 | 180 | 180 | 180 | 135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Enabling | Data | Data | Data SME2 | India | Consulting Services | Enterprise Performance | SAP | India | Package and Technology Enablement | Package Functional Transformation | L35 - Consultant | Data-Data | Technology-Consultant-India-Consulting | Data - Technology | 221400 | 5400 | #VALUE! | 3690 | Technology - Consultant | 1-3 years | Offshore | Consulting | Technology | Consultant | 62.8065 | 60 | [36 empty] | 45 | 45 | 45 | 45 | 45 |  |  | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 |  |  | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | [22 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 90 | 180 | 180 | 180 | 180 | 180 | 180 | 135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE!
Enabling | Analytics | Analytics | Analytics Architect | US | Consulting Services | Enterprise Performance | SAP | US | Package and Technology Enablement | Package Functional Transformation | L55 - Manager | Analytics-Analytics | Technology-Manager-US-Consulting | Analytics - Technology | 269280 | 122400 | 0 | 880 | Technology - Manager | 5-7 years | Onshore | Consulting | Technology | Manager | 358.9548 | 306 | [28 empty] | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 |  |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | [92 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Enabling | Analytics | Analytics | Analytics Offshore Lead | India | Consulting Services | Enterprise Performance | SAP | India | Package and Technology Enablement | Package Functional Transformation | L45 - Senior Consultant | Analytics-Analytics | Technology-Senior Consultant-India-Consulting | Analytics - Technology | 287550 | 31950 | #VALUE! | 4050 | Technology - Senior Consultant | 3-5 years | Offshore | Consulting | Technology | Senior Consultant | 62.4404 | 71 | [28 empty] | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 |  |  | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 |  |  | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | [22 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 90 | 180 | 180 | 180 | 180 | 180 | 180 | 135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE!
Enabling | Analytics | Analytics | Analytics Offshore Support | India | Consulting Services | Enterprise Performance | SAP | India | Package and Technology Enablement | Package Functional Transformation | L35 - Consultant | Analytics-Analytics | Technology-Consultant-India-Consulting | Analytics - Technology | 240300 | 24300 | #VALUE! | 4005 | Technology - Consultant | 1-3 years | Offshore | Consulting | Technology | Consultant | 53.3268 | 60 | [29 empty] | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 |  |  | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 |  |  | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | [22 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 90 | 180 | 180 | 180 | 180 | 180 | 180 | 135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE!
Enabling | Analytics | Analytics | Analytics Offshore Support | India | Consulting Services | Enterprise Performance | SAP | India | Package and Technology Enablement | Package Functional Transformation | L35 - Consultant | Analytics-Analytics | Technology-Consultant-India-Consulting | Analytics - Technology | 170100 | 0 | 1080 | 2835 | Technology - Consultant | 1-3 years | Offshore | Consulting | Technology | Consultant | 344.93 | 60 | [52 empty] | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 |  |  | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | [27 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 90 | 180 | 180 | 180 | 180 | 180 | 90 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Enabling | Analytics | Analytics | Analytics Offshore Support | India | Consulting Services | Enterprise Performance | SAP | India | Package and Technology Enablement | Package Functional Transformation | L35 - Consultant | Analytics-Analytics | Technology-Consultant-India-Consulting | Analytics - Technology | 137700 | 0 | 540 | 2295 | Technology - Consultant | 1-3 years | Offshore | Consulting | Technology | Consultant | 62.4947 | 60 | [52 empty] | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 |  |  | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | [39 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 90 | 180 | 180 | 90 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Enabling | Analytics | Analytics | Analytics Offshore Support | India | Consulting Services | Enterprise Performance | SAP | India | Package and Technology Enablement | Package Functional Transformation | L25 - Analyst | Analytics-Analytics | Technology-Analyst-India-Consulting | Analytics - Technology | 75600 | 0 | 0 | 1575 | Technology - Analyst | 0-1 years | Offshore | Consulting | Technology | Analyst | 53.1438 | 48 | [52 empty] | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | [57 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[15 empty] | 0 | 0 |  | 0 |  | 0 |  |  |  |  | 53.5286 | [145 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Enabling | Deployment | Testing Support | Testing and Cutover Lead | US | Consulting Services | Enterprise Performance | SAP | US | Package and Technology Enablement | Package Functional Transformation | L55 - Manager | Deployment-Testing Support | Technology-Manager-US-Consulting | Deployment - Technology | 685440 | 0 | 0 | 2240 | Technology - Manager | 5-7 years | Onshore | Consulting | Technology | Manager | 53.34 | 306 | [60 empty] | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 |  |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | [26 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Enabling | Deployment | Testing Support | Testing Support | US | Consulting Services | Enterprise Performance | SAP | US | Package and Technology Enablement | Package Functional Transformation | L35 - Consultant | Deployment-Testing Support | Technology-Consultant-US-Consulting | Deployment - Technology | 0 | 0 | 0 | 0 | Technology - Consultant | 1-3 years | Onshore | Consulting | Technology | Consultant | 42.6166 | 194 | [72 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [26 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Enabling | Deployment | Cutover | Deployment Offshore Lead | India | Consulting Services | Enterprise Performance | SAP | India | Package and Technology Enablement | Package Functional Transformation | L45 - Senior Consultant | Deployment-Cutover | Technology-Senior Consultant-India-Consulting | Deployment - Technology | 166140 | 0 | #VALUE! | 2340 | Technology - Senior Consultant | 3-5 years | Offshore | Consulting | Technology | Senior Consultant | 0 | 71 | [68 empty] | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 |  |  | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | [22 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 90 | 180 | 180 | 180 | 180 | 180 | 180 | 135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE!
Enabling | Deployment | Testing | Testing Support | India | Consulting Services | Enterprise Performance | SAP | India | Package and Technology Enablement | Package Functional Transformation | L35 - Consultant | Deployment-Testing | Technology-Consultant-India-Consulting | Deployment - Technology | 108000 | 0 | 945 | 1800 | Technology - Consultant | 1-3 years | Offshore | Consulting | Technology | Consultant | 364.9257 | 60 | [72 empty] | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 |  |  | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | [30 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 90 | 180 | 180 | 180 | 180 | 135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Enabling | Deployment | Cutover | Cutover Support | India | Consulting Services | Enterprise Performance | SAP | India | Package and Technology Enablement | Package Functional Transformation | L25 - Analyst | Deployment-Cutover | Technology-Analyst-India-Consulting | Deployment - Technology | 97200 | 0 | #VALUE! | 2025 | Technology - Analyst | 0-1 years | Offshore | Consulting | Technology | Analyst | 0 | 48 | [75 empty] | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 |  |  | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | [22 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 90 | 180 | 180 | 180 | 180 | 180 | 180 | 135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE! | #VALUE!
Enabling | Deployment | Release Management | Release Management | India | Consulting Services | Enterprise Performance | SAP | India | Package and Technology Enablement | Package Functional Transformation | L35 - Consultant | Deployment-Release Management | Technology-Consultant-India-Consulting | Deployment - Technology | 0 | 0 | 0 | 0 | Technology - Consultant | 1-3 years | Offshore | Consulting | Technology | Consultant | 64.0408 | 60 | [144 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[15 empty] | 0 | 0 |  | 0 | 0 | 0 | --- |  |  |  | 54.06 | [145 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Enabling | Security | Security | Cyber Executive | US | Consulting Services | Cyber | Enterprise Security | US | Strategy, Growth, and Transformation | Enterprise Technology Strategy and Transformation | LMD - Managing Director | Security-Security | Cyber Security -Managing Director-US-Consulting | Security - Cyber Security | 78660 | 8740 | 58 | 180 | Cyber Security - Managing Director | 10-15 years | Onshore | Consulting | Cyber Security | Managing Director | 43.808 | 437 | [28 empty] | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | [22 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 4 | 8 | 8 | 8 | 8 | 8 | 8 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Enabling | Security | Security | Cyber Lead | US | Consulting Services | Cyber | Enterprise Security | US | Strategy, Growth, and Transformation | Enterprise Technology Strategy and Transformation | L65 - Senior Manager | Security-Security | Cyber Security -Senior Manager-US-Consulting | Security - Cyber Security | 352320 | 58720 | 0 | 960 | Cyber Security - Senior Manager | 7-10 years | Onshore | Consulting | Cyber Security | Senior Manager | 0 | 367 | [28 empty] | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 |  |  | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 |  |  | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | [22 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Enabling | Security | Security | Cyber Delivery Manager | US | Consulting Services | Cyber | Enterprise Security | US | Package and Technology Enablement | Package Configuration and Integration Solutions | L55 - Delivery Manager | Security-Security | Cyber Security -Manager-US-Consulting | Security - Cyber Security | 982800 | 0 | #VALUE! | 3120 | Cyber Security - Manager | 5-7 years | Onshore | Consulting | Cyber Security | Manager | 0 | 315 | [38 empty] | 40 | 40 | 40 |  |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 |  |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | [24 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 80 | 160 | 160 | 160 | 160 | 160 | 160 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Enabling | Security | Security | Offshore - Cyber assessment | India | Consulting Services | Cyber | Cyber Strategy & Transformation | India | Strategy, Growth, and Transformation | Enterprise Technology Strategy and Transformation | L45 - Senior Consultant | Security-Security | Cybersecurity Consultant-Senior-India-Technology | Security - Cybersecurity Consultant | 22050 | 22050 | 0 | 450 | Cybersecurity Consultant - Senior | 6-9 years | Offshore | Technology | Cybersecurity Consultant | Senior | 417.3869 | 49 | [28 empty] | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | [106 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Enabling | Security | Security | Controls Lead | US | Consulting Services | Cyber | Enterprise Security | US | Package and Technology Enablement | Package Configuration and Integration Solutions | L55 - Delivery Manager | Security-Security | Cyber Security -Manager-US-Consulting | Security - Cyber Security | 368550 | 0 | 0 | 1170 | Cyber Security - Manager | 5-7 years | Onshore | Consulting | Cyber Security | Manager | 390.948 | 315 | [38 empty] | 45 | 45 | 45 |  |  | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | [78 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Enabling | Security | Security | Offshore - Controls Lead | India | Consulting Services | Cyber | Cyber Strategy & Transformation | India | Strategy, Growth, and Transformation | Enterprise Technology Strategy and Transformation | L45 - Senior Consultant | Security-Security | Cyber Security -Senior Consultant-India-Consulting | Security - Cyber Security | 121680 | 0 | 0 | 1170 | Cyber Security - Senior Consultant | 3-5 years | Offshore | Consulting | Cyber Security | Senior Consultant | 288.3718 | 104 | [38 empty] | 45 | 45 | 45 |  |  | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | [78 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Enabling | Security | Security | Offshore - Security Lead | India | Consulting Services | Cyber | Cyber Strategy & Transformation | India | Strategy, Growth, and Transformation | Enterprise Technology Strategy and Transformation | L55 - Manager | Security-Security | Cyber Security -Manager-India-Consulting | Security - Cyber Security | 447040 | 50800 | 1080 | 3520 | Cyber Security - Manager | 5-7 years | Offshore | Consulting | Cyber Security | Manager | 156 | 127 | [28 empty] | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 |  |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 |  |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | [24 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 80 | 160 | 160 | 160 | 160 | 160 | 160 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Enabling | Security | Security | Offshore - Security Team Member | India | Consulting Services | Cyber | Cyber Strategy & Transformation | India | Strategy, Growth, and Transformation | Enterprise Technology Strategy and Transformation | L45 - Senior Consultant | Security-Security | Cybersecurity Consultant-Senior-India-Technology | Security - Cybersecurity Consultant | 167580 | 0 | 1305 | 3420 | Cybersecurity Consultant - Senior | 6-9 years | Offshore | Technology | Cybersecurity Consultant | Senior | 279.0692 | 49 | [44 empty] | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 |  |  | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | [22 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 90 | 180 | 180 | 180 | 180 | 180 | 180 | 135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Enabling | Security | Security | Offshore - Security Team member | India | Consulting Services | Cyber | Cyber Strategy & Transformation | India | Strategy, Growth, and Transformation | Enterprise Technology Strategy and Transformation | L35 - Consultant | Security-Security | Cybersecurity Consultant-Intermediate-India-Technology | Security - Cybersecurity Consultant | 113400 | 0 | 1305 | 3240 | Cybersecurity Consultant - Intermediate | 3-6 years | Offshore | Technology | Cybersecurity Consultant | Intermediate | 156.72 | 35 | [48 empty] | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 |  |  | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | [22 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 90 | 180 | 180 | 180 | 180 | 180 | 180 | 135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Enabling | Security | Security | Offshore - Security Team member | US | Consulting Services | Cyber | Enterprise Security | US | Package and Technology Enablement | Package Configuration and Integration Solutions | L45 - Delivery Senior Consultant | Security-Security | Cybersecurity Consultant-Senior-US-Technology | Security - Cybersecurity Consultant | 348705 | 0 | 1305 | 1845 | Cybersecurity Consultant - Senior | 6-9 years | Onshore | Technology | Cybersecurity Consultant | Senior | 216.2595 | 189 | [79 empty] | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 |  |  | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | [22 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 90 | 180 | 180 | 180 | 180 | 180 | 180 | 135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Enabling | Security | Security | Cyber Delivery Manager | US | Consulting Services | Cyber | Enterprise Security | US | Package and Technology Enablement | Package Configuration and Integration Solutions | L55 - Delivery Manager | Security-Security | Cyber Security -Manager-US-Consulting | Security - Cyber Security | 126000 | 126000 | 0 | 400 | Cyber Security - Manager | 5-7 years | Onshore | Consulting | Cyber Security | Manager | 163.68 | 315 | [28 empty] | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | [106 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[15 empty] | 0 | 0 |  | 0 | 0 | 0 | --- |  |  |  | 139.9117 | [145 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Enabling | OCM | OCM | OCM Executive | US | Consulting Services | Human Capital | Organization, Workforce, & Change | US | Strategy, Growth, and Transformation | Enterprise Strategy and Growth | LMD - Managing Director | OCM-OCM | Human Capital-Managing Director-US-Consulting | OCM - Human Capital | 42944 | 3904 | 29 | 88 | Human Capital - Managing Director | 10-15 years | Onshore | Consulting | Human Capital | Managing Director | 247.4985 | 488 | [30 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [22 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 2 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Enabling | OCM | OCM | OCM Delivery Senior Manager | US | Consulting Services | Human Capital | Organization, Workforce, & Change | US | Strategy, Growth, and Transformation | Enterprise Strategy and Growth | L65 - Senior Manager | OCM-OCM | Human Capital-Senior Manager-US-Consulting | OCM - Human Capital | 422906 | 32720 | 0 | 1034 | Human Capital - Senior Manager | 7-10 years | Onshore | Consulting | Human Capital | Senior Manager | 278 | 409 | [30 empty] | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 |  |  | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 |  |  | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | [22 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Enabling | OCM | OCM | Global OCM Lead | US | Consulting Services | Human Capital | Organization, Workforce, & Change | US | Strategy, Growth, and Transformation | Enterprise Strategy and Growth | L55 - Manager | OCM-OCM | Human Capital-Manager-US-Consulting | OCM - Human Capital | 1327040 | 120640 | #VALUE! | 3520 | Human Capital - Manager | 5-7 years | Onshore | Consulting | Human Capital | Manager | 0 | 377 | [30 empty] | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 |  |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 |  |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | [22 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 80 | 160 | 160 | 160 | 160 | 160 | 160 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Enabling | OCM | Training | Global Training Lead | US | Consulting Services | Human Capital | Organization, Workforce, & Change | US | Strategy, Growth, and Transformation | Enterprise Strategy and Growth | L45 - Senior Consultant | OCM-Training | Human Capital-Senior Consultant-US-Consulting | OCM - Human Capital | 396090 | 0 | #VALUE! | 1215 | Human Capital - Senior Consultant | 3-5 years | Onshore | Consulting | Human Capital | Senior Consultant | 403.692 | 326 | [60 empty] | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | [15 empty] | 45 | 45 | 45 | 45 | 45 | 45 |  |  | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | [40 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 90 | 180 | 180 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Enabling | OCM | OCM | Global Change & Comms Lead | US | Consulting Services | Human Capital | Organization, Workforce, & Change | US | Strategy, Growth, and Transformation | Enterprise Strategy and Growth | L45 - Senior Consultant | OCM-OCM | Human Capital-Senior Consultant-US-Consulting | OCM - Human Capital | 792180 | 0 | 855 | 2430 | Human Capital - Senior Consultant | 3-5 years | Onshore | Consulting | Human Capital | Senior Consultant | 381.9729 | 326 | [56 empty] | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 |  |  | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | [32 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 90 | 180 | 180 | 180 | 180 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Enabling | OCM | OCM | ADMX GDM Required (Mexico) | Mexico | Consulting Services | Human Capital | Organization, Workforce, & Change | Mexico | Strategy, Growth, and Transformation | Functional and Operational Strategy and Transformation | L55 - Manager | OCM-OCM | Human Capital-Manager-Mexico-Consulting | OCM - Human Capital | 41748 | 1704 | 126 | 294 | Human Capital - Manager | 9-12 years | Nearshore | Consulting | Human Capital | Manager | 359.5923 | 142 | [32 empty] | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 |  |  | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 2 | 2 | 2 | [24 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 10 | 20 | 20 | 20 | 20 | 20 | 14 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Enabling | OCM | OCM | Global Change Analytics & Change Support (Mexico) | Mexico | Consulting Services | Human Capital | Organization, Workforce, & Change | Mexico | Strategy, Growth, and Transformation | Change and Transformation Management | L45 - Senior Consultant | OCM-OCM | Human Capital-Senior Consultant-Mexico-Consulting | OCM - Human Capital | 302535 | 22410 | 1080 | 3645 | Human Capital - Senior Consultant | 6-9 years | Nearshore | Consulting | Human Capital | Senior Consultant | 325.8944 | 83 | [32 empty] | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 |  |  | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 |  |  | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | [27 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 90 | 180 | 180 | 180 | 180 | 180 | 90 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Enabling | OCM | OCM | Global Communications Support (Mexico) | Mexico | Consulting Services | Human Capital | Organization, Workforce, & Change | Mexico | Strategy, Growth, and Transformation | Change and Transformation Management | L45 - Senior Consultant | OCM-OCM | Human Capital-Senior Consultant-Mexico-Consulting | OCM - Human Capital | 168075 | 0 | 1215 | 2025 | Human Capital - Senior Consultant | 6-9 years | Nearshore | Consulting | Human Capital | Senior Consultant | 325.8944 | 83 | [73 empty] | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 |  |  | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | [24 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 90 | 180 | 180 | 180 | 180 | 180 | 180 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Enabling | OCM | OCM | Adoption Assistant - Developer | US | Consulting Services | Human Capital | Organization, Workforce, & Change | US | Strategy, Growth, and Transformation | Enterprise Strategy and Growth | L65 - Senior Manager | OCM-OCM | Human Capital-Senior Manager-US-Consulting | OCM - Human Capital | 5726 | 0 | 0 | 14 | Human Capital - Senior Manager | 7-10 years | Onshore | Consulting | Human Capital | Senior Manager | 140.718 | 409 | [62 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [68 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Enabling | OCM | OCM | Adoption Assistant - Developer | US | Consulting Services | Human Capital | Organization, Workforce, & Change | US | Strategy, Growth, and Transformation | Enterprise Strategy and Growth | L55 - Manager | OCM-OCM | Human Capital-Manager-US-Consulting | OCM - Human Capital | 27144 | 0 | #VALUE! | 72 | Human Capital - Manager | 5-7 years | Onshore | Consulting | Human Capital | Manager | 81.0079 | 377 | [64 empty] | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | [68 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
Enabling | OCM | OCM | Adoption Assistant - Developer | US | Consulting Services | Human Capital | Organization, Workforce, & Change | US | Strategy, Growth, and Transformation | Enterprise Strategy and Growth | L45 - Senior Consultant | OCM-OCM | Human Capital-Senior Consultant-US-Consulting | OCM - Human Capital | 46944 | 0 | 0 | 144 | Human Capital - Senior Consultant | 3-5 years | Onshore | Consulting | Human Capital | Senior Consultant | 83.1209 | 326 | [64 empty] | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | [68 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Enabling | OCM | OCM | Adoption Assistant - Developer | India | Consulting Services | Human Capital | Organization, Workforce, & Change | India | Strategy, Growth, and Transformation | Change and Transformation Management | L45 - Senior Consultant | OCM-OCM | Human Capital-Senior Consultant-India-Consulting | OCM - Human Capital | 14472 | 0 | 0 | 108 | Human Capital - Senior Consultant | 3-5 years | Offshore | Consulting | Human Capital | Senior Consultant | 384.9029 | 134 | [64 empty] | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | [68 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Enabling | OCM | Training | USI HC Oversight GDM (required) | India | Consulting Services | Human Capital | Organization, Workforce, & Change | India | Strategy, Growth, and Transformation | Functional and Operational Strategy and Transformation | L65 - Senior Manager | OCM-Training | Human Capital-Senior Manager-India-Consulting | OCM - Human Capital | 40964 | 0 | 81 | 196 | Human Capital - Senior Manager | 7-10 years | Offshore | Consulting | Human Capital | Senior Manager | 365.62 | 209 | [65 empty] | 2 | 2 | 2 | 2 | 2 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 |  |  | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 2 | 2 | 2 | [33 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 10 | 20 | 20 | 20 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Enabling | OCM | Training | Training Manager | India | Consulting Services | Human Capital | Organization, Workforce, & Change | India | Strategy, Growth, and Transformation | Change and Transformation Management | L55 - Manager | OCM-Training | Human Capital-Manager-India-Consulting | OCM - Human Capital | 318780 | 0 | 810 | 1980 | Human Capital - Manager | 5-7 years | Offshore | Consulting | Human Capital | Manager | 328.65 | 161 | [65 empty] | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 |  |  | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | [33 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 90 | 180 | 180 | 180 | 180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Enabling | OCM | Training | Training Workstream Lead | India | Consulting Services | Human Capital | Organization, Workforce, & Change | India | Strategy, Growth, and Transformation | Change and Transformation Management | L45 - Senior Consultant | OCM-Training | Human Capital-Senior Consultant-India-Consulting | OCM - Human Capital | 217080 | 0 | 675 | 1620 | Human Capital - Senior Consultant | 3-5 years | Offshore | Consulting | Human Capital | Senior Consultant | 63.6 | 134 | [70 empty] | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 |  |  | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | [36 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 90 | 180 | 180 | 180 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Enabling | OCM | Training | Training Developer | India | Consulting Services | Human Capital | Organization, Workforce, & Change | India | Strategy, Growth, and Transformation | Change and Transformation Management | L35 - Consultant | OCM-Training | Change Manager-Intermediate-India-Technology | OCM - Change Manager | 63000 | 0 | 630 | 1575 | Change Manager - Intermediate | 3-6 years | Offshore | Technology | Change Manager | Intermediate | 129.32 | 40 | [70 empty] | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 |  |  | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | [37 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 90 | 180 | 180 | 180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Enabling | OCM | Training | Training Developer | India | Consulting Services | Human Capital | Organization, Workforce, & Change | India | Strategy, Growth, and Transformation | Change and Transformation Management | L35 - Consultant | OCM-Training | Change Manager-Intermediate-India-Technology | OCM - Change Manager | 57600 | 0 | 630 | 1440 | Change Manager - Intermediate | 3-6 years | Offshore | Technology | Change Manager | Intermediate | 86.92 | 40 | [73 empty] | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 |  |  | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | [37 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 90 | 180 | 180 | 180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Enabling | OCM | Training | Training Developer | India | Consulting Services | Human Capital | Organization, Workforce, & Change | India | Strategy, Growth, and Transformation | Change and Transformation Management | L35 - Consultant | OCM-Training | Change Manager-Intermediate-India-Technology | OCM - Change Manager | 57600 | 0 | 630 | 1440 | Change Manager - Intermediate | 3-6 years | Offshore | Technology | Change Manager | Intermediate | 63.6 | 40 | [73 empty] | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 |  |  | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | [37 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 90 | 180 | 180 | 180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Enabling | OCM | Training | Training Developer | India | Consulting Services | Human Capital | Organization, Workforce, & Change | India | Strategy, Growth, and Transformation | Change and Transformation Management | L35 - Consultant | OCM-Training | Change Manager-Intermediate-India-Technology | OCM - Change Manager | 43200 | 0 | 450 | 1080 | Change Manager - Intermediate | 3-6 years | Offshore | Technology | Change Manager | Intermediate | 54.06 | 40 | [77 empty] | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 |  |  | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | [41 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 90 | 180 | 180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Enabling | OCM | Training | Training Developer | India | Consulting Services | Human Capital | Organization, Workforce, & Change | India | Strategy, Growth, and Transformation | Change and Transformation Management | L35 - Consultant | OCM-Training | Change Manager-Intermediate-India-Technology | OCM - Change Manager | 37800 | 0 | 315 | 945 | Change Manager - Intermediate | 3-6 years | Offshore | Technology | Change Manager | Intermediate | 54.06 | 40 | [77 empty] | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 |  |  | 45 | 45 | 45 | 45 | 45 | [44 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 90 | 180 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Enabling | OCM | Training | Training Developer | India | Consulting Services | Human Capital | Organization, Workforce, & Change | India | Strategy, Growth, and Transformation | Change and Transformation Management | L25 - Analyst | OCM-Training | Change Manager-Junior-India-Technology | OCM - Change Manager | 28800 | 0 | 90 | 720 | Change Manager - Junior | 0-3 years | Offshore | Technology | Change Manager | Junior | 54.06 | 40 | [77 empty] | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | [51 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 90 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Enabling | OCM | Training | Training Developer | India | Consulting Services | Human Capital | Organization, Workforce, & Change | India | Strategy, Growth, and Transformation | Change and Transformation Management | L25 - Analyst | OCM-Training | Change Manager-Junior-India-Technology | OCM - Change Manager | 28800 | 0 | 90 | 720 | Change Manager - Junior | 0-3 years | Offshore | Technology | Change Manager | Junior | 54.06 | 40 | [77 empty] | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | [51 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 90 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Enabling | OCM | Training | Training Developer | India | Consulting Services | Human Capital | Organization, Workforce, & Change | India | Strategy, Growth, and Transformation | Change and Transformation Management | L25 - Analyst | OCM-Training | Change Manager-Junior-India-Technology | OCM - Change Manager | 28800 | 0 | 90 | 720 | Change Manager - Junior | 0-3 years | Offshore | Technology | Change Manager | Junior | 54.06 | 40 | [77 empty] | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | [51 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 90 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Enabling | OCM | Training | Training Developer | India | Consulting Services | Human Capital | Organization, Workforce, & Change | India | Strategy, Growth, and Transformation | Enterprise Strategy and Growth | L25 - Analyst | OCM-Training | Change Manager-Junior-India-Technology | OCM - Change Manager | 0 | 0 | 0 | 0 | Change Manager - Junior | 0-3 years | Offshore | Technology | Change Manager | Junior | 43.46 | 40 | [144 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Enabling | OCM | Training | Training Developer | India | Consulting Services | Human Capital | Organization, Workforce, & Change | India | Strategy, Growth, and Transformation | Enterprise Strategy and Growth | L25 - Analyst | OCM-Training | Change Manager-Junior-India-Technology | OCM - Change Manager | 0 | 0 | 0 | 0 | Change Manager - Junior | 0-3 years | Offshore | Technology | Change Manager | Junior | 43.46 | 40 | [144 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Enabling | OCM | Training | Training Developer | India | Consulting Services | Human Capital | Organization, Workforce, & Change | India | Strategy, Growth, and Transformation | Enterprise Strategy and Growth | L25 - Analyst | OCM-Training | Change Manager-Junior-India-Technology | OCM - Change Manager | 0 | 0 | 0 | 0 | Change Manager - Junior | 0-3 years | Offshore | Technology | Change Manager | Junior | 43.46 | 40 | [144 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[15 empty] | 0 | 0 |  | 0 | 0 | 0 | --- |  |  |  | 0 | [145 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Enabling | Validation | Validation | Validation SME | US | Consulting Services | Regulatory Risk & Forensic | Enterprise Operations & Risk | US | Risk, Compliance, and Governance | Regulatory, Risk, and Compliance | LMD - Managing Director | Validation-Validation | Validation-Partner-US-Consulting | Validation - Validation | 3750 | 3750 | 0 | 5 | Validation - Partner | 15+ years | Onshore | Consulting | Validation | Partner | 0 | 750 | [30 empty] | 1 | 1 | 1 | 1 | 1 | [109 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Enabling | Validation | Validation | Validation Advisor / Lead | US | Consulting Services | Regulatory Risk & Forensic | Enterprise Operations & Risk | US | Risk, Compliance, and Governance | Regulatory, Risk, and Compliance | L65 - Senior Manager | Validation-Validation | Validation-Senior Manager-US-Consulting | Validation - Validation | 87992 | 87992 | 0 | 136 | Validation - Senior Manager | 7-10 years | Onshore | Consulting | Validation | Senior Manager | 0 | 647 | [30 empty] | 32 | 32 | 32 | 32 | 8 | [109 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
Enabling | Validation | Validation | Validation Lead Offshore | India | Consulting Services | Regulatory Risk & Forensic | Enterprise Operations & Risk | India | Risk, Compliance, and Governance | Regulatory, Risk, and Compliance | L55 - Manager | Validation-Validation | Validation-Manager-India-Consulting | Validation - Validation | 36225 | 36225 | #VALUE! | 225 | Validation - Manager | 9-12 years | Offshore | Consulting | Validation | Manager | 0 | 161 | [30 empty] | 45 | 45 | 45 | 45 | 45 | [109 empty] | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | #VALUE!
[18 empty] | 0 | [152 empty] | P8: 0; P9: 0; P10: 0; P11: 0; P12: 0; P13: 0; P1: 0; P2: 0; P3: 0; P4: 0; P5: 0; P6: 0; P7: 0; P8: 0; P9: 0; P10: 0
[15 empty] | 48437850 | 3311343 | #VALUE! | 0 | [152 empty] | P8: 0; P9: 0; P10: 0; P11: 0; P12: 0; P13: 0; P1: 0; P2: 0; P3: 0; P4: 0; P5: 0; P6: 0; P7: 0; P8: 0; P9: 0; P10: 0
0 | bar: P8 to P10
0
0
0
[18 empty] | 0 | [152 empty] | P8: 12110; P9: 18847; P10: 18577; P11: 17905; P12: 16324; P13: 15683; P1: 14684; P2: 9391; P3: 0; P4: 0; P5: 0; P6: 0; P7: 0; P8: 0; P9: 0; P10: 0 | #VALUE!
[18 empty] | 0 | [152 empty] | P8: 1597440.5191; P9: 2572410.7033; P10: 2520794.9883; P11: 2409202.4706; P12: 2196108.8661; P13: 2047958.571; P1: 1848159.8994; P2: 1153940.7909; P3: 0; P4: 0; P5: 0; P6: 0; P7: 0; P8: 0; P9: 0; P10: 0 | 16346016.8087
0
Rate Helper (do not delete) | Role | Role Experience | Years of Experience | Location | Rate | Type
ServiceNow Architect-Junior-India-Technology | ServiceNow Architect | Junior | 0-3 years | India | 37 | Technology
Agile Coach-Junior-US-Technology | Agile Coach | Junior | 0-3 years | US | 163 | Technology
Agile Coach-Intermediate-US-Technology | Agile Coach | Intermediate | 3-6 years | US | 207 | Technology
Agile Coach-Senior-US-Technology | Agile Coach | Senior | 6-9 years | US | 258 | Technology
Agile Coach-Lead-US-Technology | Agile Coach | Lead | 9-12 years | US | 282 | Technology
Agile Coach-Principal-US-Technology | Agile Coach | Principal | 12+ years | US | 316 | Technology
Application Architect-Junior-India-Technology | Application Architect | Junior | 0-3 years | India | 39 | Technology
Application Architect-Intermediate-India-Technology | Application Architect | Intermediate | 3-6 years | India | 44 | Technology
Application Architect-Senior-India-Technology | Application Architect | Senior | 6-9 years | India | 46 | Technology
Application Architect-Lead-India-Technology | Application Architect | Lead | 9-12 years | India | 53 | Technology
Application Architect-Principal-India-Technology | Application Architect | Principal | 12+ years | India | 61 | Technology
Application Developer-Intermediate-India-Technology | Application Developer | Intermediate | 3-6 years | India | 25 | Technology
Application Developer-Junior-India-Technology | Application Developer | Junior | 0-3 years | India | 22 | Technology
Application Developer-Senior-India-Technology | Application Developer | Senior | 6-9 years | India | 32 | Technology
Application Developer-Lead-India-Technology | Application Developer | Lead | 9-12 years | India | 37 | Technology
Application Developer-Principal-India-Technology | Application Developer | Principal | 12+ years | India | 45 | Technology
Artificial Intelligence Architect-Junior-India-Technology | Artificial Intelligence Architect | Junior | 0-3 years | India | 45 | Technology
Artificial Intelligence Architect-Senior-India-Technology | Artificial Intelligence Architect | Senior | 6-9 years | India | 52 | Technology
Artificial Intelligence Architect-Intermediate-India-Technology | Artificial Intelligence Architect | Intermediate | 3-6 years | India | 49 | Technology
Artificial Intelligence Architect-Lead-India-Technology | Artificial Intelligence Architect | Lead | 9-12 years | India | 62 | Technology
Artificial Intelligence Architect-Principal-India-Technology | Artificial Intelligence Architect | Principal | 12+ years | India | 75 | Technology
Artificial Intelligence Developer-Junior-India-Technology | Artificial Intelligence Developer | Junior | 0-3 years | India | 28 | Technology
Artificial Intelligence Developer-Senior-India-Technology | Artificial Intelligence Developer | Senior | 6-9 years | India | 39 | Technology
Artificial Intelligence Developer-Intermediate-India-Technology | Artificial Intelligence Developer | Intermediate | 3-6 years | India | 33 | Technology
Artificial Intelligence Developer-Lead-India-Technology | Artificial Intelligence Developer | Lead | 9-12 years | India | 49 | Technology
Artificial Intelligence Developer-Principal-India-Technology | Artificial Intelligence Developer | Principal | 12+ years | India | 59 | Technology
Business Analyst-Intermediate-India-Technology | Business Analyst | Intermediate | 3-6 years | India | 33 | Technology
Business Analyst-Junior-India-Technology | Business Analyst | Junior | 0-3 years | India | 29 | Technology
Business Analyst-Senior-India-Technology | Business Analyst | Senior | 6-9 years | India | 42 | Technology
Business Analyst-Lead-India-Technology | Business Analyst | Lead | 9-12 years | India | 52 | Technology
Business Analyst-Principal-India-Technology | Business Analyst | Principal | 12+ years | India | 60 | Technology
Business Architect-Intermediate-India-Technology | Business Architect | Intermediate | 3-6 years | India | 44 | Technology
Business Architect-Junior-India-Technology | Business Architect | Junior | 0-3 years | India | 31 | Technology
Business Architect-Lead-India-Technology | Business Architect | Lead | 9-12 years | India | 63 | Technology
Business Architect-Principal-India-Technology | Business Architect | Principal | 12+ years | India | 71 | Technology
Business Architect-Senior-India-Technology | Business Architect | Senior | 6-9 years | India | 52 | Technology
Business Consultant-Intermediate-India-Technology | Business Consultant | Intermediate | 3-6 years | India | 41 | Technology
Business Consultant-Junior-India-Technology | Business Consultant | Junior | 0-3 years | India | 33 | Technology
Business Consultant-Lead-India-Technology | Business Consultant | Lead | 9-12 years | India | 59 | Technology
Business Consultant-Principal-India-Technology | Business Consultant | Principal | 12+ years | India | 75 | Technology
Business Consultant-Senior-India-Technology | Business Consultant | Senior | 6-9 years | India | 49 | Technology
Change Manager-Intermediate-India-Technology | Change Manager | Intermediate | 3-6 years | India | 40 | Technology
Change Manager-Junior-India-Technology | Change Manager | Junior | 0-3 years | India | 40 | Technology
Change Manager-Lead-India-Technology | Change Manager | Lead | 9-12 years | India | 61 | Technology
Change Manager-Principal-India-Technology | Change Manager | Principal | 12+ years | India | 75 | Technology
Change Manager-Senior-India-Technology | Change Manager | Senior | 6-9 years | India | 51 | Technology
Cloud Architect-Intermediate-India-Technology | Cloud Architect | Intermediate | 3-6 years | India | 44 | Technology
Cloud Architect-Junior-India-Technology | Cloud Architect | Junior | 0-3 years | India | 33 | Technology
Cloud Architect-Lead-India-Technology | Cloud Architect | Lead | 9-12 years | India | 62 | Technology
Cloud Architect-Principal-India-Technology | Cloud Architect | Principal | 12+ years | India | 72 | Technology
Cloud Architect-Senior-India-Technology | Cloud Architect | Senior | 6-9 years | India | 52 | Technology
Cloud Engineer-Intermediate-India-Technology | Cloud Engineer | Intermediate | 3-6 years | India | 32 | Technology
Cloud Engineer-Junior-India-Technology | Cloud Engineer | Junior | 0-3 years | India | 28 | Technology
Cloud Engineer-Lead-India-Technology | Cloud Engineer | Lead | 9-12 years | India | 49 | Technology
Cloud Engineer-Principal-India-Technology | Cloud Engineer | Principal | 12+ years | India | 59 | Technology
Cloud Engineer-Senior-India-Technology | Cloud Engineer | Senior | 6-9 years | India | 39 | Technology
Container Engineer-Intermediate-India-Technology | Container Engineer | Intermediate | 3-6 years | India | 32 | Technology
Container Engineer-Junior-India-Technology | Container Engineer | Junior | 0-3 years | India | 26 | Technology
Container Engineer-Lead-India-Technology | Container Engineer | Lead | 9-12 years | India | 43 | Technology
Container Engineer-Principal-India-Technology | Container Engineer | Principal | 12+ years | India | 59 | Technology
Container Engineer-Senior-India-Technology | Container Engineer | Senior | 6-9 years | India | 38 | Technology
Cyber Security -Analyst-India-Consulting | Cyber Security | Analyst | 0-1 years | India | 76 | Consulting
Cyber Security -Consultant-India-Consulting | Cyber Security | Consultant | 1-3 years | India | 78 | Consulting
Cyber Security -Manager-India-Consulting | Cyber Security | Manager | 5-7 years | India | 127 | Consulting
Cyber Security -Managing Director-India-Consulting | Cyber Security | Managing Director | 10-15 years | India | 261 | Consulting
Cyber Security -Principal-India-Consulting | Cyber Security | Principal | 15+ years | India | 261 | Consulting
Cyber Security -Senior Consultant-India-Consulting | Cyber Security | Senior Consultant | 3-5 years | India | 104 | Consulting
Cyber Security -Senior Manager-India-Consulting | Cyber Security | Senior Manager | 7-10 years | India | 162 | Consulting
Cybersecurity Analyst-Intermediate-India-Technology | Cybersecurity Analyst | Intermediate | 3-6 years | India | 33 | Technology
Cybersecurity Analyst-Junior-India-Technology | Cybersecurity Analyst | Junior | 0-3 years | India | 29 | Technology
Cybersecurity Analyst-Lead-India-Technology | Cybersecurity Analyst | Lead | 9-12 years | India | 52 | Technology
Cybersecurity Analyst-Principal-India-Technology | Cybersecurity Analyst | Principal | 12+ years | India | 60 | Technology
Cybersecurity Analyst-Senior-India-Technology | Cybersecurity Analyst | Senior | 6-9 years | India | 43 | Technology
Cybersecurity Assurance Analyst-Intermediate-India-Technology | Cybersecurity Assurance Analyst | Intermediate | 3-6 years | India | 33 | Technology
Cybersecurity Assurance Analyst-Junior-India-Technology | Cybersecurity Assurance Analyst | Junior | 0-3 years | India | 29 | Technology
Cybersecurity Assurance Analyst-Lead-India-Technology | Cybersecurity Assurance Analyst | Lead | 9-12 years | India | 52 | Technology
Cybersecurity Assurance Analyst-Principal-India-Technology | Cybersecurity Assurance Analyst | Principal | 12+ years | India | 60 | Technology
Cybersecurity Assurance Analyst-Senior-India-Technology | Cybersecurity Assurance Analyst | Senior | 6-9 years | India | 43 | Technology
Cybersecurity Consultant-Intermediate-India-Technology | Cybersecurity Consultant | Intermediate | 3-6 years | India | 35 | Technology
Cybersecurity Consultant-Junior-India-Technology | Cybersecurity Consultant | Junior | 0-3 years | India | 31 | Technology
Cybersecurity Consultant-Lead-India-Technology | Cybersecurity Consultant | Lead | 9-12 years | India | 59 | Technology
Cybersecurity Consultant-Principal-India-Technology | Cybersecurity Consultant | Principal | 12+ years | India | 66 | Technology
Cybersecurity Consultant-Senior-India-Technology | Cybersecurity Consultant | Senior | 6-9 years | India | 49 | Technology
Data Analyst-Intermediate-India-Technology | Data Analyst | Intermediate | 3-6 years | India | 33 | Technology
Data Analyst-Junior-India-Technology | Data Analyst | Junior | 0-3 years | India | 29 | Technology
Data Analyst-Lead-India-Technology | Data Analyst | Lead | 9-12 years | India | 49 | Technology
Data Analyst-Principal-India-Technology | Data Analyst | Principal | 12+ years | India | 60 | Technology
Data Analyst-Senior-India-Technology | Data Analyst | Senior | 6-9 years | India | 41 | Technology
Data Architect-Intermediate-India-Technology | Data Architect | Intermediate | 3-6 years | India | 40 | Technology
Data Architect-Junior-India-Technology | Data Architect | Junior | 0-3 years | India | 34 | Technology
Data Architect-Lead-India-Technology | Data Architect | Lead | 9-12 years | India | 50 | Technology
Data Architect-Principal-India-Technology | Data Architect | Principal | 12+ years | India | 60 | Technology
Data Architect-Senior-India-Technology | Data Architect | Senior | 6-9 years | India | 44 | Technology
Data Engineer-Intermediate-India-Technology | Data Engineer | Intermediate | 3-6 years | India | 25 | Technology
Data Engineer-Junior-India-Technology | Data Engineer | Junior | 0-3 years | India | 22 | Technology
Data Engineer-Lead-India-Technology | Data Engineer | Lead | 9-12 years | India | 37 | Technology
Data Engineer-Principal-India-Technology | Data Engineer | Principal | 12+ years | India | 45 | Technology
Data Engineer-Senior-India-Technology | Data Engineer | Senior | 6-9 years | India | 32 | Technology
Data Integration Architect-Intermediate-India-Technology | Data Integration Architect | Intermediate | 3-6 years | India | 43 | Technology
Data Integration Architect-Junior-India-Technology | Data Integration Architect | Junior | 0-3 years | India | 35 | Technology
Data Integration Architect-Lead-India-Technology | Data Integration Architect | Lead | 9-12 years | India | 52 | Technology
Data Integration Architect-Principal-India-Technology | Data Integration Architect | Principal | 12+ years | India | 58 | Technology
Data Integration Architect-Senior-India-Technology | Data Integration Architect | Senior | 6-9 years | India | 49 | Technology
Data Science Developer-Intermediate-India-Technology | Data Science Developer | Intermediate | 3-6 years | India | 39 | Technology
Data Science Developer-Junior-India-Technology | Data Science Developer | Junior | 0-3 years | India | 32 | Technology
Data Science Developer-Lead-India-Technology | Data Science Developer | Lead | 9-12 years | India | 52 | Technology
Data Science Developer-Principal-India-Technology | Data Science Developer | Principal | 12+ years | India | 60 | Technology
Data Science Developer-Senior-India-Technology | Data Science Developer | Senior | 6-9 years | India | 43 | Technology
Data Visualization Engineer-Intermediate-India-Technology | Data Visualization Engineer | Intermediate | 3-6 years | India | 34 | Technology
Data Visualization Engineer-Junior-India-Technology | Data Visualization Engineer | Junior | 0-3 years | India | 31 | Technology
Data Visualization Engineer-Lead-India-Technology | Data Visualization Engineer | Lead | 9-12 years | India | 49 | Technology
Data Visualization Engineer-Principal-India-Technology | Data Visualization Engineer | Principal | 12+ years | India | 59 | Technology
Data Visualization Engineer-Senior-India-Technology | Data Visualization Engineer | Senior | 6-9 years | India | 39 | Technology
Data Warehouse / Business Intelligence Engineer-Intermediate-India-Technology | Data Warehouse / Business Intelligence Engineer | Intermediate | 3-6 years | India | 29 | Technology
Data Warehouse / Business Intelligence Engineer-Junior-India-Technology | Data Warehouse / Business Intelligence Engineer | Junior | 0-3 years | India | 25 | Technology
Data Warehouse / Business Intelligence Engineer-Lead-India-Technology | Data Warehouse / Business Intelligence Engineer | Lead | 9-12 years | India | 41 | Technology
Data Warehouse / Business Intelligence Engineer-Principal-India-Technology | Data Warehouse / Business Intelligence Engineer | Principal | 12+ years | India | 46 | Technology
Data Warehouse / Business Intelligence Engineer-Senior-India-Technology | Data Warehouse / Business Intelligence Engineer | Senior | 6-9 years | India | 34 | Technology
Database Administrator-Intermediate-India-Technology | Database Administrator | Intermediate | 3-6 years | India | 25 | Technology
Database Administrator-Junior-India-Technology | Database Administrator | Junior | 0-3 years | India | 22 | Technology
Database Administrator-Lead-India-Technology | Database Administrator | Lead | 9-12 years | India | 37 | Technology
Database Administrator-Principal-India-Technology | Database Administrator | Principal | 12+ years | India | 45 | Technology
Database Administrator-Senior-India-Technology | Database Administrator | Senior | 6-9 years | India | 32 | Technology
Deal Advisory / M&A-Analyst-India-Consulting | Deal Advisory / M&A | Analyst | 0-1 years | India | 170 | Consulting
Deal Advisory / M&A-Consultant-India-Consulting | Deal Advisory / M&A | Consultant | 1-3 years | India | 170 | Consulting
Deal Advisory / M&A-Manager-India-Consulting | Deal Advisory / M&A | Manager | 5-7 years | India | 365 | Consulting
Cyber Security -Managing Director-US-Consulting | Cyber Security | Managing Director | 10-15 years | US | 437 | Consulting
Deal Advisory / M&A-Principal-India-Consulting | Deal Advisory / M&A | Principal | 15+ years | India | 419 | Consulting
Deal Advisory / M&A-Senior Consultant-India-Consulting | Deal Advisory / M&A | Senior Consultant | 3-5 years | India | 280 | Consulting
Deal Advisory / M&A-Senior Manager-India-Consulting | Deal Advisory / M&A | Senior Manager | 7-10 years | India | 389 | Consulting
Delivery Manager-Intermediate-India-Technology | Delivery Manager | Intermediate | 3-6 years | India | 45 | Technology
Delivery Manager-Junior-India-Technology | Delivery Manager | Junior | 0-3 years | India | 42 | Technology
Delivery Manager-Lead-India-Technology | Delivery Manager | Lead | 9-12 years | India | 57 | Technology
Delivery Manager-Principal-India-Technology | Delivery Manager | Principal | 12+ years | India | 66 | Technology
Delivery Manager-Senior-India-Technology | Delivery Manager | Senior | 6-9 years | India | 49 | Technology
Desktop Engineer-Intermediate-India-Technology | Desktop Engineer | Intermediate | 3-6 years | India | 25 | Technology
Desktop Engineer-Junior-India-Technology | Desktop Engineer | Junior | 0-3 years | India | 21 | Technology
Desktop Engineer-Lead-India-Technology | Desktop Engineer | Lead | 9-12 years | India | 37 | Technology
Desktop Engineer-Principal-India-Technology | Desktop Engineer | Principal | 12+ years | India | 45 | Technology
Desktop Engineer-Senior-India-Technology | Desktop Engineer | Senior | 6-9 years | India | 32 | Technology
Developer/Coder-Intermediate-India-Technology | Developer/Coder | Intermediate | 3-6 years | India | 32 | Technology
Developer/Coder-Junior-India-Technology | Developer/Coder | Junior | 0-3 years | India | 25 | Technology
Developer/Coder-Lead-India-Technology | Developer/Coder | Lead | 9-12 years | India | 42 | Technology
Developer/Coder-Principal-India-Technology | Developer/Coder | Principal | 12+ years | India | 46 | Technology
Developer/Coder-Senior-India-Technology | Developer/Coder | Senior | 6-9 years | India | 37 | Technology
DevOps Engineer-Intermediate-India-Technology | DevOps Engineer | Intermediate | 3-6 years | India | 32 | Technology
DevOps Engineer-Junior-India-Technology | DevOps Engineer | Junior | 0-3 years | India | 26 | Technology
DevOps Engineer-Lead-India-Technology | DevOps Engineer | Lead | 9-12 years | India | 42 | Technology
DevOps Engineer-Principal-India-Technology | DevOps Engineer | Principal | 12+ years | India | 59 | Technology
DevOps Engineer-Senior-India-Technology | DevOps Engineer | Senior | 6-9 years | India | 38 | Technology
Enterprise Architect-Intermediate-India-Technology | Enterprise Architect | Intermediate | 3-6 years | India | 47 | Technology
Enterprise Architect-Junior-India-Technology | Enterprise Architect | Junior | 0-3 years | India | 45 | Technology
Enterprise Architect-Lead-India-Technology | Enterprise Architect | Lead | 9-12 years | India | 62 | Technology
Enterprise Architect-Principal-India-Technology | Enterprise Architect | Principal | 12+ years | India | 71 | Technology
Enterprise Architect-Senior-India-Technology | Enterprise Architect | Senior | 6-9 years | India | 52 | Technology
Functional Consultant-Intermediate-India-Technology | Functional Consultant | Intermediate | 3-6 years | India | 35 | Technology
Functional Consultant-Junior-India-Technology | Functional Consultant | Junior | 0-3 years | India | 31 | Technology
Functional Consultant-Lead-India-Technology | Functional Consultant | Lead | 9-12 years | India | 59 | Technology
Functional Consultant-Principal-India-Technology | Functional Consultant | Principal | 12+ years | India | 66 | Technology
Functional Consultant-Senior-India-Technology | Functional Consultant | Senior | 6-9 years | India | 48 | Technology
Human Capital-Analyst-India-Consulting | Human Capital | Analyst | 0-1 years | India | 106 | Consulting
Human Capital-Consultant-India-Consulting | Human Capital | Consultant | 1-3 years | India | 121 | Consulting
Human Capital-Manager-India-Consulting | Human Capital | Manager | 5-7 years | India | 161 | Consulting
Deal Advisory / M&A-Managing Director-India-Consulting | Deal Advisory / M&A | Managing Director | 10-15 years | India | 419 | Consulting
Human Capital-Principal-India-Consulting | Human Capital | Principal | 15+ years | India | 266 | Consulting
Human Capital-Senior Consultant-India-Consulting | Human Capital | Senior Consultant | 3-5 years | India | 134 | Consulting
Human Capital-Senior Manager-India-Consulting | Human Capital | Senior Manager | 7-10 years | India | 209 | Consulting
Infrastructure Consultant-Intermediate-India-Technology | Infrastructure Consultant | Intermediate | 3-6 years | India | 38 | Technology
Infrastructure Consultant-Junior-India-Technology | Infrastructure Consultant | Junior | 0-3 years | India | 35 | Technology
Infrastructure Consultant-Lead-India-Technology | Infrastructure Consultant | Lead | 9-12 years | India | 59 | Technology
Infrastructure Consultant-Principal-India-Technology | Infrastructure Consultant | Principal | 12+ years | India | 66 | Technology
Infrastructure Consultant-Senior-India-Technology | Infrastructure Consultant | Senior | 6-9 years | India | 52 | Technology
Infrastructure Project Manager-Intermediate-India-Technology | Infrastructure Project Manager | Intermediate | 3-6 years | India | 37 | Technology
Infrastructure Project Manager-Junior-India-Technology | Infrastructure Project Manager | Junior | 0-3 years | India | 32 | Technology
Infrastructure Project Manager-Lead-India-Technology | Infrastructure Project Manager | Lead | 9-12 years | India | 49 | Technology
Infrastructure Project Manager-Principal-India-Technology | Infrastructure Project Manager | Principal | 12+ years | India | 57 | Technology
Infrastructure Project Manager-Senior-India-Technology | Infrastructure Project Manager | Senior | 6-9 years | India | 42 | Technology
Integration Engineer-Intermediate-India-Technology | Integration Engineer | Intermediate | 3-6 years | India | 25 | Technology
Integration Engineer-Junior-India-Technology | Integration Engineer | Junior | 0-3 years | India | 22 | Technology
Integration Engineer-Lead-India-Technology | Integration Engineer | Lead | 9-12 years | India | 38 | Technology
Integration Engineer-Principal-India-Technology | Integration Engineer | Principal | 12+ years | India | 45 | Technology
Integration Engineer-Senior-India-Technology | Integration Engineer | Senior | 6-9 years | India | 32 | Technology
Integration Lead-Intermediate-India-Technology | Integration Lead | Intermediate | 3-6 years | India | 32 | Technology
Integration Lead-Junior-India-Technology | Integration Lead | Junior | 0-3 years | India | 26 | Technology
Integration Lead-Lead-India-Technology | Integration Lead | Lead | 9-12 years | India | 45 | Technology
Integration Lead-Principal-India-Technology | Integration Lead | Principal | 12+ years | India | 51 | Technology
Integration Lead-Senior-India-Technology | Integration Lead | Senior | 6-9 years | India | 39 | Technology
Kubernetes Engineer-Intermediate-India-Technology | Kubernetes Engineer | Intermediate | 3-6 years | India | 32 | Technology
Kubernetes Engineer-Junior-India-Technology | Kubernetes Engineer | Junior | 0-3 years | India | 26 | Technology
Kubernetes Engineer-Lead-India-Technology | Kubernetes Engineer | Lead | 9-12 years | India | 43 | Technology
Kubernetes Engineer-Principal-India-Technology | Kubernetes Engineer | Principal | 12+ years | India | 59 | Technology
Kubernetes Engineer-Senior-India-Technology | Kubernetes Engineer | Senior | 6-9 years | India | 38 | Technology
Network Architect-Intermediate-India-Technology | Network Architect | Intermediate | 3-6 years | India | 42 | Technology
Network Architect-Junior-India-Technology | Network Architect | Junior | 0-3 years | India | 31 | Technology
Network Architect-Lead-India-Technology | Network Architect | Lead | 9-12 years | India | 53 | Technology
Network Architect-Principal-India-Technology | Network Architect | Principal | 12+ years | India | 70 | Technology
Network Architect-Senior-India-Technology | Network Architect | Senior | 6-9 years | India | 49 | Technology
Network Engineer-Intermediate-India-Technology | Network Engineer | Intermediate | 3-6 years | India | 31 | Technology
Network Engineer-Junior-India-Technology | Network Engineer | Junior | 0-3 years | India | 21 | Technology
Network Engineer-Lead-India-Technology | Network Engineer | Lead | 9-12 years | India | 40 | Technology
Network Engineer-Principal-India-Technology | Network Engineer | Principal | 12+ years | India | 59 | Technology
Network Engineer-Senior-India-Technology | Network Engineer | Senior | 6-9 years | India | 37 | Technology
Program Director/ Industry Lead-Intermediate-India-Technology | Program Director/ Industry Lead | Intermediate | 3-6 years | India | 52 | Technology
Program Director/ Industry Lead-Junior-India-Technology | Program Director/ Industry Lead | Junior | 0-3 years | India | 46 | Technology
Program Director/ Industry Lead-Lead-India-Technology | Program Director/ Industry Lead | Lead | 9-12 years | India | 77 | Technology
Program Director/ Industry Lead-Principal-India-Technology | Program Director/ Industry Lead | Principal | 12+ years | India | 82 | Technology
Program Director/ Industry Lead-Senior-India-Technology | Program Director/ Industry Lead | Senior | 6-9 years | India | 65 | Technology
Program Manager-Intermediate-India-Technology | Program Manager | Intermediate | 3-6 years | India | 41 | Technology
Program Manager-Junior-India-Technology | Program Manager | Junior | 0-3 years | India | 40 | Technology
Program Manager-Lead-India-Technology | Program Manager | Lead | 9-12 years | India | 63 | Technology
Program Manager-Principal-India-Technology | Program Manager | Principal | 12+ years | India | 75 | Technology
Program Manager-Senior-India-Technology | Program Manager | Senior | 6-9 years | India | 56 | Technology
Project Manager-Intermediate-India-Technology | Project Manager | Intermediate | 3-6 years | India | 37 | Technology
Project Manager-Junior-India-Technology | Project Manager | Junior | 0-3 years | India | 30 | Technology
Project Manager-Lead-India-Technology | Project Manager | Lead | 9-12 years | India | 49 | Technology
Project Manager-Principal-India-Technology | Project Manager | Principal | 12+ years | India | 59 | Technology
Project Manager-Senior-India-Technology | Project Manager | Senior | 6-9 years | India | 42 | Technology
Scrum Master-Intermediate-India-Technology | Scrum Master | Intermediate | 3-6 years | India | 37 | Technology
Scrum Master-Junior-India-Technology | Scrum Master | Junior | 0-3 years | India | 30 | Technology
Scrum Master-Lead-India-Technology | Scrum Master | Lead | 9-12 years | India | 49 | Technology
Scrum Master-Principal-India-Technology | Scrum Master | Principal | 12+ years | India | 58 | Technology
Scrum Master-Senior-India-Technology | Scrum Master | Senior | 6-9 years | India | 42 | Technology
Security Architect-Intermediate-India-Technology | Security Architect | Intermediate | 3-6 years | India | 48 | Technology
Security Architect-Junior-India-Technology | Security Architect | Junior | 0-3 years | India | 45 | Technology
Security Architect-Lead-India-Technology | Security Architect | Lead | 9-12 years | India | 62 | Technology
Security Architect-Principal-India-Technology | Security Architect | Principal | 12+ years | India | 70 | Technology
Security Architect-Senior-India-Technology | Security Architect | Senior | 6-9 years | India | 52 | Technology
Security Engineer-Intermediate-India-Technology | Security Engineer | Intermediate | 3-6 years | India | 32 | Technology
Security Engineer-Junior-India-Technology | Security Engineer | Junior | 0-3 years | India | 28 | Technology
Security Engineer-Lead-India-Technology | Security Engineer | Lead | 9-12 years | India | 49 | Technology
Security Engineer-Principal-India-Technology | Security Engineer | Principal | 12+ years | India | 59 | Technology
Security Engineer-Senior-India-Technology | Security Engineer | Senior | 6-9 years | India | 39 | Technology
ServiceNow Architect-Intermediate-India-Technology | ServiceNow Architect | Intermediate | 3-6 years | India | 39 | Technology
ServiceNow Architect-Lead-India-Technology | ServiceNow Architect | Lead | 9-12 years | India | 50 | Technology
ServiceNow Architect-Principal-India-Technology | ServiceNow Architect | Principal | 12+ years | India | 60 | Technology
ServiceNow Architect-Senior-India-Technology | ServiceNow Architect | Senior | 6-9 years | India | 44 | Technology
Software Engineer-Intermediate-India-Technology | Software Engineer | Intermediate | 3-6 years | India | 25 | Technology
Software Engineer-Junior-India-Technology | Software Engineer | Junior | 0-3 years | India | 22 | Technology
Software Engineer-Lead-India-Technology | Software Engineer | Lead | 9-12 years | India | 37 | Technology
Software Engineer-Principal-India-Technology | Software Engineer | Principal | 12+ years | India | 45 | Technology
Software Engineer-Senior-India-Technology | Software Engineer | Senior | 6-9 years | India | 32 | Technology
Solution Architect-Intermediate-India-Technology | Solution Architect | Intermediate | 3-6 years | India | 44 | Technology
Solution Architect-Junior-India-Technology | Solution Architect | Junior | 0-3 years | India | 40 | Technology
Solution Architect-Lead-India-Technology | Solution Architect | Lead | 9-12 years | India | 62 | Technology
Solution Architect-Principal-India-Technology | Solution Architect | Principal | 12+ years | India | 70 | Technology
Solution Architect-Senior-India-Technology | Solution Architect | Senior | 6-9 years | India | 52 | Technology
Strategy-Analyst-India-Consulting | Strategy | Analyst | 0-1 years | India | 80 | Consulting
Strategy-Consultant-India-Consulting | Strategy | Consultant | 1-3 years | India | 122 | Consulting
Strategy-Manager-India-Consulting | Strategy | Manager | 5-7 years | India | 179 | Consulting
Deal Advisory / M&A-Managing Director-US-Consulting | Deal Advisory / M&A | Managing Director | 10-15 years | US | 730 | Consulting
Strategy-Principal-India-Consulting | Strategy | Principal | 15+ years | India | 391 | Consulting
Strategy-Senior Consultant-India-Consulting | Strategy | Senior Consultant | 3-5 years | India | 133 | Consulting
Strategy-Senior Manager-India-Consulting | Strategy | Senior Manager | 7-10 years | India | 226 | Consulting
System Administrator-Intermediate-India-Technology | System Administrator | Intermediate | 3-6 years | India | 25 | Technology
System Administrator-Junior-India-Technology | System Administrator | Junior | 0-3 years | India | 21 | Technology
System Administrator-Lead-India-Technology | System Administrator | Lead | 9-12 years | India | 35 | Technology
System Administrator-Principal-India-Technology | System Administrator | Principal | 12+ years | India | 39 | Technology
System Administrator-Senior-India-Technology | System Administrator | Senior | 6-9 years | India | 30 | Technology
Systems Engineer-Intermediate-India-Technology | Systems Engineer | Intermediate | 3-6 years | India | 25 | Technology
Systems Engineer-Junior-India-Technology | Systems Engineer | Junior | 0-3 years | India | 22 | Technology
Systems Engineer-Lead-India-Technology | Systems Engineer | Lead | 9-12 years | India | 37 | Technology
Systems Engineer-Principal-India-Technology | Systems Engineer | Principal | 12+ years | India | 45 | Technology
Systems Engineer-Senior-India-Technology | Systems Engineer | Senior | 6-9 years | India | 32 | Technology
Systems Implementation Consultant-Intermediate-India-Technology | Systems Implementation Consultant | Intermediate | 3-6 years | India | 35 | Technology
Systems Implementation Consultant-Junior-India-Technology | Systems Implementation Consultant | Junior | 0-3 years | India | 30 | Technology
Systems Implementation Consultant-Lead-India-Technology | Systems Implementation Consultant | Lead | 9-12 years | India | 59 | Technology
Systems Implementation Consultant-Principal-India-Technology | Systems Implementation Consultant | Principal | 12+ years | India | 66 | Technology
Systems Implementation Consultant-Senior-India-Technology | Systems Implementation Consultant | Senior | 6-9 years | India | 48 | Technology
Tech Consultant-Intermediate-India-Technology | Tech Consultant | Intermediate | 3-6 years | India | 33 | Technology
Tech Consultant-Junior-India-Technology | Tech Consultant | Junior | 0-3 years | India | 29 | Technology
Tech Consultant-Lead-India-Technology | Tech Consultant | Lead | 9-12 years | India | 52 | Technology
Tech Consultant-Principal-India-Technology | Tech Consultant | Principal | 12+ years | India | 60 | Technology
Tech Consultant-Senior-India-Technology | Tech Consultant | Senior | 6-9 years | India | 42 | Technology
Technical Analyst-Intermediate-India-Technology | Technical Analyst | Intermediate | 3-6 years | India | 28 | Technology
Technical Analyst-Junior-India-Technology | Technical Analyst | Junior | 0-3 years | India | 24 | Technology
Technical Analyst-Lead-India-Technology | Technical Analyst | Lead | 9-12 years | India | 41 | Technology
Technical Analyst-Principal-India-Technology | Technical Analyst | Principal | 12+ years | India | 47 | Technology
Technical Analyst-Senior-India-Technology | Technical Analyst | Senior | 6-9 years | India | 35 | Technology
Technical Architect-Intermediate-India-Technology | Technical Architect | Intermediate | 3-6 years | India | 40 | Technology
Technical Architect-Junior-India-Technology | Technical Architect | Junior | 0-3 years | India | 38 | Technology
Technical Architect-Lead-India-Technology | Technical Architect | Lead | 9-12 years | India | 50 | Technology
Technical Architect-Principal-India-Technology | Technical Architect | Principal | 12+ years | India | 60 | Technology
Technical Architect-Senior-India-Technology | Technical Architect | Senior | 6-9 years | India | 44 | Technology
Technical Consultant-Intermediate-India-Technology | Technical Consultant | Intermediate | 3-6 years | India | 33 | Technology
Technical Consultant-Junior-India-Technology | Technical Consultant | Junior | 0-3 years | India | 29 | Technology
Technical Consultant-Lead-India-Technology | Technical Consultant | Lead | 9-12 years | India | 49 | Technology
Technical Consultant-Principal-India-Technology | Technical Consultant | Principal | 12+ years | India | 60 | Technology
Technical Consultant-Senior-India-Technology | Technical Consultant | Senior | 6-9 years | India | 40 | Technology
Technical Writer-Intermediate-India-Technology | Technical Writer | Intermediate | 3-6 years | India | 25 | Technology
Technical Writer-Junior-India-Technology | Technical Writer | Junior | 0-3 years | India | 21 | Technology
Technical Writer-Lead-India-Technology | Technical Writer | Lead | 9-12 years | India | 36 | Technology
Technical Writer-Principal-India-Technology | Technical Writer | Principal | 12+ years | India | 39 | Technology
Technical Writer-Senior-India-Technology | Technical Writer | Senior | 6-9 years | India | 30 | Technology
Technical/Functional Team Lead-Intermediate-India-Technology | Technical/Functional Team Lead | Intermediate | 3-6 years | India | 33 | Technology
Technical/Functional Team Lead-Junior-India-Technology | Technical/Functional Team Lead | Junior | 0-3 years | India | 29 | Technology
Technical/Functional Team Lead-Lead-India-Technology | Technical/Functional Team Lead | Lead | 9-12 years | India | 52 | Technology
Technical/Functional Team Lead-Principal-India-Technology | Technical/Functional Team Lead | Principal | 12+ years | India | 60 | Technology
Technical/Functional Team Lead-Senior-India-Technology | Technical/Functional Team Lead | Senior | 6-9 years | India | 42 | Technology
Technology-Analyst-India-Consulting | Technology | Analyst | 0-1 years | India | 48 | Consulting
Technology-Consultant-India-Consulting | Technology | Consultant | 1-3 years | India | 60 | Consulting
Technology-Manager-India-Consulting | Technology | Manager | 5-7 years | India | 99 | Consulting
Human Capital-Managing Director-India-Consulting | Human Capital | Managing Director | 10-15 years | India | 266 | Consulting
Technology-Principal-India-Consulting | Technology | Principal | 15+ years | India | 180 | Consulting
Technology-Senior Consultant-India-Consulting | Technology | Senior Consultant | 3-5 years | India | 71 | Consulting
Technology-Senior Manager-India-Consulting | Technology | Senior Manager | 7-10 years | India | 134 | Consulting
Technology Analyst-Intermediate-India-Technology | Technology Analyst | Intermediate | 3-6 years | India | 28 | Technology
Technology Analyst-Junior-India-Technology | Technology Analyst | Junior | 0-3 years | India | 24 | Technology
Technology Analyst-Lead-India-Technology | Technology Analyst | Lead | 9-12 years | India | 40 | Technology
Technology Analyst-Principal-India-Technology | Technology Analyst | Principal | 12+ years | India | 47 | Technology
Technology Analyst-Senior-India-Technology | Technology Analyst | Senior | 6-9 years | India | 35 | Technology
Test Engineer-Intermediate-India-Technology | Test Engineer | Intermediate | 3-6 years | India | 24 | Technology
Test Engineer-Junior-India-Technology | Test Engineer | Junior | 0-3 years | India | 22 | Technology
Test Engineer-Lead-India-Technology | Test Engineer | Lead | 9-12 years | India | 34 | Technology
Test Engineer-Principal-India-Technology | Test Engineer | Principal | 12+ years | India | 38 | Technology
Test Engineer-Senior-India-Technology | Test Engineer | Senior | 6-9 years | India | 29 | Technology
UX Designer-Intermediate-India-Technology | UX Designer | Intermediate | 3-6 years | India | 39 | Technology
UX Designer-Junior-India-Technology | UX Designer | Junior | 0-3 years | India | 34 | Technology
UX Designer-Lead-India-Technology | UX Designer | Lead | 9-12 years | India | 58 | Technology
UX Designer-Principal-India-Technology | UX Designer | Principal | 12+ years | India | 75 | Technology
UX Designer-Senior-India-Technology | UX Designer | Senior | 6-9 years | India | 52 | Technology
Agile Coach-Junior-India-Technology | Agile Coach | Junior | 0-3 years | India | 40 | Technology
Agile Coach-Intermediate-India-Technology | Agile Coach | Intermediate | 3-6 years | India | 46 | Technology
Agile Coach-Senior-India-Technology | Agile Coach | Senior | 6-9 years | India | 51 | Technology
Agile Coach-Lead-India-Technology | Agile Coach | Lead | 9-12 years | India | 61 | Technology
Agile Coach-Principal-India-Technology | Agile Coach | Principal | 12+ years | India | 75 | Technology
Application Architect-Junior-US-Technology | Application Architect | Junior | 0-3 years | US | 166 | Technology
Application Architect-Intermediate-US-Technology | Application Architect | Intermediate | 3-6 years | US | 172 | Technology
Application Architect-Senior-US-Technology | Application Architect | Senior | 6-9 years | US | 195 | Technology
Application Architect-Lead-US-Technology | Application Architect | Lead | 9-12 years | US | 207 | Technology
Application Architect-Principal-US-Technology | Application Architect | Principal | 12+ years | US | 224 | Technology
Application Developer-Junior-US-Technology | Application Developer | Junior | 0-3 years | US | 109 | Technology
Application Developer-Intermediate-US-Technology | Application Developer | Intermediate | 3-6 years | US | 124 | Technology
Application Developer-Senior-US-Technology | Application Developer | Senior | 6-9 years | US | 138 | Technology
Application Developer-Lead-US-Technology | Application Developer | Lead | 9-12 years | US | 153 | Technology
Application Developer-Principal-US-Technology | Application Developer | Principal | 12+ years | US | 172 | Technology
Artificial Intelligence Architect-Junior-US-Technology | Artificial Intelligence Architect | Junior | 0-3 years | US | 189 | Technology
Artificial Intelligence Architect-Intermediate-US-Technology | Artificial Intelligence Architect | Intermediate | 3-6 years | US | 201 | Technology
Artificial Intelligence Architect-Senior-US-Technology | Artificial Intelligence Architect | Senior | 6-9 years | US | 235 | Technology
Artificial Intelligence Architect-Lead-US-Technology | Artificial Intelligence Architect | Lead | 9-12 years | US | 264 | Technology
Artificial Intelligence Architect-Principal-US-Technology | Artificial Intelligence Architect | Principal | 12+ years | US | 316 | Technology
Artificial Intelligence Developer-Junior-US-Technology | Artificial Intelligence Developer | Junior | 0-3 years | US | 126 | Technology
Artificial Intelligence Developer-Intermediate-US-Technology | Artificial Intelligence Developer | Intermediate | 3-6 years | US | 143 | Technology
Artificial Intelligence Developer-Senior-US-Technology | Artificial Intelligence Developer | Senior | 6-9 years | US | 172 | Technology
Artificial Intelligence Developer-Lead-US-Technology | Artificial Intelligence Developer | Lead | 9-12 years | US | 184 | Technology
Artificial Intelligence Developer-Principal-US-Technology | Artificial Intelligence Developer | Principal | 12+ years | US | 195 | Technology
Business Analyst-Junior-US-Technology | Business Analyst | Junior | 0-3 years | US | 120 | Technology
Business Analyst-Intermediate-US-Technology | Business Analyst | Intermediate | 3-6 years | US | 132 | Technology
Business Analyst-Senior-US-Technology | Business Analyst | Senior | 6-9 years | US | 166 | Technology
Business Analyst-Lead-US-Technology | Business Analyst | Lead | 9-12 years | US | 184 | Technology
Business Analyst-Principal-US-Technology | Business Analyst | Principal | 12+ years | US | 195 | Technology
Business Architect-Intermediate-US-Technology | Business Architect | Intermediate | 3-6 years | US | 189 | Technology
Business Architect-Junior-US-Technology | Business Architect | Junior | 0-3 years | US | 149 | Technology
Business Architect-Lead-US-Technology | Business Architect | Lead | 9-12 years | US | 264 | Technology
Business Architect-Principal-US-Technology | Business Architect | Principal | 12+ years | US | 321 | Technology
Business Architect-Senior-US-Technology | Business Architect | Senior | 6-9 years | US | 235 | Technology
Business Consultant-Intermediate-US-Technology | Business Consultant | Intermediate | 3-6 years | US | 212 | Technology
Business Consultant-Junior-US-Technology | Business Consultant | Junior | 0-3 years | US | 161 | Technology
Business Consultant-Lead-US-Technology | Business Consultant | Lead | 9-12 years | US | 281 | Technology
Business Consultant-Principal-US-Technology | Business Consultant | Principal | 12+ years | US | 339 | Technology
Business Consultant-Senior-US-Technology | Business Consultant | Senior | 6-9 years | US | 241 | Technology
Change Manager-Intermediate-US-Technology | Change Manager | Intermediate | 3-6 years | US | 207 | Technology
Change Manager-Junior-US-Technology | Change Manager | Junior | 0-3 years | US | 163 | Technology
Change Manager-Lead-US-Technology | Change Manager | Lead | 9-12 years | US | 281 | Technology
Change Manager-Principal-US-Technology | Change Manager | Principal | 12+ years | US | 316 | Technology
Change Manager-Senior-US-Technology | Change Manager | Senior | 6-9 years | US | 235 | Technology
Cloud Architect-Intermediate-US-Technology | Cloud Architect | Intermediate | 3-6 years | US | 189 | Technology
Cloud Architect-Junior-US-Technology | Cloud Architect | Junior | 0-3 years | US | 153 | Technology
Cloud Architect-Lead-US-Technology | Cloud Architect | Lead | 9-12 years | US | 258 | Technology
Cloud Architect-Principal-US-Technology | Cloud Architect | Principal | 12+ years | US | 316 | Technology
Cloud Architect-Senior-US-Technology | Cloud Architect | Senior | 6-9 years | US | 230 | Technology
Cloud Engineer-Intermediate-US-Technology | Cloud Engineer | Intermediate | 3-6 years | US | 126 | Technology
Cloud Engineer-Junior-US-Technology | Cloud Engineer | Junior | 0-3 years | US | 120 | Technology
Cloud Engineer-Lead-US-Technology | Cloud Engineer | Lead | 9-12 years | US | 166 | Technology
Cloud Engineer-Principal-US-Technology | Cloud Engineer | Principal | 12+ years | US | 187 | Technology
Cloud Engineer-Senior-US-Technology | Cloud Engineer | Senior | 6-9 years | US | 157 | Technology
Container Engineer-Intermediate-US-Technology | Container Engineer | Intermediate | 3-6 years | US | 120 | Technology
Container Engineer-Junior-US-Technology | Container Engineer | Junior | 0-3 years | US | 108 | Technology
Container Engineer-Lead-US-Technology | Container Engineer | Lead | 9-12 years | US | 149 | Technology
Container Engineer-Principal-US-Technology | Container Engineer | Principal | 12+ years | US | 189 | Technology
Container Engineer-Senior-US-Technology | Container Engineer | Senior | 6-9 years | US | 127 | Technology
Cyber Security -Analyst-US-Consulting | Cyber Security | Analyst | 0-1 years | US | 230 | Consulting
Cyber Security -Consultant-US-Consulting | Cyber Security | Consultant | 1-3 years | US | 236 | Consulting
Cyber Security -Manager-US-Consulting | Cyber Security | Manager | 5-7 years | US | 315 | Consulting
Human Capital-Managing Director-US-Consulting | Human Capital | Managing Director | 10-15 years | US | 488 | Consulting
Cyber Security -Principal-US-Consulting | Cyber Security | Principal | 15+ years | US | 437 | Consulting
Cyber Security -Senior Consultant-US-Consulting | Cyber Security | Senior Consultant | 3-5 years | US | 264 | Consulting
Cyber Security -Senior Manager-US-Consulting | Cyber Security | Senior Manager | 7-10 years | US | 367 | Consulting
Cybersecurity Analyst-Intermediate-US-Technology | Cybersecurity Analyst | Intermediate | 3-6 years | US | 132 | Technology
Cybersecurity Analyst-Junior-US-Technology | Cybersecurity Analyst | Junior | 0-3 years | US | 120 | Technology
Cybersecurity Analyst-Lead-US-Technology | Cybersecurity Analyst | Lead | 9-12 years | US | 180 | Technology
Cybersecurity Analyst-Principal-US-Technology | Cybersecurity Analyst | Principal | 12+ years | US | 189 | Technology
Cybersecurity Analyst-Senior-US-Technology | Cybersecurity Analyst | Senior | 6-9 years | US | 166 | Technology
Cybersecurity Assurance Analyst-Intermediate-US-Technology | Cybersecurity Assurance Analyst | Intermediate | 3-6 years | US | 132 | Technology
Cybersecurity Assurance Analyst-Junior-US-Technology | Cybersecurity Assurance Analyst | Junior | 0-3 years | US | 120 | Technology
Cybersecurity Assurance Analyst-Lead-US-Technology | Cybersecurity Assurance Analyst | Lead | 9-12 years | US | 180 | Technology
Cybersecurity Assurance Analyst-Principal-US-Technology | Cybersecurity Assurance Analyst | Principal | 12+ years | US | 189 | Technology
Cybersecurity Assurance Analyst-Senior-US-Technology | Cybersecurity Assurance Analyst | Senior | 6-9 years | US | 166 | Technology
Cybersecurity Consultant-Intermediate-US-Technology | Cybersecurity Consultant | Intermediate | 3-6 years | US | 149 | Technology
Cybersecurity Consultant-Junior-US-Technology | Cybersecurity Consultant | Junior | 0-3 years | US | 132 | Technology
Cybersecurity Consultant-Lead-US-Technology | Cybersecurity Consultant | Lead | 9-12 years | US | 218 | Technology
Cybersecurity Consultant-Principal-US-Technology | Cybersecurity Consultant | Principal | 12+ years | US | 264 | Technology
Cybersecurity Consultant-Senior-US-Technology | Cybersecurity Consultant | Senior | 6-9 years | US | 189 | Technology
Data Analyst-Intermediate-US-Technology | Data Analyst | Intermediate | 3-6 years | US | 126 | Technology
Data Analyst-Junior-US-Technology | Data Analyst | Junior | 0-3 years | US | 120 | Technology
Data Analyst-Lead-US-Technology | Data Analyst | Lead | 9-12 years | US | 172 | Technology
Data Analyst-Principal-US-Technology | Data Analyst | Principal | 12+ years | US | 189 | Technology
Data Analyst-Senior-US-Technology | Data Analyst | Senior | 6-9 years | US | 161 | Technology
Data Architect-Intermediate-US-Technology | Data Architect | Intermediate | 3-6 years | US | 184 | Technology
Data Architect-Junior-US-Technology | Data Architect | Junior | 0-3 years | US | 166 | Technology
Data Architect-Lead-US-Technology | Data Architect | Lead | 9-12 years | US | 201 | Technology
Data Architect-Principal-US-Technology | Data Architect | Principal | 12+ years | US | 223 | Technology
Data Architect-Senior-US-Technology | Data Architect | Senior | 6-9 years | US | 192 | Technology
Data Engineer-Intermediate-US-Technology | Data Engineer | Intermediate | 3-6 years | US | 124 | Technology
Data Engineer-Junior-US-Technology | Data Engineer | Junior | 0-3 years | US | 108 | Technology
Data Engineer-Lead-US-Technology | Data Engineer | Lead | 9-12 years | US | 157 | Technology
Data Engineer-Principal-US-Technology | Data Engineer | Principal | 12+ years | US | 166 | Technology
Data Engineer-Senior-US-Technology | Data Engineer | Senior | 6-9 years | US | 148 | Technology
Data Integration Architect-Intermediate-US-Technology | Data Integration Architect | Intermediate | 3-6 years | US | 172 | Technology
Data Integration Architect-Junior-US-Technology | Data Integration Architect | Junior | 0-3 years | US | 166 | Technology
Data Integration Architect-Lead-US-Technology | Data Integration Architect | Lead | 9-12 years | US | 207 | Technology
Data Integration Architect-Principal-US-Technology | Data Integration Architect | Principal | 12+ years | US | 230 | Technology
Data Integration Architect-Senior-US-Technology | Data Integration Architect | Senior | 6-9 years | US | 195 | Technology
Data Science Developer-Intermediate-US-Technology | Data Science Developer | Intermediate | 3-6 years | US | 147 | Technology
Data Science Developer-Junior-US-Technology | Data Science Developer | Junior | 0-3 years | US | 124 | Technology
Data Science Developer-Lead-US-Technology | Data Science Developer | Lead | 9-12 years | US | 177 | Technology
Data Science Developer-Principal-US-Technology | Data Science Developer | Principal | 12+ years | US | 189 | Technology
Data Science Developer-Senior-US-Technology | Data Science Developer | Senior | 6-9 years | US | 170 | Technology
Data Visualization Engineer-Intermediate-US-Technology | Data Visualization Engineer | Intermediate | 3-6 years | US | 126 | Technology
Data Visualization Engineer-Junior-US-Technology | Data Visualization Engineer | Junior | 0-3 years | US | 122 | Technology
Data Visualization Engineer-Lead-US-Technology | Data Visualization Engineer | Lead | 9-12 years | US | 170 | Technology
Data Visualization Engineer-Principal-US-Technology | Data Visualization Engineer | Principal | 12+ years | US | 187 | Technology
Data Visualization Engineer-Senior-US-Technology | Data Visualization Engineer | Senior | 6-9 years | US | 155 | Technology
Data Warehouse / Business Intelligence Engineer-Intermediate-US-Technology | Data Warehouse / Business Intelligence Engineer | Intermediate | 3-6 years | US | 120 | Technology
Data Warehouse / Business Intelligence Engineer-Junior-US-Technology | Data Warehouse / Business Intelligence Engineer | Junior | 0-3 years | US | 108 | Technology
Data Warehouse / Business Intelligence Engineer-Lead-US-Technology | Data Warehouse / Business Intelligence Engineer | Lead | 9-12 years | US | 146 | Technology
Data Warehouse / Business Intelligence Engineer-Principal-US-Technology | Data Warehouse / Business Intelligence Engineer | Principal | 12+ years | US | 158 | Technology
Data Warehouse / Business Intelligence Engineer-Senior-US-Technology | Data Warehouse / Business Intelligence Engineer | Senior | 6-9 years | US | 142 | Technology
Database Administrator-Intermediate-US-Technology | Database Administrator | Intermediate | 3-6 years | US | 121 | Technology
Database Administrator-Junior-US-Technology | Database Administrator | Junior | 0-3 years | US | 106 | Technology
Database Administrator-Lead-US-Technology | Database Administrator | Lead | 9-12 years | US | 145 | Technology
Database Administrator-Principal-US-Technology | Database Administrator | Principal | 12+ years | US | 167 | Technology
Database Administrator-Senior-US-Technology | Database Administrator | Senior | 6-9 years | US | 133 | Technology
Deal Advisory / M&A-Analyst-US-Consulting | Deal Advisory / M&A | Analyst | 0-1 years | US | 273 | Consulting
Deal Advisory / M&A-Consultant-US-Consulting | Deal Advisory / M&A | Consultant | 1-3 years | US | 273 | Consulting
Deal Advisory / M&A-Manager-US-Consulting | Deal Advisory / M&A | Manager | 5-7 years | US | 541 | Consulting
Strategy-Managing Director-India-Consulting | Strategy | Managing Director | 10-15 years | India | 391 | Consulting
Deal Advisory / M&A-Principal-US-Consulting | Deal Advisory / M&A | Principal | 15+ years | US | 730 | Consulting
Deal Advisory / M&A-Senior Consultant-US-Consulting | Deal Advisory / M&A | Senior Consultant | 3-5 years | US | 404 | Consulting
Deal Advisory / M&A-Senior Manager-US-Consulting | Deal Advisory / M&A | Senior Manager | 7-10 years | US | 675 | Consulting
Delivery Manager-Intermediate-US-Technology | Delivery Manager | Intermediate | 3-6 years | US | 166 | Technology
Delivery Manager-Junior-US-Technology | Delivery Manager | Junior | 0-3 years | US | 150 | Technology
Delivery Manager-Lead-US-Technology | Delivery Manager | Lead | 9-12 years | US | 189 | Technology
Delivery Manager-Principal-US-Technology | Delivery Manager | Principal | 12+ years | US | 201 | Technology
Delivery Manager-Senior-US-Technology | Delivery Manager | Senior | 6-9 years | US | 178 | Technology
Desktop Engineer-Intermediate-US-Technology | Desktop Engineer | Intermediate | 3-6 years | US | 109 | Technology
Desktop Engineer-Junior-US-Technology | Desktop Engineer | Junior | 0-3 years | US | 86 | Technology
Desktop Engineer-Lead-US-Technology | Desktop Engineer | Lead | 9-12 years | US | 132 | Technology
Desktop Engineer-Principal-US-Technology | Desktop Engineer | Principal | 12+ years | US | 166 | Technology
Desktop Engineer-Senior-US-Technology | Desktop Engineer | Senior | 6-9 years | US | 120 | Technology
Developer/Coder-Intermediate-US-Technology | Developer/Coder | Intermediate | 3-6 years | US | 124 | Technology
Developer/Coder-Junior-US-Technology | Developer/Coder | Junior | 0-3 years | US | 108 | Technology
Developer/Coder-Lead-US-Technology | Developer/Coder | Lead | 9-12 years | US | 153 | Technology
Developer/Coder-Principal-US-Technology | Developer/Coder | Principal | 12+ years | US | 166 | Technology
Developer/Coder-Senior-US-Technology | Developer/Coder | Senior | 6-9 years | US | 132 | Technology
DevOps Engineer-Intermediate-US-Technology | DevOps Engineer | Intermediate | 3-6 years | US | 128 | Technology
DevOps Engineer-Junior-US-Technology | DevOps Engineer | Junior | 0-3 years | US | 108 | Technology
DevOps Engineer-Lead-US-Technology | DevOps Engineer | Lead | 9-12 years | US | 176 | Technology
DevOps Engineer-Principal-US-Technology | DevOps Engineer | Principal | 12+ years | US | 195 | Technology
DevOps Engineer-Senior-US-Technology | DevOps Engineer | Senior | 6-9 years | US | 151 | Technology
Enterprise Architect-Intermediate-US-Technology | Enterprise Architect | Intermediate | 3-6 years | US | 189 | Technology
Enterprise Architect-Junior-US-Technology | Enterprise Architect | Junior | 0-3 years | US | 153 | Technology
Enterprise Architect-Lead-US-Technology | Enterprise Architect | Lead | 9-12 years | US | 258 | Technology
Enterprise Architect-Principal-US-Technology | Enterprise Architect | Principal | 12+ years | US | 316 | Technology
Enterprise Architect-Senior-US-Technology | Enterprise Architect | Senior | 6-9 years | US | 227 | Technology
Functional Consultant-Intermediate-US-Technology | Functional Consultant | Intermediate | 3-6 years | US | 164 | Technology
Functional Consultant-Junior-US-Technology | Functional Consultant | Junior | 0-3 years | US | 143 | Technology
Functional Consultant-Lead-US-Technology | Functional Consultant | Lead | 9-12 years | US | 235 | Technology
Functional Consultant-Principal-US-Technology | Functional Consultant | Principal | 12+ years | US | 258 | Technology
Functional Consultant-Senior-US-Technology | Functional Consultant | Senior | 6-9 years | US | 204 | Technology
Human Capital-Analyst-US-Consulting | Human Capital | Analyst | 0-1 years | US | 248 | Consulting
Human Capital-Consultant-US-Consulting | Human Capital | Consultant | 1-3 years | US | 268 | Consulting
Human Capital-Manager-US-Consulting | Human Capital | Manager | 5-7 years | US | 377 | Consulting
Strategy-Managing Director-US-Consulting | Strategy | Managing Director | 10-15 years | US | 750 | Consulting
Human Capital-Principal-US-Consulting | Human Capital | Principal | 15+ years | US | 488 | Consulting
Human Capital-Senior Consultant-US-Consulting | Human Capital | Senior Consultant | 3-5 years | US | 326 | Consulting
Human Capital-Senior Manager-US-Consulting | Human Capital | Senior Manager | 7-10 years | US | 409 | Consulting
Infrastructure Consultant-Intermediate-US-Technology | Infrastructure Consultant | Intermediate | 3-6 years | US | 143 | Technology
Infrastructure Consultant-Junior-US-Technology | Infrastructure Consultant | Junior | 0-3 years | US | 132 | Technology
Infrastructure Consultant-Lead-US-Technology | Infrastructure Consultant | Lead | 9-12 years | US | 217 | Technology
Infrastructure Consultant-Principal-US-Technology | Infrastructure Consultant | Principal | 12+ years | US | 258 | Technology
Infrastructure Consultant-Senior-US-Technology | Infrastructure Consultant | Senior | 6-9 years | US | 189 | Technology
Infrastructure Project Manager-Intermediate-US-Technology | Infrastructure Project Manager | Intermediate | 3-6 years | US | 143 | Technology
Infrastructure Project Manager-Junior-US-Technology | Infrastructure Project Manager | Junior | 0-3 years | US | 120 | Technology
Infrastructure Project Manager-Lead-US-Technology | Infrastructure Project Manager | Lead | 9-12 years | US | 173 | Technology
Infrastructure Project Manager-Principal-US-Technology | Infrastructure Project Manager | Principal | 12+ years | US | 189 | Technology
Infrastructure Project Manager-Senior-US-Technology | Infrastructure Project Manager | Senior | 6-9 years | US | 166 | Technology
Integration Engineer-Intermediate-US-Technology | Integration Engineer | Intermediate | 3-6 years | US | 120 | Technology
Integration Engineer-Junior-US-Technology | Integration Engineer | Junior | 0-3 years | US | 108 | Technology
Integration Engineer-Lead-US-Technology | Integration Engineer | Lead | 9-12 years | US | 148 | Technology
Integration Engineer-Principal-US-Technology | Integration Engineer | Principal | 12+ years | US | 166 | Technology
Integration Engineer-Senior-US-Technology | Integration Engineer | Senior | 6-9 years | US | 140 | Technology
Integration Lead-Intermediate-US-Technology | Integration Lead | Intermediate | 3-6 years | US | 148 | Technology
Integration Lead-Junior-US-Technology | Integration Lead | Junior | 0-3 years | US | 139 | Technology
Integration Lead-Lead-US-Technology | Integration Lead | Lead | 9-12 years | US | 171 | Technology
Integration Lead-Principal-US-Technology | Integration Lead | Principal | 12+ years | US | 187 | Technology
Integration Lead-Senior-US-Technology | Integration Lead | Senior | 6-9 years | US | 154 | Technology
Kubernetes Engineer-Intermediate-US-Technology | Kubernetes Engineer | Intermediate | 3-6 years | US | 117 | Technology
Kubernetes Engineer-Junior-US-Technology | Kubernetes Engineer | Junior | 0-3 years | US | 106 | Technology
Kubernetes Engineer-Lead-US-Technology | Kubernetes Engineer | Lead | 9-12 years | US | 166 | Technology
Kubernetes Engineer-Principal-US-Technology | Kubernetes Engineer | Principal | 12+ years | US | 187 | Technology
Kubernetes Engineer-Senior-US-Technology | Kubernetes Engineer | Senior | 6-9 years | US | 140 | Technology
Network Architect-Intermediate-US-Technology | Network Architect | Intermediate | 3-6 years | US | 149 | Technology
Network Architect-Junior-US-Technology | Network Architect | Junior | 0-3 years | US | 127 | Technology
Network Architect-Lead-US-Technology | Network Architect | Lead | 9-12 years | US | 227 | Technology
Network Architect-Principal-US-Technology | Network Architect | Principal | 12+ years | US | 258 | Technology
Network Architect-Senior-US-Technology | Network Architect | Senior | 6-9 years | US | 203 | Technology
Network Engineer-Intermediate-US-Technology | Network Engineer | Intermediate | 3-6 years | US | 120 | Technology
Network Engineer-Junior-US-Technology | Network Engineer | Junior | 0-3 years | US | 115 | Technology
Network Engineer-Lead-US-Technology | Network Engineer | Lead | 9-12 years | US | 138 | Technology
Network Engineer-Principal-US-Technology | Network Engineer | Principal | 12+ years | US | 178 | Technology
Network Engineer-Senior-US-Technology | Network Engineer | Senior | 6-9 years | US | 124 | Technology
Program Director/ Industry Lead-Intermediate-US-Technology | Program Director/ Industry Lead | Intermediate | 3-6 years | US | 224 | Technology
Program Director/ Industry Lead-Junior-US-Technology | Program Director/ Industry Lead | Junior | 0-3 years | US | 163 | Technology
Program Director/ Industry Lead-Lead-US-Technology | Program Director/ Industry Lead | Lead | 9-12 years | US | 316 | Technology
Program Director/ Industry Lead-Principal-US-Technology | Program Director/ Industry Lead | Principal | 12+ years | US | 344 | Technology
Program Director/ Industry Lead-Senior-US-Technology | Program Director/ Industry Lead | Senior | 6-9 years | US | 287 | Technology
Program Manager-Intermediate-US-Technology | Program Manager | Intermediate | 3-6 years | US | 218 | Technology
Program Manager-Junior-US-Technology | Program Manager | Junior | 0-3 years | US | 163 | Technology
Program Manager-Lead-US-Technology | Program Manager | Lead | 9-12 years | US | 281 | Technology
Program Manager-Principal-US-Technology | Program Manager | Principal | 12+ years | US | 304 | Technology
Program Manager-Senior-US-Technology | Program Manager | Senior | 6-9 years | US | 247 | Technology
Project Manager-Intermediate-US-Technology | Project Manager | Intermediate | 3-6 years | US | 143 | Technology
Project Manager-Junior-US-Technology | Project Manager | Junior | 0-3 years | US | 120 | Technology
Project Manager-Lead-US-Technology | Project Manager | Lead | 9-12 years | US | 173 | Technology
Project Manager-Principal-US-Technology | Project Manager | Principal | 12+ years | US | 192 | Technology
Project Manager-Senior-US-Technology | Project Manager | Senior | 6-9 years | US | 166 | Technology
Scrum Master-Intermediate-US-Technology | Scrum Master | Intermediate | 3-6 years | US | 143 | Technology
Scrum Master-Junior-US-Technology | Scrum Master | Junior | 0-3 years | US | 120 | Technology
Scrum Master-Lead-US-Technology | Scrum Master | Lead | 9-12 years | US | 181 | Technology
Scrum Master-Principal-US-Technology | Scrum Master | Principal | 12+ years | US | 201 | Technology
Scrum Master-Senior-US-Technology | Scrum Master | Senior | 6-9 years | US | 166 | Technology
Security Architect-Intermediate-US-Technology | Security Architect | Intermediate | 3-6 years | US | 195 | Technology
Security Architect-Junior-US-Technology | Security Architect | Junior | 0-3 years | US | 189 | Technology
Security Architect-Lead-US-Technology | Security Architect | Lead | 9-12 years | US | 258 | Technology
Security Architect-Principal-US-Technology | Security Architect | Principal | 12+ years | US | 316 | Technology
Security Architect-Senior-US-Technology | Security Architect | Senior | 6-9 years | US | 227 | Technology
Security Engineer-Intermediate-US-Technology | Security Engineer | Intermediate | 3-6 years | US | 122 | Technology
Security Engineer-Junior-US-Technology | Security Engineer | Junior | 0-3 years | US | 118 | Technology
Security Engineer-Lead-US-Technology | Security Engineer | Lead | 9-12 years | US | 164 | Technology
Security Engineer-Principal-US-Technology | Security Engineer | Principal | 12+ years | US | 187 | Technology
Security Engineer-Senior-US-Technology | Security Engineer | Senior | 6-9 years | US | 157 | Technology
ServiceNow Architect-Intermediate-US-Technology | ServiceNow Architect | Intermediate | 3-6 years | US | 172 | Technology
ServiceNow Architect-Junior-US-Technology | ServiceNow Architect | Junior | 0-3 years | US | 153 | Technology
ServiceNow Architect-Lead-US-Technology | ServiceNow Architect | Lead | 9-12 years | US | 201 | Technology
ServiceNow Architect-Principal-US-Technology | ServiceNow Architect | Principal | 12+ years | US | 223 | Technology
ServiceNow Architect-Senior-US-Technology | ServiceNow Architect | Senior | 6-9 years | US | 192 | Technology
Software Engineer-Intermediate-US-Technology | Software Engineer | Intermediate | 3-6 years | US | 124 | Technology
Software Engineer-Junior-US-Technology | Software Engineer | Junior | 0-3 years | US | 108 | Technology
Software Engineer-Lead-US-Technology | Software Engineer | Lead | 9-12 years | US | 153 | Technology
Software Engineer-Principal-US-Technology | Software Engineer | Principal | 12+ years | US | 166 | Technology
Software Engineer-Senior-US-Technology | Software Engineer | Senior | 6-9 years | US | 142 | Technology
Solution Architect-Intermediate-US-Technology | Solution Architect | Intermediate | 3-6 years | US | 189 | Technology
Solution Architect-Junior-US-Technology | Solution Architect | Junior | 0-3 years | US | 153 | Technology
Solution Architect-Lead-US-Technology | Solution Architect | Lead | 9-12 years | US | 258 | Technology
Solution Architect-Principal-US-Technology | Solution Architect | Principal | 12+ years | US | 316 | Technology
Solution Architect-Senior-US-Technology | Solution Architect | Senior | 6-9 years | US | 227 | Technology
Strategy-Analyst-US-Consulting | Strategy | Analyst | 0-1 years | US | 351 | Consulting
Strategy-Consultant-US-Consulting | Strategy | Consultant | 1-3 years | US | 388 | Consulting
Strategy-Manager-US-Consulting | Strategy | Manager | 5-7 years | US | 568 | Consulting
Technology-Managing Director-India-Consulting | Technology | Managing Director | 10-15 years | India | 180 | Consulting
Strategy-Principal-US-Consulting | Strategy | Principal | 15+ years | US | 750 | Consulting
Strategy-Senior Consultant-US-Consulting | Strategy | Senior Consultant | 3-5 years | US | 471 | Consulting
Strategy-Senior Manager-US-Consulting | Strategy | Senior Manager | 7-10 years | US | 647 | Consulting
System Administrator-Intermediate-US-Technology | System Administrator | Intermediate | 3-6 years | US | 114 | Technology
System Administrator-Junior-US-Technology | System Administrator | Junior | 0-3 years | US | 104 | Technology
System Administrator-Lead-US-Technology | System Administrator | Lead | 9-12 years | US | 142 | Technology
System Administrator-Principal-US-Technology | System Administrator | Principal | 12+ years | US | 151 | Technology
System Administrator-Senior-US-Technology | System Administrator | Senior | 6-9 years | US | 125 | Technology
Systems Engineer-Intermediate-US-Technology | Systems Engineer | Intermediate | 3-6 years | US | 124 | Technology
Systems Engineer-Junior-US-Technology | Systems Engineer | Junior | 0-3 years | US | 115 | Technology
Systems Engineer-Lead-US-Technology | Systems Engineer | Lead | 9-12 years | US | 157 | Technology
Systems Engineer-Principal-US-Technology | Systems Engineer | Principal | 12+ years | US | 166 | Technology
Systems Engineer-Senior-US-Technology | Systems Engineer | Senior | 6-9 years | US | 148 | Technology
Systems Implementation Consultant-Intermediate-US-Technology | Systems Implementation Consultant | Intermediate | 3-6 years | US | 143 | Technology
Systems Implementation Consultant-Junior-US-Technology | Systems Implementation Consultant | Junior | 0-3 years | US | 132 | Technology
Systems Implementation Consultant-Lead-US-Technology | Systems Implementation Consultant | Lead | 9-12 years | US | 217 | Technology
Systems Implementation Consultant-Principal-US-Technology | Systems Implementation Consultant | Principal | 12+ years | US | 258 | Technology
Systems Implementation Consultant-Senior-US-Technology | Systems Implementation Consultant | Senior | 6-9 years | US | 189 | Technology
Tech Consultant-Intermediate-US-Technology | Tech Consultant | Intermediate | 3-6 years | US | 132 | Technology
Tech Consultant-Junior-US-Technology | Tech Consultant | Junior | 0-3 years | US | 120 | Technology
Tech Consultant-Lead-US-Technology | Tech Consultant | Lead | 9-12 years | US | 180 | Technology
Tech Consultant-Principal-US-Technology | Tech Consultant | Principal | 12+ years | US | 189 | Technology
Tech Consultant-Senior-US-Technology | Tech Consultant | Senior | 6-9 years | US | 166 | Technology
Technical Analyst-Intermediate-US-Technology | Technical Analyst | Intermediate | 3-6 years | US | 117 | Technology
Technical Analyst-Junior-US-Technology | Technical Analyst | Junior | 0-3 years | US | 106 | Technology
Technical Analyst-Lead-US-Technology | Technical Analyst | Lead | 9-12 years | US | 164 | Technology
Technical Analyst-Principal-US-Technology | Technical Analyst | Principal | 12+ years | US | 177 | Technology
Technical Analyst-Senior-US-Technology | Technical Analyst | Senior | 6-9 years | US | 148 | Technology
Technical Architect-Intermediate-US-Technology | Technical Architect | Intermediate | 3-6 years | US | 145 | Technology
Technical Architect-Junior-US-Technology | Technical Architect | Junior | 0-3 years | US | 125 | Technology
Technical Architect-Lead-US-Technology | Technical Architect | Lead | 9-12 years | US | 201 | Technology
Technical Architect-Principal-US-Technology | Technical Architect | Principal | 12+ years | US | 223 | Technology
Technical Architect-Senior-US-Technology | Technical Architect | Senior | 6-9 years | US | 166 | Technology
Technical Consultant-Intermediate-US-Technology | Technical Consultant | Intermediate | 3-6 years | US | 120 | Technology
Technical Consultant-Junior-US-Technology | Technical Consultant | Junior | 0-3 years | US | 115 | Technology
Technical Consultant-Lead-US-Technology | Technical Consultant | Lead | 9-12 years | US | 174 | Technology
Technical Consultant-Principal-US-Technology | Technical Consultant | Principal | 12+ years | US | 189 | Technology
Technical Consultant-Senior-US-Technology | Technical Consultant | Senior | 6-9 years | US | 157 | Technology
Technical Writer-Intermediate-US-Technology | Technical Writer | Intermediate | 3-6 years | US | 106 | Technology
Technical Writer-Junior-US-Technology | Technical Writer | Junior | 0-3 years | US | 86 | Technology
Technical Writer-Lead-US-Technology | Technical Writer | Lead | 9-12 years | US | 142 | Technology
Technical Writer-Principal-US-Technology | Technical Writer | Principal | 12+ years | US | 151 | Technology
Technical Writer-Senior-US-Technology | Technical Writer | Senior | 6-9 years | US | 132 | Technology
Technical/Functional Team Lead-Intermediate-US-Technology | Technical/Functional Team Lead | Intermediate | 3-6 years | US | 127 | Technology
Technical/Functional Team Lead-Junior-US-Technology | Technical/Functional Team Lead | Junior | 0-3 years | US | 120 | Technology
Technical/Functional Team Lead-Lead-US-Technology | Technical/Functional Team Lead | Lead | 9-12 years | US | 172 | Technology
Technical/Functional Team Lead-Principal-US-Technology | Technical/Functional Team Lead | Principal | 12+ years | US | 189 | Technology
Technical/Functional Team Lead-Senior-US-Technology | Technical/Functional Team Lead | Senior | 6-9 years | US | 157 | Technology
Technology-Analyst-US-Consulting | Technology | Analyst | 0-1 years | US | 189 | Consulting
Technology-Consultant-US-Consulting | Technology | Consultant | 1-3 years | US | 194 | Consulting
Technology-Manager-US-Consulting | Technology | Manager | 5-7 years | US | 306 | Consulting
Technology-Managing Director-US-Consulting | Technology | Managing Director | 10-15 years | US | 383 | Consulting
Technology-Principal-US-Consulting | Technology | Principal | 15+ years | US | 383 | Consulting
Technology-Senior Consultant-US-Consulting | Technology | Senior Consultant | 3-5 years | US | 260 | Consulting
Technology-Senior Manager-US-Consulting | Technology | Senior Manager | 7-10 years | US | 342 | Consulting
Technology Analyst-Intermediate-US-Technology | Technology Analyst | Intermediate | 3-6 years | US | 140 | Technology
Technology Analyst-Junior-US-Technology | Technology Analyst | Junior | 0-3 years | US | 120 | Technology
Technology Analyst-Lead-US-Technology | Technology Analyst | Lead | 9-12 years | US | 164 | Technology
Technology Analyst-Principal-US-Technology | Technology Analyst | Principal | 12+ years | US | 177 | Technology
Technology Analyst-Senior-US-Technology | Technology Analyst | Senior | 6-9 years | US | 154 | Technology
Test Engineer-Intermediate-US-Technology | Test Engineer | Intermediate | 3-6 years | US | 114 | Technology
Test Engineer-Junior-US-Technology | Test Engineer | Junior | 0-3 years | US | 102 | Technology
Test Engineer-Lead-US-Technology | Test Engineer | Lead | 9-12 years | US | 147 | Technology
Test Engineer-Principal-US-Technology | Test Engineer | Principal | 12+ years | US | 156 | Technology
Test Engineer-Senior-US-Technology | Test Engineer | Senior | 6-9 years | US | 134 | Technology
UX Designer-Intermediate-US-Technology | UX Designer | Intermediate | 3-6 years | US | 166 | Technology
UX Designer-Junior-US-Technology | UX Designer | Junior | 0-3 years | US | 147 | Technology
UX Designer-Lead-US-Technology | UX Designer | Lead | 9-12 years | US | 239 | Technology
UX Designer-Principal-US-Technology | UX Designer | Principal | 12+ years | US | 272 | Technology
UX Designer-Senior-US-Technology | UX Designer | Senior | 6-9 years | US | 207 | Technology
Validation-Partner-US-Consulting | Validation | Partner | 15+ years | US | 750 | Consulting
Validation-Senior Manager-US-Consulting | Validation | Senior Manager | 7-10 years | US | 647 | Consulting
Validation-Manager-India-Consulting | Validation | Manager | 9-12 years | India | 161 | Consulting
Validation-Senior Consultant-India-Consulting | Validation | Senior Consultant | 6-9 years | India | 121 | Consulting
Validation-Consultant-India-Consulting | Validation | Consultant | 3-6 years | India | 104 | Consulting
Validation-Analyst-India-Consulting | Validation | Analyst | 1-3 years | India | 48 | Consulting
Human Capital-Manager-Mexico-Consulting | Human Capital | Manager | 9-12 years | Mexico | 142 | Consulting
Human Capital-Senior Consultant-Mexico-Consulting | Human Capital | Senior Consultant | 6-9 years | Mexico | 83 | Consulting
Human Capital-Consultant-Mexico-Consulting | Human Capital | Consultant | 3-6 years | Mexico | 73 | Consulting
Tax Advisory-Partner-US-Tax | Tax Advisory | Partner | 12+ years | US | 625 | Tax
Tax Advisory-Managing Director-US-Tax | Tax Advisory | Managing Director | 12+ years | US | 575 | Tax
Tax Advisory-Senior Manager-US-Tax | Tax Advisory | Senior Manager | 9-12 years | US | 500 | Tax
Tax Advisory-Manager-US-Tax | Tax Advisory | Manager | 6-9 years | US | 365 | Tax
Tax Advisory-Senior Consultant-US-Tax | Tax Advisory | Senior Consultant | 3-6 years | US | 285 | Tax
Tax Advisory-Consultant-US-Tax | Tax Advisory | Consultant | 0-3 years | US | 185 | Tax
Tax Advisory-Principal-India-Tax | Tax Advisory | Principal | 12+ years | India | N/A | Tax
Tax Advisory-Managing Director-India-Tax | Tax Advisory | Managing Director | 12+ years | India | N/A | Tax
Tax Advisory-Senior Manager-India-Tax | Tax Advisory | Senior Manager | 9-12 years | India | 330 | Tax
Tax Advisory-Manager-India-Tax | Tax Advisory | Manager | 6-9 years | India | 240 | Tax
Tax Advisory-Senior Consultant-India-Tax | Tax Advisory | Senior Consultant | 3-6 years | India | 180 | Tax
Tax Advisory-Consultant-India-Tax | Tax Advisory | Consultant | 0-3 years | India | 120 | Tax

## Schedule
# | Invoice Description | Invoice Amount | Invoice Date | [10 empty] | Scoping and Planning Phase | [25 empty] | Build 1 |  |  |  | Build 2 |  |  |  | Build 3 |  |  |  | Build 4 |  |  |  | Build 5 |  |  |  | Build 6 | [6 empty] | SIT 1 | [8 empty] | SIT 2 | [10 empty] | UAT/Val Test | [8 empty] | Dry Run
1 | Scoping Kick off | 1500000 | 2026-10-01 | [20 empty] | Prep |  | Design 1 | [5 empty] | Design 2 |  |  |  | Design 3 |  |  |  | Design 4 |  |  |  | Design 5 | [19 empty] | MC1 | [8 empty] | MC2 | [10 empty] | MC3 | [8 empty] | CS | [8 empty] | FPC |  |  | HYC
2 | Scoping Phase - 2 | 1500000 | 2026-11-01
3 | Project Kick off | 2500000 | 2026-12-01
4 | Design Sprint 1 | 2500000 | 2027-01-01 | [10 empty] | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY29-P1 | FY29 | FY29 | FY29 | FY29 | FY29
5 | Design Sprint 2 | 2500000 | 2027-02-01 | [10 empty] | FY27-P4 | FY27-P4 | FY27-P5 | FY27-P5 | FY27-P5 | FY27-P5 | FY27-P6 | FY27-P6 | FY27-P6 | FY27-P6 | FY27-P7 | FY27-P7 | FY27-P7 | FY27-P7 | FY27-P8 | FY27-P8 | FY27-P8 | FY27-P8 | FY27-P9 | FY27-P9 | FY27-P9 | FY27-P9 | FY27-P10 | FY27-P10 | FY27-P10 | FY27-P10 | FY27-P11 | FY27-P11 | FY27-P11 | FY27-P11 | FY27-P12 | FY27-P12 | FY27-P12 | FY27-P12 | FY27-P13 | FY27-P13 | FY27-P13 | FY27-P13 | FY28-P1 | FY28-P1 | FY28-P1 | FY28-P1 | FY28-P2 | FY28-P2 | FY28-P2 | FY28-P2 | FY28-P3 | FY28-P3 | FY28-P3 | FY28-P3 | FY28-P4 | FY28-P4 | FY28-P4 | FY28-P4 | FY28-P5 | FY28-P5 | FY28-P5 | FY28-P5 | FY28-P6 | FY28-P6 | FY28-P6 | FY28-P6 | FY28-P7 | FY28-P7 | FY28-P7 | FY28-P7 | FY28-P8 | FY28-P8 | FY28-P8 | FY28-P8 | FY28-P9 | FY28-P9 | FY28-P9 | FY28-P9 | FY28-P10 | FY28-P10 | FY28-P10 | FY28-P10 | FY28-P11 | FY28-P11 | FY28-P11 | FY28-P11 | FY28-P12 | FY28-P12 | FY28-P12 | FY28-P12 | FY28-P13 | FY28-P13 | FY28-P13 | FY28-P13 | FY29-P1 | FY29-P1 | FY29-P1 | FY29-P1 | FY29-P2 | FY29-P2
6 | Design Sprint 3 | 2500000 | 2027-03-01 | time axis 2026-09-07 to 2028-07-03
7 | Design Sprint 4 | 2500000 | 2027-04-01
8 | Design Sprint 5 | 2500000 | 2027-05-01
9 | Build Sprint 1 | 2500000 | 2027-06-01
10 | Build Sprint 2 | 2500000 | 2027-07-01
11 | Build Sprint 3 | 2500000 | 2027-08-01
12 | Build Sprint 4 | 2500000 | 2027-09-01
13 | Build Sprint 5 | 2000000 | 2027-10-01
14 | Build Sprint 6 | 2000000 | 2027-11-01
15 | MC1 | 2000000 | 2027-12-01
16 | SIT1 | 2000000 | 2028-01-01
17 | MC2 | 2000000 | 2028-02-01
18 | SIT 2 | 2000000 | 2028-03-01
19 | MC3 | 1500000 | 2028-04-01
20 | UAT | 1500000 | 2028-05-01
21 | Dry Run Completed | 1500000 | 2028-06-01
22 | Final Cutover and Go-Live | 1500000 | 2028-07-01
23 | Hypercare Completed | 1500000 | 2028-07-07
| Total | 47500000
# | Invoice Description | Invoice Amount | Invoiced Amount after Holdback | Holdback Amount | Remaining Holdback | Cumulative Remaining Holdback | Penalty @5% | Penalty 7% | Penalty 10% | Holdback Release % | Invoice Date
1 | Scoping Kick off | 1500000 | 1350000 | 150000 | [6 empty] | 2026-10-01
2 | Scoping Phase - 2 | 1500000 | 1350000 | 150000 | [6 empty] | 2026-11-01
3 | Project Kick off | 2500000 | 2250000 | 250000 | [6 empty] | 2026-12-01
| Stage Gate 1 - Holdback Release 1 |  | 412500 | 550000 | 137500 | 137500 | 55000 | 137500 | 330000 | 75%
4 | Design Sprint 1 | 2500000 | 2250000 | 250000 | [6 empty] | 2027-01-01
5 | Design Sprint 2 | 2500000 | 2250000 | 250000 | [6 empty] | 2027-02-01
6 | Design Sprint 3 | 2500000 | 2250000 | 250000 | [6 empty] | 2027-03-01
7 | Design Sprint 4 | 2500000 | 2250000 | 250000 | [6 empty] | 2027-04-01
8 | Design Sprint 5 | 2500000 | 2250000 | 250000 | [6 empty] | 2027-05-01 | Holdback %
| Stage Gate 2 - Holdback Release 2 |  | 1062500 | 1250000 | 187500 | 325000 | 125000 | 312500 | 750000 | 85%
9 | Build Sprint 1 | 2500000 | 2250000 | 250000 | [6 empty] | 2027-06-01 | 10% | 50% of the holdback gets released at the Holdback release stage gates and 50% gets put in a purse for the last Holdback Release 5
10 | Build Sprint 2 | 2500000 | 2250000 | 250000 | [6 empty] | 2027-07-01
11 | Build Sprint 3 | 2500000 | 2250000 | 250000 | [6 empty] | 2027-08-01
12 | Build Sprint 4 | 2500000 | 2250000 | 250000 | [6 empty] | 2027-09-01
13 | Build Sprint 5 | 2000000 | 1800000 | 200000 | [6 empty] | 2027-10-01
14 | Build Sprint 6 | 2000000 | 1800000 | 200000 | [6 empty] | 2027-11-01 | Penalty on Holdback %
| Stage Gate 3 - Holdback Release 3 |  | 1190000 | 1400000 | 210000 | 535000 | 140000 | 350000 | 840000 | 85%
15 | MC1 | 2000000 | 1800000 | 200000 | [6 empty] | 2027-12-01 | 10% | 2 - 4 weeks late on milestone
16 | SIT1 | 2000000 | 1800000 | 200000 | [6 empty] | 2028-01-01 | 25% | 4 - 6 weeks late on milstone
17 | MC2 | 2000000 | 1800000 | 200000 | [6 empty] | 2028-02-01 | 60% | 6 - 8 weeks late on milestone
18 | SIT 2 | 2000000 | 1800000 | 200000 | [6 empty] | 2028-03-01 | 100% | >8 Weeks late on milestone
19 | MC3 | 1500000 | 1350000 | 150000 | [6 empty] | 2028-04-01
20 | UAT | 1500000 | 1350000 | 150000 | [6 empty] | 2028-05-01
21 | Dry Run Completed | 1500000 | 1350000 | 150000 | [6 empty] | 2028-06-01
| Stage Gate 4 - Holdback Relase 4 |  | 1062500 | 1250000 | 187500 | 722500 | 125000 | 312500 | 750000 | 85%
22 | Final Cutover and Go-Live | 1500000 | 1350000 | 150000 | [6 empty] | 2028-07-01
23 | Hypercare Completed | 1500000 | 1350000 | 150000 | [6 empty] | 2028-07-07
|  |  | 1022500 |  |  | Total penalty risk: | 445000 | 1112500 | 2670000
| Total | 47500000 | 47500000

## Rate Card
Rate Helper (do not delete) | Role | Role Experience | Years of Experience | Location | Rate | Type
ServiceNow Architect-Junior-India-Technology | ServiceNow Architect | Junior | 0-3 years | India | 37 | Technology
Agile Coach-Junior-US-Technology | Agile Coach | Junior | 0-3 years | US | 163 | Technology
Agile Coach-Intermediate-US-Technology | Agile Coach | Intermediate | 3-6 years | US | 207 | Technology
Agile Coach-Senior-US-Technology | Agile Coach | Senior | 6-9 years | US | 258 | Technology
Agile Coach-Lead-US-Technology | Agile Coach | Lead | 9-12 years | US | 282 | Technology
Agile Coach-Principal-US-Technology | Agile Coach | Principal | 12+ years | US | 316 | Technology
Application Architect-Junior-India-Technology | Application Architect | Junior | 0-3 years | India | 39 | Technology
Application Architect-Intermediate-India-Technology | Application Architect | Intermediate | 3-6 years | India | 44 | Technology
Application Architect-Senior-India-Technology | Application Architect | Senior | 6-9 years | India | 46 | Technology
Application Architect-Lead-India-Technology | Application Architect | Lead | 9-12 years | India | 53 | Technology
Application Architect-Principal-India-Technology | Application Architect | Principal | 12+ years | India | 61 | Technology
Application Developer-Intermediate-India-Technology | Application Developer | Intermediate | 3-6 years | India | 25 | Technology
Application Developer-Junior-India-Technology | Application Developer | Junior | 0-3 years | India | 22 | Technology
Application Developer-Senior-India-Technology | Application Developer | Senior | 6-9 years | India | 32 | Technology
Application Developer-Lead-India-Technology | Application Developer | Lead | 9-12 years | India | 37 | Technology
Application Developer-Principal-India-Technology | Application Developer | Principal | 12+ years | India | 45 | Technology
Artificial Intelligence Architect-Junior-India-Technology | Artificial Intelligence Architect | Junior | 0-3 years | India | 45 | Technology
Artificial Intelligence Architect-Senior-India-Technology | Artificial Intelligence Architect | Senior | 6-9 years | India | 52 | Technology
Artificial Intelligence Architect-Intermediate-India-Technology | Artificial Intelligence Architect | Intermediate | 3-6 years | India | 49 | Technology
Artificial Intelligence Architect-Lead-India-Technology | Artificial Intelligence Architect | Lead | 9-12 years | India | 62 | Technology
Artificial Intelligence Architect-Principal-India-Technology | Artificial Intelligence Architect | Principal | 12+ years | India | 75 | Technology
Artificial Intelligence Developer-Junior-India-Technology | Artificial Intelligence Developer | Junior | 0-3 years | India | 28 | Technology
Artificial Intelligence Developer-Senior-India-Technology | Artificial Intelligence Developer | Senior | 6-9 years | India | 39 | Technology
Artificial Intelligence Developer-Intermediate-India-Technology | Artificial Intelligence Developer | Intermediate | 3-6 years | India | 33 | Technology
Artificial Intelligence Developer-Lead-India-Technology | Artificial Intelligence Developer | Lead | 9-12 years | India | 49 | Technology
Artificial Intelligence Developer-Principal-India-Technology | Artificial Intelligence Developer | Principal | 12+ years | India | 59 | Technology
Business Analyst-Intermediate-India-Technology | Business Analyst | Intermediate | 3-6 years | India | 33 | Technology
Business Analyst-Junior-India-Technology | Business Analyst | Junior | 0-3 years | India | 29 | Technology
Business Analyst-Senior-India-Technology | Business Analyst | Senior | 6-9 years | India | 42 | Technology
Business Analyst-Lead-India-Technology | Business Analyst | Lead | 9-12 years | India | 52 | Technology
Business Analyst-Principal-India-Technology | Business Analyst | Principal | 12+ years | India | 60 | Technology
Business Architect-Intermediate-India-Technology | Business Architect | Intermediate | 3-6 years | India | 44 | Technology
Business Architect-Junior-India-Technology | Business Architect | Junior | 0-3 years | India | 31 | Technology
Business Architect-Lead-India-Technology | Business Architect | Lead | 9-12 years | India | 63 | Technology
Business Architect-Principal-India-Technology | Business Architect | Principal | 12+ years | India | 71 | Technology
Business Architect-Senior-India-Technology | Business Architect | Senior | 6-9 years | India | 52 | Technology
Business Consultant-Intermediate-India-Technology | Business Consultant | Intermediate | 3-6 years | India | 41 | Technology
Business Consultant-Junior-India-Technology | Business Consultant | Junior | 0-3 years | India | 33 | Technology
Business Consultant-Lead-India-Technology | Business Consultant | Lead | 9-12 years | India | 59 | Technology
Business Consultant-Principal-India-Technology | Business Consultant | Principal | 12+ years | India | 75 | Technology
Business Consultant-Senior-India-Technology | Business Consultant | Senior | 6-9 years | India | 49 | Technology
Change Manager-Intermediate-India-Technology | Change Manager | Intermediate | 3-6 years | India | 40 | Technology
Change Manager-Junior-India-Technology | Change Manager | Junior | 0-3 years | India | 40 | Technology
Change Manager-Lead-India-Technology | Change Manager | Lead | 9-12 years | India | 61 | Technology
Change Manager-Principal-India-Technology | Change Manager | Principal | 12+ years | India | 75 | Technology
Change Manager-Senior-India-Technology | Change Manager | Senior | 6-9 years | India | 51 | Technology
Cloud Architect-Intermediate-India-Technology | Cloud Architect | Intermediate | 3-6 years | India | 44 | Technology
Cloud Architect-Junior-India-Technology | Cloud Architect | Junior | 0-3 years | India | 33 | Technology
Cloud Architect-Lead-India-Technology | Cloud Architect | Lead | 9-12 years | India | 62 | Technology
Cloud Architect-Principal-India-Technology | Cloud Architect | Principal | 12+ years | India | 72 | Technology
Cloud Architect-Senior-India-Technology | Cloud Architect | Senior | 6-9 years | India | 52 | Technology
Cloud Engineer-Intermediate-India-Technology | Cloud Engineer | Intermediate | 3-6 years | India | 32 | Technology
Cloud Engineer-Junior-India-Technology | Cloud Engineer | Junior | 0-3 years | India | 28 | Technology
Cloud Engineer-Lead-India-Technology | Cloud Engineer | Lead | 9-12 years | India | 49 | Technology
Cloud Engineer-Principal-India-Technology | Cloud Engineer | Principal | 12+ years | India | 59 | Technology
Cloud Engineer-Senior-India-Technology | Cloud Engineer | Senior | 6-9 years | India | 39 | Technology
Container Engineer-Intermediate-India-Technology | Container Engineer | Intermediate | 3-6 years | India | 32 | Technology
Container Engineer-Junior-India-Technology | Container Engineer | Junior | 0-3 years | India | 26 | Technology
Container Engineer-Lead-India-Technology | Container Engineer | Lead | 9-12 years | India | 43 | Technology
Container Engineer-Principal-India-Technology | Container Engineer | Principal | 12+ years | India | 59 | Technology
Container Engineer-Senior-India-Technology | Container Engineer | Senior | 6-9 years | India | 38 | Technology
Cyber Security -Analyst-India-Consulting | Cyber Security | Analyst | 0-1 years | India | 76 | Consulting
Cyber Security -Consultant-India-Consulting | Cyber Security | Consultant | 1-3 years | India | 78 | Consulting
Cyber Security -Manager-India-Consulting | Cyber Security | Manager | 5-7 years | India | 127 | Consulting
Cyber Security -Managing Director-India-Consulting | Cyber Security | Managing Director | 10-15 years | India | 261 | Consulting
Cyber Security -Principal-India-Consulting | Cyber Security | Principal | 15+ years | India | 261 | Consulting
Cyber Security -Senior Consultant-India-Consulting | Cyber Security | Senior Consultant | 3-5 years | India | 104 | Consulting
Cyber Security -Senior Manager-India-Consulting | Cyber Security | Senior Manager | 7-10 years | India | 162 | Consulting
Cybersecurity Analyst-Intermediate-India-Technology | Cybersecurity Analyst | Intermediate | 3-6 years | India | 33 | Technology
Cybersecurity Analyst-Junior-India-Technology | Cybersecurity Analyst | Junior | 0-3 years | India | 29 | Technology
Cybersecurity Analyst-Lead-India-Technology | Cybersecurity Analyst | Lead | 9-12 years | India | 52 | Technology
Cybersecurity Analyst-Principal-India-Technology | Cybersecurity Analyst | Principal | 12+ years | India | 60 | Technology
Cybersecurity Analyst-Senior-India-Technology | Cybersecurity Analyst | Senior | 6-9 years | India | 43 | Technology
Cybersecurity Assurance Analyst-Intermediate-India-Technology | Cybersecurity Assurance Analyst | Intermediate | 3-6 years | India | 33 | Technology
Cybersecurity Assurance Analyst-Junior-India-Technology | Cybersecurity Assurance Analyst | Junior | 0-3 years | India | 29 | Technology
Cybersecurity Assurance Analyst-Lead-India-Technology | Cybersecurity Assurance Analyst | Lead | 9-12 years | India | 52 | Technology
Cybersecurity Assurance Analyst-Principal-India-Technology | Cybersecurity Assurance Analyst | Principal | 12+ years | India | 60 | Technology
Cybersecurity Assurance Analyst-Senior-India-Technology | Cybersecurity Assurance Analyst | Senior | 6-9 years | India | 43 | Technology
Cybersecurity Consultant-Intermediate-India-Technology | Cybersecurity Consultant | Intermediate | 3-6 years | India | 35 | Technology
Cybersecurity Consultant-Junior-India-Technology | Cybersecurity Consultant | Junior | 0-3 years | India | 31 | Technology
Cybersecurity Consultant-Lead-India-Technology | Cybersecurity Consultant | Lead | 9-12 years | India | 59 | Technology
Cybersecurity Consultant-Principal-India-Technology | Cybersecurity Consultant | Principal | 12+ years | India | 66 | Technology
Cybersecurity Consultant-Senior-India-Technology | Cybersecurity Consultant | Senior | 6-9 years | India | 49 | Technology
Data Analyst-Intermediate-India-Technology | Data Analyst | Intermediate | 3-6 years | India | 33 | Technology
Data Analyst-Junior-India-Technology | Data Analyst | Junior | 0-3 years | India | 29 | Technology
Data Analyst-Lead-India-Technology | Data Analyst | Lead | 9-12 years | India | 49 | Technology
Data Analyst-Principal-India-Technology | Data Analyst | Principal | 12+ years | India | 60 | Technology
Data Analyst-Senior-India-Technology | Data Analyst | Senior | 6-9 years | India | 41 | Technology
Data Architect-Intermediate-India-Technology | Data Architect | Intermediate | 3-6 years | India | 40 | Technology
Data Architect-Junior-India-Technology | Data Architect | Junior | 0-3 years | India | 34 | Technology
Data Architect-Lead-India-Technology | Data Architect | Lead | 9-12 years | India | 50 | Technology
Data Architect-Principal-India-Technology | Data Architect | Principal | 12+ years | India | 60 | Technology
Data Architect-Senior-India-Technology | Data Architect | Senior | 6-9 years | India | 44 | Technology
Data Engineer-Intermediate-India-Technology | Data Engineer | Intermediate | 3-6 years | India | 25 | Technology
Data Engineer-Junior-India-Technology | Data Engineer | Junior | 0-3 years | India | 22 | Technology
Data Engineer-Lead-India-Technology | Data Engineer | Lead | 9-12 years | India | 37 | Technology
Data Engineer-Principal-India-Technology | Data Engineer | Principal | 12+ years | India | 45 | Technology
Data Engineer-Senior-India-Technology | Data Engineer | Senior | 6-9 years | India | 32 | Technology
Data Integration Architect-Intermediate-India-Technology | Data Integration Architect | Intermediate | 3-6 years | India | 43 | Technology
Data Integration Architect-Junior-India-Technology | Data Integration Architect | Junior | 0-3 years | India | 35 | Technology
Data Integration Architect-Lead-India-Technology | Data Integration Architect | Lead | 9-12 years | India | 52 | Technology
Data Integration Architect-Principal-India-Technology | Data Integration Architect | Principal | 12+ years | India | 58 | Technology
Data Integration Architect-Senior-India-Technology | Data Integration Architect | Senior | 6-9 years | India | 49 | Technology
Data Science Developer-Intermediate-India-Technology | Data Science Developer | Intermediate | 3-6 years | India | 39 | Technology
Data Science Developer-Junior-India-Technology | Data Science Developer | Junior | 0-3 years | India | 32 | Technology
Data Science Developer-Lead-India-Technology | Data Science Developer | Lead | 9-12 years | India | 52 | Technology
Data Science Developer-Principal-India-Technology | Data Science Developer | Principal | 12+ years | India | 60 | Technology
Data Science Developer-Senior-India-Technology | Data Science Developer | Senior | 6-9 years | India | 43 | Technology
Data Visualization Engineer-Intermediate-India-Technology | Data Visualization Engineer | Intermediate | 3-6 years | India | 34 | Technology
Data Visualization Engineer-Junior-India-Technology | Data Visualization Engineer | Junior | 0-3 years | India | 31 | Technology
Data Visualization Engineer-Lead-India-Technology | Data Visualization Engineer | Lead | 9-12 years | India | 49 | Technology
Data Visualization Engineer-Principal-India-Technology | Data Visualization Engineer | Principal | 12+ years | India | 59 | Technology
Data Visualization Engineer-Senior-India-Technology | Data Visualization Engineer | Senior | 6-9 years | India | 39 | Technology
Data Warehouse / Business Intelligence Engineer-Intermediate-India-Technology | Data Warehouse / Business Intelligence Engineer | Intermediate | 3-6 years | India | 29 | Technology
Data Warehouse / Business Intelligence Engineer-Junior-India-Technology | Data Warehouse / Business Intelligence Engineer | Junior | 0-3 years | India | 25 | Technology
Data Warehouse / Business Intelligence Engineer-Lead-India-Technology | Data Warehouse / Business Intelligence Engineer | Lead | 9-12 years | India | 41 | Technology
Data Warehouse / Business Intelligence Engineer-Principal-India-Technology | Data Warehouse / Business Intelligence Engineer | Principal | 12+ years | India | 46 | Technology
Data Warehouse / Business Intelligence Engineer-Senior-India-Technology | Data Warehouse / Business Intelligence Engineer | Senior | 6-9 years | India | 34 | Technology
Database Administrator-Intermediate-India-Technology | Database Administrator | Intermediate | 3-6 years | India | 25 | Technology
Database Administrator-Junior-India-Technology | Database Administrator | Junior | 0-3 years | India | 22 | Technology
Database Administrator-Lead-India-Technology | Database Administrator | Lead | 9-12 years | India | 37 | Technology
Database Administrator-Principal-India-Technology | Database Administrator | Principal | 12+ years | India | 45 | Technology
Database Administrator-Senior-India-Technology | Database Administrator | Senior | 6-9 years | India | 32 | Technology
Deal Advisory / M&A-Analyst-India-Consulting | Deal Advisory / M&A | Analyst | 0-1 years | India | 170 | Consulting
Deal Advisory / M&A-Consultant-India-Consulting | Deal Advisory / M&A | Consultant | 1-3 years | India | 170 | Consulting
Deal Advisory / M&A-Manager-India-Consulting | Deal Advisory / M&A | Manager | 5-7 years | India | 365 | Consulting
Cyber Security -Managing Director-US-Consulting | Cyber Security | Managing Director | 10-15 years | US | 437 | Consulting
Deal Advisory / M&A-Principal-India-Consulting | Deal Advisory / M&A | Principal | 15+ years | India | 419 | Consulting
Deal Advisory / M&A-Senior Consultant-India-Consulting | Deal Advisory / M&A | Senior Consultant | 3-5 years | India | 280 | Consulting
Deal Advisory / M&A-Senior Manager-India-Consulting | Deal Advisory / M&A | Senior Manager | 7-10 years | India | 389 | Consulting
Delivery Manager-Intermediate-India-Technology | Delivery Manager | Intermediate | 3-6 years | India | 45 | Technology
Delivery Manager-Junior-India-Technology | Delivery Manager | Junior | 0-3 years | India | 42 | Technology
Delivery Manager-Lead-India-Technology | Delivery Manager | Lead | 9-12 years | India | 57 | Technology
Delivery Manager-Principal-India-Technology | Delivery Manager | Principal | 12+ years | India | 66 | Technology
Delivery Manager-Senior-India-Technology | Delivery Manager | Senior | 6-9 years | India | 49 | Technology
Desktop Engineer-Intermediate-India-Technology | Desktop Engineer | Intermediate | 3-6 years | India | 25 | Technology
Desktop Engineer-Junior-India-Technology | Desktop Engineer | Junior | 0-3 years | India | 21 | Technology
Desktop Engineer-Lead-India-Technology | Desktop Engineer | Lead | 9-12 years | India | 37 | Technology
Desktop Engineer-Principal-India-Technology | Desktop Engineer | Principal | 12+ years | India | 45 | Technology
Desktop Engineer-Senior-India-Technology | Desktop Engineer | Senior | 6-9 years | India | 32 | Technology
Developer/Coder-Intermediate-India-Technology | Developer/Coder | Intermediate | 3-6 years | India | 32 | Technology
Developer/Coder-Junior-India-Technology | Developer/Coder | Junior | 0-3 years | India | 25 | Technology
Developer/Coder-Lead-India-Technology | Developer/Coder | Lead | 9-12 years | India | 42 | Technology
Developer/Coder-Principal-India-Technology | Developer/Coder | Principal | 12+ years | India | 46 | Technology
Developer/Coder-Senior-India-Technology | Developer/Coder | Senior | 6-9 years | India | 37 | Technology
DevOps Engineer-Intermediate-India-Technology | DevOps Engineer | Intermediate | 3-6 years | India | 32 | Technology
DevOps Engineer-Junior-India-Technology | DevOps Engineer | Junior | 0-3 years | India | 26 | Technology
DevOps Engineer-Lead-India-Technology | DevOps Engineer | Lead | 9-12 years | India | 42 | Technology
DevOps Engineer-Principal-India-Technology | DevOps Engineer | Principal | 12+ years | India | 59 | Technology
DevOps Engineer-Senior-India-Technology | DevOps Engineer | Senior | 6-9 years | India | 38 | Technology
Enterprise Architect-Intermediate-India-Technology | Enterprise Architect | Intermediate | 3-6 years | India | 47 | Technology
Enterprise Architect-Junior-India-Technology | Enterprise Architect | Junior | 0-3 years | India | 45 | Technology
Enterprise Architect-Lead-India-Technology | Enterprise Architect | Lead | 9-12 years | India | 62 | Technology
Enterprise Architect-Principal-India-Technology | Enterprise Architect | Principal | 12+ years | India | 71 | Technology
Enterprise Architect-Senior-India-Technology | Enterprise Architect | Senior | 6-9 years | India | 52 | Technology
Functional Consultant-Intermediate-India-Technology | Functional Consultant | Intermediate | 3-6 years | India | 35 | Technology
Functional Consultant-Junior-India-Technology | Functional Consultant | Junior | 0-3 years | India | 31 | Technology
Functional Consultant-Lead-India-Technology | Functional Consultant | Lead | 9-12 years | India | 59 | Technology
Functional Consultant-Principal-India-Technology | Functional Consultant | Principal | 12+ years | India | 66 | Technology
Functional Consultant-Senior-India-Technology | Functional Consultant | Senior | 6-9 years | India | 48 | Technology
Human Capital-Analyst-India-Consulting | Human Capital | Analyst | 0-1 years | India | 106 | Consulting
Human Capital-Consultant-India-Consulting | Human Capital | Consultant | 1-3 years | India | 121 | Consulting
Human Capital-Manager-India-Consulting | Human Capital | Manager | 5-7 years | India | 161 | Consulting
Deal Advisory / M&A-Managing Director-India-Consulting | Deal Advisory / M&A | Managing Director | 10-15 years | India | 419 | Consulting
Human Capital-Principal-India-Consulting | Human Capital | Principal | 15+ years | India | 266 | Consulting
Human Capital-Senior Consultant-India-Consulting | Human Capital | Senior Consultant | 3-5 years | India | 134 | Consulting
Human Capital-Senior Manager-India-Consulting | Human Capital | Senior Manager | 7-10 years | India | 209 | Consulting
Infrastructure Consultant-Intermediate-India-Technology | Infrastructure Consultant | Intermediate | 3-6 years | India | 38 | Technology
Infrastructure Consultant-Junior-India-Technology | Infrastructure Consultant | Junior | 0-3 years | India | 35 | Technology
Infrastructure Consultant-Lead-India-Technology | Infrastructure Consultant | Lead | 9-12 years | India | 59 | Technology
Infrastructure Consultant-Principal-India-Technology | Infrastructure Consultant | Principal | 12+ years | India | 66 | Technology
Infrastructure Consultant-Senior-India-Technology | Infrastructure Consultant | Senior | 6-9 years | India | 52 | Technology
Infrastructure Project Manager-Intermediate-India-Technology | Infrastructure Project Manager | Intermediate | 3-6 years | India | 37 | Technology
Infrastructure Project Manager-Junior-India-Technology | Infrastructure Project Manager | Junior | 0-3 years | India | 32 | Technology
Infrastructure Project Manager-Lead-India-Technology | Infrastructure Project Manager | Lead | 9-12 years | India | 49 | Technology
Infrastructure Project Manager-Principal-India-Technology | Infrastructure Project Manager | Principal | 12+ years | India | 57 | Technology
Infrastructure Project Manager-Senior-India-Technology | Infrastructure Project Manager | Senior | 6-9 years | India | 42 | Technology
Integration Engineer-Intermediate-India-Technology | Integration Engineer | Intermediate | 3-6 years | India | 25 | Technology
Integration Engineer-Junior-India-Technology | Integration Engineer | Junior | 0-3 years | India | 22 | Technology
Integration Engineer-Lead-India-Technology | Integration Engineer | Lead | 9-12 years | India | 38 | Technology
Integration Engineer-Principal-India-Technology | Integration Engineer | Principal | 12+ years | India | 45 | Technology
Integration Engineer-Senior-India-Technology | Integration Engineer | Senior | 6-9 years | India | 32 | Technology
Integration Lead-Intermediate-India-Technology | Integration Lead | Intermediate | 3-6 years | India | 32 | Technology
Integration Lead-Junior-India-Technology | Integration Lead | Junior | 0-3 years | India | 26 | Technology
Integration Lead-Lead-India-Technology | Integration Lead | Lead | 9-12 years | India | 45 | Technology
Integration Lead-Principal-India-Technology | Integration Lead | Principal | 12+ years | India | 51 | Technology
Integration Lead-Senior-India-Technology | Integration Lead | Senior | 6-9 years | India | 39 | Technology
Kubernetes Engineer-Intermediate-India-Technology | Kubernetes Engineer | Intermediate | 3-6 years | India | 32 | Technology
Kubernetes Engineer-Junior-India-Technology | Kubernetes Engineer | Junior | 0-3 years | India | 26 | Technology
Kubernetes Engineer-Lead-India-Technology | Kubernetes Engineer | Lead | 9-12 years | India | 43 | Technology
Kubernetes Engineer-Principal-India-Technology | Kubernetes Engineer | Principal | 12+ years | India | 59 | Technology
Kubernetes Engineer-Senior-India-Technology | Kubernetes Engineer | Senior | 6-9 years | India | 38 | Technology
Network Architect-Intermediate-India-Technology | Network Architect | Intermediate | 3-6 years | India | 42 | Technology
Network Architect-Junior-India-Technology | Network Architect | Junior | 0-3 years | India | 31 | Technology
Network Architect-Lead-India-Technology | Network Architect | Lead | 9-12 years | India | 53 | Technology
Network Architect-Principal-India-Technology | Network Architect | Principal | 12+ years | India | 70 | Technology
Network Architect-Senior-India-Technology | Network Architect | Senior | 6-9 years | India | 49 | Technology
Network Engineer-Intermediate-India-Technology | Network Engineer | Intermediate | 3-6 years | India | 31 | Technology
Network Engineer-Junior-India-Technology | Network Engineer | Junior | 0-3 years | India | 21 | Technology
Network Engineer-Lead-India-Technology | Network Engineer | Lead | 9-12 years | India | 40 | Technology
Network Engineer-Principal-India-Technology | Network Engineer | Principal | 12+ years | India | 59 | Technology
Network Engineer-Senior-India-Technology | Network Engineer | Senior | 6-9 years | India | 37 | Technology
Program Director/ Industry Lead-Intermediate-India-Technology | Program Director/ Industry Lead | Intermediate | 3-6 years | India | 52 | Technology
Program Director/ Industry Lead-Junior-India-Technology | Program Director/ Industry Lead | Junior | 0-3 years | India | 46 | Technology
Program Director/ Industry Lead-Lead-India-Technology | Program Director/ Industry Lead | Lead | 9-12 years | India | 77 | Technology
Program Director/ Industry Lead-Principal-India-Technology | Program Director/ Industry Lead | Principal | 12+ years | India | 82 | Technology
Program Director/ Industry Lead-Senior-India-Technology | Program Director/ Industry Lead | Senior | 6-9 years | India | 65 | Technology
Program Manager-Intermediate-India-Technology | Program Manager | Intermediate | 3-6 years | India | 41 | Technology
Program Manager-Junior-India-Technology | Program Manager | Junior | 0-3 years | India | 40 | Technology
Program Manager-Lead-India-Technology | Program Manager | Lead | 9-12 years | India | 63 | Technology
Program Manager-Principal-India-Technology | Program Manager | Principal | 12+ years | India | 75 | Technology
Program Manager-Senior-India-Technology | Program Manager | Senior | 6-9 years | India | 56 | Technology
Project Manager-Intermediate-India-Technology | Project Manager | Intermediate | 3-6 years | India | 37 | Technology
Project Manager-Junior-India-Technology | Project Manager | Junior | 0-3 years | India | 30 | Technology
Project Manager-Lead-India-Technology | Project Manager | Lead | 9-12 years | India | 49 | Technology
Project Manager-Principal-India-Technology | Project Manager | Principal | 12+ years | India | 59 | Technology
Project Manager-Senior-India-Technology | Project Manager | Senior | 6-9 years | India | 42 | Technology
Scrum Master-Intermediate-India-Technology | Scrum Master | Intermediate | 3-6 years | India | 37 | Technology
Scrum Master-Junior-India-Technology | Scrum Master | Junior | 0-3 years | India | 30 | Technology
Scrum Master-Lead-India-Technology | Scrum Master | Lead | 9-12 years | India | 49 | Technology
Scrum Master-Principal-India-Technology | Scrum Master | Principal | 12+ years | India | 58 | Technology
Scrum Master-Senior-India-Technology | Scrum Master | Senior | 6-9 years | India | 42 | Technology
Security Architect-Intermediate-India-Technology | Security Architect | Intermediate | 3-6 years | India | 48 | Technology
Security Architect-Junior-India-Technology | Security Architect | Junior | 0-3 years | India | 45 | Technology
Security Architect-Lead-India-Technology | Security Architect | Lead | 9-12 years | India | 62 | Technology
Security Architect-Principal-India-Technology | Security Architect | Principal | 12+ years | India | 70 | Technology
Security Architect-Senior-India-Technology | Security Architect | Senior | 6-9 years | India | 52 | Technology
Security Engineer-Intermediate-India-Technology | Security Engineer | Intermediate | 3-6 years | India | 32 | Technology
Security Engineer-Junior-India-Technology | Security Engineer | Junior | 0-3 years | India | 28 | Technology
Security Engineer-Lead-India-Technology | Security Engineer | Lead | 9-12 years | India | 49 | Technology
Security Engineer-Principal-India-Technology | Security Engineer | Principal | 12+ years | India | 59 | Technology
Security Engineer-Senior-India-Technology | Security Engineer | Senior | 6-9 years | India | 39 | Technology
ServiceNow Architect-Intermediate-India-Technology | ServiceNow Architect | Intermediate | 3-6 years | India | 39 | Technology
ServiceNow Architect-Lead-India-Technology | ServiceNow Architect | Lead | 9-12 years | India | 50 | Technology
ServiceNow Architect-Principal-India-Technology | ServiceNow Architect | Principal | 12+ years | India | 60 | Technology
ServiceNow Architect-Senior-India-Technology | ServiceNow Architect | Senior | 6-9 years | India | 44 | Technology
Software Engineer-Intermediate-India-Technology | Software Engineer | Intermediate | 3-6 years | India | 25 | Technology
Software Engineer-Junior-India-Technology | Software Engineer | Junior | 0-3 years | India | 22 | Technology
Software Engineer-Lead-India-Technology | Software Engineer | Lead | 9-12 years | India | 37 | Technology
Software Engineer-Principal-India-Technology | Software Engineer | Principal | 12+ years | India | 45 | Technology
Software Engineer-Senior-India-Technology | Software Engineer | Senior | 6-9 years | India | 32 | Technology
Solution Architect-Intermediate-India-Technology | Solution Architect | Intermediate | 3-6 years | India | 44 | Technology
Solution Architect-Junior-India-Technology | Solution Architect | Junior | 0-3 years | India | 40 | Technology
Solution Architect-Lead-India-Technology | Solution Architect | Lead | 9-12 years | India | 62 | Technology
Solution Architect-Principal-India-Technology | Solution Architect | Principal | 12+ years | India | 70 | Technology
Solution Architect-Senior-India-Technology | Solution Architect | Senior | 6-9 years | India | 52 | Technology
Strategy-Analyst-India-Consulting | Strategy | Analyst | 0-1 years | India | 80 | Consulting
Strategy-Consultant-India-Consulting | Strategy | Consultant | 1-3 years | India | 122 | Consulting
Strategy-Manager-India-Consulting | Strategy | Manager | 5-7 years | India | 179 | Consulting
Deal Advisory / M&A-Managing Director-US-Consulting | Deal Advisory / M&A | Managing Director | 10-15 years | US | 730 | Consulting
Strategy-Principal-India-Consulting | Strategy | Principal | 15+ years | India | 391 | Consulting
Strategy-Senior Consultant-India-Consulting | Strategy | Senior Consultant | 3-5 years | India | 133 | Consulting
Strategy-Senior Manager-India-Consulting | Strategy | Senior Manager | 7-10 years | India | 226 | Consulting
System Administrator-Intermediate-India-Technology | System Administrator | Intermediate | 3-6 years | India | 25 | Technology
System Administrator-Junior-India-Technology | System Administrator | Junior | 0-3 years | India | 21 | Technology
System Administrator-Lead-India-Technology | System Administrator | Lead | 9-12 years | India | 35 | Technology
System Administrator-Principal-India-Technology | System Administrator | Principal | 12+ years | India | 39 | Technology
System Administrator-Senior-India-Technology | System Administrator | Senior | 6-9 years | India | 30 | Technology
Systems Engineer-Intermediate-India-Technology | Systems Engineer | Intermediate | 3-6 years | India | 25 | Technology
Systems Engineer-Junior-India-Technology | Systems Engineer | Junior | 0-3 years | India | 22 | Technology
Systems Engineer-Lead-India-Technology | Systems Engineer | Lead | 9-12 years | India | 37 | Technology
Systems Engineer-Principal-India-Technology | Systems Engineer | Principal | 12+ years | India | 45 | Technology
Systems Engineer-Senior-India-Technology | Systems Engineer | Senior | 6-9 years | India | 32 | Technology
Systems Implementation Consultant-Intermediate-India-Technology | Systems Implementation Consultant | Intermediate | 3-6 years | India | 35 | Technology
Systems Implementation Consultant-Junior-India-Technology | Systems Implementation Consultant | Junior | 0-3 years | India | 30 | Technology
Systems Implementation Consultant-Lead-India-Technology | Systems Implementation Consultant | Lead | 9-12 years | India | 59 | Technology
Systems Implementation Consultant-Principal-India-Technology | Systems Implementation Consultant | Principal | 12+ years | India | 66 | Technology
Systems Implementation Consultant-Senior-India-Technology | Systems Implementation Consultant | Senior | 6-9 years | India | 48 | Technology
Tech Consultant-Intermediate-India-Technology | Tech Consultant | Intermediate | 3-6 years | India | 33 | Technology
Tech Consultant-Junior-India-Technology | Tech Consultant | Junior | 0-3 years | India | 29 | Technology
Tech Consultant-Lead-India-Technology | Tech Consultant | Lead | 9-12 years | India | 52 | Technology
Tech Consultant-Principal-India-Technology | Tech Consultant | Principal | 12+ years | India | 60 | Technology
Tech Consultant-Senior-India-Technology | Tech Consultant | Senior | 6-9 years | India | 42 | Technology
Technical Analyst-Intermediate-India-Technology | Technical Analyst | Intermediate | 3-6 years | India | 28 | Technology
Technical Analyst-Junior-India-Technology | Technical Analyst | Junior | 0-3 years | India | 24 | Technology
Technical Analyst-Lead-India-Technology | Technical Analyst | Lead | 9-12 years | India | 41 | Technology
Technical Analyst-Principal-India-Technology | Technical Analyst | Principal | 12+ years | India | 47 | Technology
Technical Analyst-Senior-India-Technology | Technical Analyst | Senior | 6-9 years | India | 35 | Technology
Technical Architect-Intermediate-India-Technology | Technical Architect | Intermediate | 3-6 years | India | 40 | Technology
Technical Architect-Junior-India-Technology | Technical Architect | Junior | 0-3 years | India | 38 | Technology
Technical Architect-Lead-India-Technology | Technical Architect | Lead | 9-12 years | India | 50 | Technology
Technical Architect-Principal-India-Technology | Technical Architect | Principal | 12+ years | India | 60 | Technology
Technical Architect-Senior-India-Technology | Technical Architect | Senior | 6-9 years | India | 44 | Technology
Technical Consultant-Intermediate-India-Technology | Technical Consultant | Intermediate | 3-6 years | India | 33 | Technology
Technical Consultant-Junior-India-Technology | Technical Consultant | Junior | 0-3 years | India | 29 | Technology
Technical Consultant-Lead-India-Technology | Technical Consultant | Lead | 9-12 years | India | 49 | Technology
Technical Consultant-Principal-India-Technology | Technical Consultant | Principal | 12+ years | India | 60 | Technology
Technical Consultant-Senior-India-Technology | Technical Consultant | Senior | 6-9 years | India | 40 | Technology
Technical Writer-Intermediate-India-Technology | Technical Writer | Intermediate | 3-6 years | India | 25 | Technology
Technical Writer-Junior-India-Technology | Technical Writer | Junior | 0-3 years | India | 21 | Technology
Technical Writer-Lead-India-Technology | Technical Writer | Lead | 9-12 years | India | 36 | Technology
Technical Writer-Principal-India-Technology | Technical Writer | Principal | 12+ years | India | 39 | Technology
Technical Writer-Senior-India-Technology | Technical Writer | Senior | 6-9 years | India | 30 | Technology
Technical/Functional Team Lead-Intermediate-India-Technology | Technical/Functional Team Lead | Intermediate | 3-6 years | India | 33 | Technology
Technical/Functional Team Lead-Junior-India-Technology | Technical/Functional Team Lead | Junior | 0-3 years | India | 29 | Technology
Technical/Functional Team Lead-Lead-India-Technology | Technical/Functional Team Lead | Lead | 9-12 years | India | 52 | Technology
Technical/Functional Team Lead-Principal-India-Technology | Technical/Functional Team Lead | Principal | 12+ years | India | 60 | Technology
Technical/Functional Team Lead-Senior-India-Technology | Technical/Functional Team Lead | Senior | 6-9 years | India | 42 | Technology
Technology-Analyst-India-Consulting | Technology | Analyst | 0-1 years | India | 48 | Consulting
Technology-Consultant-India-Consulting | Technology | Consultant | 1-3 years | India | 60 | Consulting
Technology-Manager-India-Consulting | Technology | Manager | 5-7 years | India | 99 | Consulting
Human Capital-Managing Director-India-Consulting | Human Capital | Managing Director | 10-15 years | India | 266 | Consulting
Technology-Principal-India-Consulting | Technology | Principal | 15+ years | India | 180 | Consulting
Technology-Senior Consultant-India-Consulting | Technology | Senior Consultant | 3-5 years | India | 71 | Consulting
Technology-Senior Manager-India-Consulting | Technology | Senior Manager | 7-10 years | India | 134 | Consulting
Technology Analyst-Intermediate-India-Technology | Technology Analyst | Intermediate | 3-6 years | India | 28 | Technology
Technology Analyst-Junior-India-Technology | Technology Analyst | Junior | 0-3 years | India | 24 | Technology
Technology Analyst-Lead-India-Technology | Technology Analyst | Lead | 9-12 years | India | 40 | Technology
Technology Analyst-Principal-India-Technology | Technology Analyst | Principal | 12+ years | India | 47 | Technology
Technology Analyst-Senior-India-Technology | Technology Analyst | Senior | 6-9 years | India | 35 | Technology
Test Engineer-Intermediate-India-Technology | Test Engineer | Intermediate | 3-6 years | India | 24 | Technology
Test Engineer-Junior-India-Technology | Test Engineer | Junior | 0-3 years | India | 22 | Technology
Test Engineer-Lead-India-Technology | Test Engineer | Lead | 9-12 years | India | 34 | Technology
Test Engineer-Principal-India-Technology | Test Engineer | Principal | 12+ years | India | 38 | Technology
Test Engineer-Senior-India-Technology | Test Engineer | Senior | 6-9 years | India | 29 | Technology
UX Designer-Intermediate-India-Technology | UX Designer | Intermediate | 3-6 years | India | 39 | Technology
UX Designer-Junior-India-Technology | UX Designer | Junior | 0-3 years | India | 34 | Technology
UX Designer-Lead-India-Technology | UX Designer | Lead | 9-12 years | India | 58 | Technology
UX Designer-Principal-India-Technology | UX Designer | Principal | 12+ years | India | 75 | Technology
UX Designer-Senior-India-Technology | UX Designer | Senior | 6-9 years | India | 52 | Technology
Agile Coach-Junior-India-Technology | Agile Coach | Junior | 0-3 years | India | 40 | Technology
Agile Coach-Intermediate-India-Technology | Agile Coach | Intermediate | 3-6 years | India | 46 | Technology
Agile Coach-Senior-India-Technology | Agile Coach | Senior | 6-9 years | India | 51 | Technology
Agile Coach-Lead-India-Technology | Agile Coach | Lead | 9-12 years | India | 61 | Technology
Agile Coach-Principal-India-Technology | Agile Coach | Principal | 12+ years | India | 75 | Technology
Application Architect-Junior-US-Technology | Application Architect | Junior | 0-3 years | US | 166 | Technology
Application Architect-Intermediate-US-Technology | Application Architect | Intermediate | 3-6 years | US | 172 | Technology
Application Architect-Senior-US-Technology | Application Architect | Senior | 6-9 years | US | 195 | Technology
Application Architect-Lead-US-Technology | Application Architect | Lead | 9-12 years | US | 207 | Technology
Application Architect-Principal-US-Technology | Application Architect | Principal | 12+ years | US | 224 | Technology
Application Developer-Junior-US-Technology | Application Developer | Junior | 0-3 years | US | 109 | Technology
Application Developer-Intermediate-US-Technology | Application Developer | Intermediate | 3-6 years | US | 124 | Technology
Application Developer-Senior-US-Technology | Application Developer | Senior | 6-9 years | US | 138 | Technology
Application Developer-Lead-US-Technology | Application Developer | Lead | 9-12 years | US | 153 | Technology
Application Developer-Principal-US-Technology | Application Developer | Principal | 12+ years | US | 172 | Technology
Artificial Intelligence Architect-Junior-US-Technology | Artificial Intelligence Architect | Junior | 0-3 years | US | 189 | Technology
Artificial Intelligence Architect-Intermediate-US-Technology | Artificial Intelligence Architect | Intermediate | 3-6 years | US | 201 | Technology
Artificial Intelligence Architect-Senior-US-Technology | Artificial Intelligence Architect | Senior | 6-9 years | US | 235 | Technology
Artificial Intelligence Architect-Lead-US-Technology | Artificial Intelligence Architect | Lead | 9-12 years | US | 264 | Technology
Artificial Intelligence Architect-Principal-US-Technology | Artificial Intelligence Architect | Principal | 12+ years | US | 316 | Technology
Artificial Intelligence Developer-Junior-US-Technology | Artificial Intelligence Developer | Junior | 0-3 years | US | 126 | Technology
Artificial Intelligence Developer-Intermediate-US-Technology | Artificial Intelligence Developer | Intermediate | 3-6 years | US | 143 | Technology
Artificial Intelligence Developer-Senior-US-Technology | Artificial Intelligence Developer | Senior | 6-9 years | US | 172 | Technology
Artificial Intelligence Developer-Lead-US-Technology | Artificial Intelligence Developer | Lead | 9-12 years | US | 184 | Technology
Artificial Intelligence Developer-Principal-US-Technology | Artificial Intelligence Developer | Principal | 12+ years | US | 195 | Technology
Business Analyst-Junior-US-Technology | Business Analyst | Junior | 0-3 years | US | 120 | Technology
Business Analyst-Intermediate-US-Technology | Business Analyst | Intermediate | 3-6 years | US | 132 | Technology
Business Analyst-Senior-US-Technology | Business Analyst | Senior | 6-9 years | US | 166 | Technology
Business Analyst-Lead-US-Technology | Business Analyst | Lead | 9-12 years | US | 184 | Technology
Business Analyst-Principal-US-Technology | Business Analyst | Principal | 12+ years | US | 195 | Technology
Business Architect-Intermediate-US-Technology | Business Architect | Intermediate | 3-6 years | US | 189 | Technology
Business Architect-Junior-US-Technology | Business Architect | Junior | 0-3 years | US | 149 | Technology
Business Architect-Lead-US-Technology | Business Architect | Lead | 9-12 years | US | 264 | Technology
Business Architect-Principal-US-Technology | Business Architect | Principal | 12+ years | US | 321 | Technology
Business Architect-Senior-US-Technology | Business Architect | Senior | 6-9 years | US | 235 | Technology
Business Consultant-Intermediate-US-Technology | Business Consultant | Intermediate | 3-6 years | US | 212 | Technology
Business Consultant-Junior-US-Technology | Business Consultant | Junior | 0-3 years | US | 161 | Technology
Business Consultant-Lead-US-Technology | Business Consultant | Lead | 9-12 years | US | 281 | Technology
Business Consultant-Principal-US-Technology | Business Consultant | Principal | 12+ years | US | 339 | Technology
Business Consultant-Senior-US-Technology | Business Consultant | Senior | 6-9 years | US | 241 | Technology
Human Capital-Manager-Mexico-Consulting | Human Capital | Manager | 9-12 years | Mexico | 142 | Consulting
Human Capital-Senior Consultant-Mexico-Consulting | Human Capital | Senior Consultant | 6-9 years | Mexico | 83 | Consulting
Human Capital-Consultant-Mexico-Consulting | Human Capital | Consultant | 3-6 years | Mexico | 73 | Consulting
Change Manager-Intermediate-US-Technology | Change Manager | Intermediate | 3-6 years | US | 207 | Technology
Change Manager-Junior-US-Technology | Change Manager | Junior | 0-3 years | US | 163 | Technology
Cloud Architect-Intermediate-US-Technology | Cloud Architect | Intermediate | 3-6 years | US | 189 | Technology
Cloud Architect-Junior-US-Technology | Cloud Architect | Junior | 0-3 years | US | 153 | Technology
Cloud Architect-Lead-US-Technology | Cloud Architect | Lead | 9-12 years | US | 258 | Technology
Cloud Architect-Principal-US-Technology | Cloud Architect | Principal | 12+ years | US | 316 | Technology
Cloud Architect-Senior-US-Technology | Cloud Architect | Senior | 6-9 years | US | 230 | Technology
Cloud Engineer-Intermediate-US-Technology | Cloud Engineer | Intermediate | 3-6 years | US | 126 | Technology
Cloud Engineer-Junior-US-Technology | Cloud Engineer | Junior | 0-3 years | US | 120 | Technology
Cloud Engineer-Lead-US-Technology | Cloud Engineer | Lead | 9-12 years | US | 166 | Technology
Cloud Engineer-Principal-US-Technology | Cloud Engineer | Principal | 12+ years | US | 187 | Technology
Cloud Engineer-Senior-US-Technology | Cloud Engineer | Senior | 6-9 years | US | 157 | Technology
Container Engineer-Intermediate-US-Technology | Container Engineer | Intermediate | 3-6 years | US | 120 | Technology
Container Engineer-Junior-US-Technology | Container Engineer | Junior | 0-3 years | US | 108 | Technology
Container Engineer-Lead-US-Technology | Container Engineer | Lead | 9-12 years | US | 149 | Technology
Container Engineer-Principal-US-Technology | Container Engineer | Principal | 12+ years | US | 189 | Technology
Container Engineer-Senior-US-Technology | Container Engineer | Senior | 6-9 years | US | 127 | Technology
Cyber Security -Analyst-US-Consulting | Cyber Security | Analyst | 0-1 years | US | 230 | Consulting
Cyber Security -Consultant-US-Consulting | Cyber Security | Consultant | 1-3 years | US | 236 | Consulting
Cyber Security -Manager-US-Consulting | Cyber Security | Manager | 5-7 years | US | 315 | Consulting
Change Manager-Lead-US-Technology | Change Manager | Lead | 9-12 years | US | 281 | Technology
Cyber Security -Principal-US-Consulting | Cyber Security | Principal | 15+ years | US | 437 | Consulting
Cyber Security -Senior Consultant-US-Consulting | Cyber Security | Senior Consultant | 3-5 years | US | 264 | Consulting
Cyber Security -Senior Manager-US-Consulting | Cyber Security | Senior Manager | 7-10 years | US | 367 | Consulting
Cybersecurity Analyst-Intermediate-US-Technology | Cybersecurity Analyst | Intermediate | 3-6 years | US | 132 | Technology
Cybersecurity Analyst-Junior-US-Technology | Cybersecurity Analyst | Junior | 0-3 years | US | 120 | Technology
Cybersecurity Analyst-Lead-US-Technology | Cybersecurity Analyst | Lead | 9-12 years | US | 180 | Technology
Cybersecurity Analyst-Principal-US-Technology | Cybersecurity Analyst | Principal | 12+ years | US | 189 | Technology
Cybersecurity Analyst-Senior-US-Technology | Cybersecurity Analyst | Senior | 6-9 years | US | 166 | Technology
Cybersecurity Assurance Analyst-Intermediate-US-Technology | Cybersecurity Assurance Analyst | Intermediate | 3-6 years | US | 132 | Technology
Cybersecurity Assurance Analyst-Junior-US-Technology | Cybersecurity Assurance Analyst | Junior | 0-3 years | US | 120 | Technology
Cybersecurity Assurance Analyst-Lead-US-Technology | Cybersecurity Assurance Analyst | Lead | 9-12 years | US | 180 | Technology
Cybersecurity Assurance Analyst-Principal-US-Technology | Cybersecurity Assurance Analyst | Principal | 12+ years | US | 189 | Technology
Cybersecurity Assurance Analyst-Senior-US-Technology | Cybersecurity Assurance Analyst | Senior | 6-9 years | US | 166 | Technology
Cybersecurity Consultant-Intermediate-US-Technology | Cybersecurity Consultant | Intermediate | 3-6 years | US | 149 | Technology
Cybersecurity Consultant-Junior-US-Technology | Cybersecurity Consultant | Junior | 0-3 years | US | 132 | Technology
Cybersecurity Consultant-Lead-US-Technology | Cybersecurity Consultant | Lead | 9-12 years | US | 218 | Technology
Cybersecurity Consultant-Principal-US-Technology | Cybersecurity Consultant | Principal | 12+ years | US | 264 | Technology
Cybersecurity Consultant-Senior-US-Technology | Cybersecurity Consultant | Senior | 6-9 years | US | 189 | Technology
Data Analyst-Intermediate-US-Technology | Data Analyst | Intermediate | 3-6 years | US | 126 | Technology
Data Analyst-Junior-US-Technology | Data Analyst | Junior | 0-3 years | US | 120 | Technology
Data Analyst-Lead-US-Technology | Data Analyst | Lead | 9-12 years | US | 172 | Technology
Data Analyst-Principal-US-Technology | Data Analyst | Principal | 12+ years | US | 189 | Technology
Data Analyst-Senior-US-Technology | Data Analyst | Senior | 6-9 years | US | 161 | Technology
Data Architect-Intermediate-US-Technology | Data Architect | Intermediate | 3-6 years | US | 184 | Technology
Data Architect-Junior-US-Technology | Data Architect | Junior | 0-3 years | US | 166 | Technology
Data Architect-Lead-US-Technology | Data Architect | Lead | 9-12 years | US | 201 | Technology
Data Architect-Principal-US-Technology | Data Architect | Principal | 12+ years | US | 223 | Technology
Data Architect-Senior-US-Technology | Data Architect | Senior | 6-9 years | US | 192 | Technology
Data Engineer-Intermediate-US-Technology | Data Engineer | Intermediate | 3-6 years | US | 124 | Technology
Data Engineer-Junior-US-Technology | Data Engineer | Junior | 0-3 years | US | 108 | Technology
Data Engineer-Lead-US-Technology | Data Engineer | Lead | 9-12 years | US | 157 | Technology
Data Engineer-Principal-US-Technology | Data Engineer | Principal | 12+ years | US | 166 | Technology
Data Engineer-Senior-US-Technology | Data Engineer | Senior | 6-9 years | US | 148 | Technology
Data Integration Architect-Intermediate-US-Technology | Data Integration Architect | Intermediate | 3-6 years | US | 172 | Technology
Data Integration Architect-Junior-US-Technology | Data Integration Architect | Junior | 0-3 years | US | 166 | Technology
Data Integration Architect-Lead-US-Technology | Data Integration Architect | Lead | 9-12 years | US | 207 | Technology
Data Integration Architect-Principal-US-Technology | Data Integration Architect | Principal | 12+ years | US | 230 | Technology
Data Integration Architect-Senior-US-Technology | Data Integration Architect | Senior | 6-9 years | US | 195 | Technology
Data Science Developer-Intermediate-US-Technology | Data Science Developer | Intermediate | 3-6 years | US | 147 | Technology
Data Science Developer-Junior-US-Technology | Data Science Developer | Junior | 0-3 years | US | 124 | Technology
Data Science Developer-Lead-US-Technology | Data Science Developer | Lead | 9-12 years | US | 177 | Technology
Data Science Developer-Principal-US-Technology | Data Science Developer | Principal | 12+ years | US | 189 | Technology
Data Science Developer-Senior-US-Technology | Data Science Developer | Senior | 6-9 years | US | 170 | Technology
Data Visualization Engineer-Intermediate-US-Technology | Data Visualization Engineer | Intermediate | 3-6 years | US | 126 | Technology
Data Visualization Engineer-Junior-US-Technology | Data Visualization Engineer | Junior | 0-3 years | US | 122 | Technology
Data Visualization Engineer-Lead-US-Technology | Data Visualization Engineer | Lead | 9-12 years | US | 170 | Technology
Data Visualization Engineer-Principal-US-Technology | Data Visualization Engineer | Principal | 12+ years | US | 187 | Technology
Data Visualization Engineer-Senior-US-Technology | Data Visualization Engineer | Senior | 6-9 years | US | 155 | Technology
Data Warehouse / Business Intelligence Engineer-Intermediate-US-Technology | Data Warehouse / Business Intelligence Engineer | Intermediate | 3-6 years | US | 120 | Technology
Data Warehouse / Business Intelligence Engineer-Junior-US-Technology | Data Warehouse / Business Intelligence Engineer | Junior | 0-3 years | US | 108 | Technology
Data Warehouse / Business Intelligence Engineer-Lead-US-Technology | Data Warehouse / Business Intelligence Engineer | Lead | 9-12 years | US | 146 | Technology
Data Warehouse / Business Intelligence Engineer-Principal-US-Technology | Data Warehouse / Business Intelligence Engineer | Principal | 12+ years | US | 158 | Technology
Data Warehouse / Business Intelligence Engineer-Senior-US-Technology | Data Warehouse / Business Intelligence Engineer | Senior | 6-9 years | US | 142 | Technology
Database Administrator-Intermediate-US-Technology | Database Administrator | Intermediate | 3-6 years | US | 121 | Technology
Database Administrator-Junior-US-Technology | Database Administrator | Junior | 0-3 years | US | 106 | Technology
Database Administrator-Lead-US-Technology | Database Administrator | Lead | 9-12 years | US | 145 | Technology
Database Administrator-Principal-US-Technology | Database Administrator | Principal | 12+ years | US | 167 | Technology
Database Administrator-Senior-US-Technology | Database Administrator | Senior | 6-9 years | US | 133 | Technology
Deal Advisory / M&A-Analyst-US-Consulting | Deal Advisory / M&A | Analyst | 0-1 years | US | 273 | Consulting
Deal Advisory / M&A-Consultant-US-Consulting | Deal Advisory / M&A | Consultant | 1-3 years | US | 273 | Consulting
Deal Advisory / M&A-Manager-US-Consulting | Deal Advisory / M&A | Manager | 5-7 years | US | 541 | Consulting
Strategy-Managing Director-India-Consulting | Strategy | Managing Director | 10-15 years | India | 391 | Consulting
Deal Advisory / M&A-Principal-US-Consulting | Deal Advisory / M&A | Principal | 15+ years | US | 730 | Consulting
Deal Advisory / M&A-Senior Consultant-US-Consulting | Deal Advisory / M&A | Senior Consultant | 3-5 years | US | 404 | Consulting
Deal Advisory / M&A-Senior Manager-US-Consulting | Deal Advisory / M&A | Senior Manager | 7-10 years | US | 675 | Consulting
Delivery Manager-Intermediate-US-Technology | Delivery Manager | Intermediate | 3-6 years | US | 166 | Technology
Delivery Manager-Junior-US-Technology | Delivery Manager | Junior | 0-3 years | US | 150 | Technology
Delivery Manager-Lead-US-Technology | Delivery Manager | Lead | 9-12 years | US | 189 | Technology
Delivery Manager-Principal-US-Technology | Delivery Manager | Principal | 12+ years | US | 201 | Technology
Delivery Manager-Senior-US-Technology | Delivery Manager | Senior | 6-9 years | US | 178 | Technology
Desktop Engineer-Intermediate-US-Technology | Desktop Engineer | Intermediate | 3-6 years | US | 109 | Technology
Desktop Engineer-Junior-US-Technology | Desktop Engineer | Junior | 0-3 years | US | 86 | Technology
Desktop Engineer-Lead-US-Technology | Desktop Engineer | Lead | 9-12 years | US | 132 | Technology
Desktop Engineer-Principal-US-Technology | Desktop Engineer | Principal | 12+ years | US | 166 | Technology
Desktop Engineer-Senior-US-Technology | Desktop Engineer | Senior | 6-9 years | US | 120 | Technology
Developer/Coder-Intermediate-US-Technology | Developer/Coder | Intermediate | 3-6 years | US | 124 | Technology
Developer/Coder-Junior-US-Technology | Developer/Coder | Junior | 0-3 years | US | 108 | Technology
Developer/Coder-Lead-US-Technology | Developer/Coder | Lead | 9-12 years | US | 153 | Technology
Developer/Coder-Principal-US-Technology | Developer/Coder | Principal | 12+ years | US | 166 | Technology
Developer/Coder-Senior-US-Technology | Developer/Coder | Senior | 6-9 years | US | 132 | Technology
DevOps Engineer-Intermediate-US-Technology | DevOps Engineer | Intermediate | 3-6 years | US | 128 | Technology
DevOps Engineer-Junior-US-Technology | DevOps Engineer | Junior | 0-3 years | US | 108 | Technology
DevOps Engineer-Lead-US-Technology | DevOps Engineer | Lead | 9-12 years | US | 176 | Technology
DevOps Engineer-Principal-US-Technology | DevOps Engineer | Principal | 12+ years | US | 195 | Technology
DevOps Engineer-Senior-US-Technology | DevOps Engineer | Senior | 6-9 years | US | 151 | Technology
Enterprise Architect-Intermediate-US-Technology | Enterprise Architect | Intermediate | 3-6 years | US | 189 | Technology
Enterprise Architect-Junior-US-Technology | Enterprise Architect | Junior | 0-3 years | US | 153 | Technology
Enterprise Architect-Lead-US-Technology | Enterprise Architect | Lead | 9-12 years | US | 258 | Technology
Enterprise Architect-Principal-US-Technology | Enterprise Architect | Principal | 12+ years | US | 316 | Technology
Enterprise Architect-Senior-US-Technology | Enterprise Architect | Senior | 6-9 years | US | 227 | Technology
Functional Consultant-Intermediate-US-Technology | Functional Consultant | Intermediate | 3-6 years | US | 164 | Technology
Functional Consultant-Junior-US-Technology | Functional Consultant | Junior | 0-3 years | US | 143 | Technology
Functional Consultant-Lead-US-Technology | Functional Consultant | Lead | 9-12 years | US | 235 | Technology
Functional Consultant-Principal-US-Technology | Functional Consultant | Principal | 12+ years | US | 258 | Technology
Functional Consultant-Senior-US-Technology | Functional Consultant | Senior | 6-9 years | US | 204 | Technology
Change Manager-Principal-US-Technology | Change Manager | Principal | 12+ years | US | 316 | Technology
Change Manager-Senior-US-Technology | Change Manager | Senior | 6-9 years | US | 235 | Technology
Human Capital-Managing Director-US-Consulting | Human Capital | Managing Director | 10-15 years | US | 488 | Consulting
Strategy-Managing Director-US-Consulting | Strategy | Managing Director | 10-15 years | US | 750 | Consulting
Human Capital-Analyst-US-Consulting | Human Capital | Analyst | 0-1 years | US | 248 | Consulting
Human Capital-Consultant-US-Consulting | Human Capital | Consultant | 1-3 years | US | 268 | Consulting
Human Capital-Manager-US-Consulting | Human Capital | Manager | 5-7 years | US | 377 | Consulting
Infrastructure Consultant-Intermediate-US-Technology | Infrastructure Consultant | Intermediate | 3-6 years | US | 143 | Technology
Infrastructure Consultant-Junior-US-Technology | Infrastructure Consultant | Junior | 0-3 years | US | 132 | Technology
Infrastructure Consultant-Lead-US-Technology | Infrastructure Consultant | Lead | 9-12 years | US | 217 | Technology
Infrastructure Consultant-Principal-US-Technology | Infrastructure Consultant | Principal | 12+ years | US | 258 | Technology
Infrastructure Consultant-Senior-US-Technology | Infrastructure Consultant | Senior | 6-9 years | US | 189 | Technology
Infrastructure Project Manager-Intermediate-US-Technology | Infrastructure Project Manager | Intermediate | 3-6 years | US | 143 | Technology
Infrastructure Project Manager-Junior-US-Technology | Infrastructure Project Manager | Junior | 0-3 years | US | 120 | Technology
Infrastructure Project Manager-Lead-US-Technology | Infrastructure Project Manager | Lead | 9-12 years | US | 173 | Technology
Infrastructure Project Manager-Principal-US-Technology | Infrastructure Project Manager | Principal | 12+ years | US | 189 | Technology
Infrastructure Project Manager-Senior-US-Technology | Infrastructure Project Manager | Senior | 6-9 years | US | 166 | Technology
Integration Engineer-Intermediate-US-Technology | Integration Engineer | Intermediate | 3-6 years | US | 120 | Technology
Integration Engineer-Junior-US-Technology | Integration Engineer | Junior | 0-3 years | US | 108 | Technology
Integration Engineer-Lead-US-Technology | Integration Engineer | Lead | 9-12 years | US | 148 | Technology
Integration Engineer-Principal-US-Technology | Integration Engineer | Principal | 12+ years | US | 166 | Technology
Integration Engineer-Senior-US-Technology | Integration Engineer | Senior | 6-9 years | US | 140 | Technology
Integration Lead-Intermediate-US-Technology | Integration Lead | Intermediate | 3-6 years | US | 148 | Technology
Integration Lead-Junior-US-Technology | Integration Lead | Junior | 0-3 years | US | 139 | Technology
Integration Lead-Lead-US-Technology | Integration Lead | Lead | 9-12 years | US | 171 | Technology
Integration Lead-Principal-US-Technology | Integration Lead | Principal | 12+ years | US | 187 | Technology
Integration Lead-Senior-US-Technology | Integration Lead | Senior | 6-9 years | US | 154 | Technology
Kubernetes Engineer-Intermediate-US-Technology | Kubernetes Engineer | Intermediate | 3-6 years | US | 117 | Technology
Kubernetes Engineer-Junior-US-Technology | Kubernetes Engineer | Junior | 0-3 years | US | 106 | Technology
Kubernetes Engineer-Lead-US-Technology | Kubernetes Engineer | Lead | 9-12 years | US | 166 | Technology
Kubernetes Engineer-Principal-US-Technology | Kubernetes Engineer | Principal | 12+ years | US | 187 | Technology
Kubernetes Engineer-Senior-US-Technology | Kubernetes Engineer | Senior | 6-9 years | US | 140 | Technology
Network Architect-Intermediate-US-Technology | Network Architect | Intermediate | 3-6 years | US | 149 | Technology
Network Architect-Junior-US-Technology | Network Architect | Junior | 0-3 years | US | 127 | Technology
Network Architect-Lead-US-Technology | Network Architect | Lead | 9-12 years | US | 227 | Technology
Network Architect-Principal-US-Technology | Network Architect | Principal | 12+ years | US | 258 | Technology
Network Architect-Senior-US-Technology | Network Architect | Senior | 6-9 years | US | 203 | Technology
Network Engineer-Intermediate-US-Technology | Network Engineer | Intermediate | 3-6 years | US | 120 | Technology
Network Engineer-Junior-US-Technology | Network Engineer | Junior | 0-3 years | US | 115 | Technology
Network Engineer-Lead-US-Technology | Network Engineer | Lead | 9-12 years | US | 138 | Technology
Network Engineer-Principal-US-Technology | Network Engineer | Principal | 12+ years | US | 178 | Technology
Network Engineer-Senior-US-Technology | Network Engineer | Senior | 6-9 years | US | 124 | Technology
Program Director/ Industry Lead-Intermediate-US-Technology | Program Director/ Industry Lead | Intermediate | 3-6 years | US | 224 | Technology
Program Director/ Industry Lead-Junior-US-Technology | Program Director/ Industry Lead | Junior | 0-3 years | US | 163 | Technology
Program Director/ Industry Lead-Lead-US-Technology | Program Director/ Industry Lead | Lead | 9-12 years | US | 316 | Technology
Program Director/ Industry Lead-Principal-US-Technology | Program Director/ Industry Lead | Principal | 12+ years | US | 344 | Technology
Program Director/ Industry Lead-Senior-US-Technology | Program Director/ Industry Lead | Senior | 6-9 years | US | 287 | Technology
Program Manager-Intermediate-US-Technology | Program Manager | Intermediate | 3-6 years | US | 218 | Technology
Program Manager-Junior-US-Technology | Program Manager | Junior | 0-3 years | US | 163 | Technology
Program Manager-Lead-US-Technology | Program Manager | Lead | 9-12 years | US | 281 | Technology
Program Manager-Principal-US-Technology | Program Manager | Principal | 12+ years | US | 304 | Technology
Program Manager-Senior-US-Technology | Program Manager | Senior | 6-9 years | US | 247 | Technology
Project Manager-Intermediate-US-Technology | Project Manager | Intermediate | 3-6 years | US | 143 | Technology
Project Manager-Junior-US-Technology | Project Manager | Junior | 0-3 years | US | 120 | Technology
Project Manager-Lead-US-Technology | Project Manager | Lead | 9-12 years | US | 173 | Technology
Project Manager-Principal-US-Technology | Project Manager | Principal | 12+ years | US | 192 | Technology
Project Manager-Senior-US-Technology | Project Manager | Senior | 6-9 years | US | 166 | Technology
Scrum Master-Intermediate-US-Technology | Scrum Master | Intermediate | 3-6 years | US | 143 | Technology
Scrum Master-Junior-US-Technology | Scrum Master | Junior | 0-3 years | US | 120 | Technology
Scrum Master-Lead-US-Technology | Scrum Master | Lead | 9-12 years | US | 181 | Technology
Scrum Master-Principal-US-Technology | Scrum Master | Principal | 12+ years | US | 201 | Technology
Scrum Master-Senior-US-Technology | Scrum Master | Senior | 6-9 years | US | 166 | Technology
Security Architect-Intermediate-US-Technology | Security Architect | Intermediate | 3-6 years | US | 195 | Technology
Security Architect-Junior-US-Technology | Security Architect | Junior | 0-3 years | US | 189 | Technology
Security Architect-Lead-US-Technology | Security Architect | Lead | 9-12 years | US | 258 | Technology
Security Architect-Principal-US-Technology | Security Architect | Principal | 12+ years | US | 316 | Technology
Security Architect-Senior-US-Technology | Security Architect | Senior | 6-9 years | US | 227 | Technology
Security Engineer-Intermediate-US-Technology | Security Engineer | Intermediate | 3-6 years | US | 122 | Technology
Security Engineer-Junior-US-Technology | Security Engineer | Junior | 0-3 years | US | 118 | Technology
Security Engineer-Lead-US-Technology | Security Engineer | Lead | 9-12 years | US | 164 | Technology
Security Engineer-Principal-US-Technology | Security Engineer | Principal | 12+ years | US | 187 | Technology
Security Engineer-Senior-US-Technology | Security Engineer | Senior | 6-9 years | US | 157 | Technology
ServiceNow Architect-Intermediate-US-Technology | ServiceNow Architect | Intermediate | 3-6 years | US | 172 | Technology
ServiceNow Architect-Junior-US-Technology | ServiceNow Architect | Junior | 0-3 years | US | 153 | Technology
ServiceNow Architect-Lead-US-Technology | ServiceNow Architect | Lead | 9-12 years | US | 201 | Technology
ServiceNow Architect-Principal-US-Technology | ServiceNow Architect | Principal | 12+ years | US | 223 | Technology
ServiceNow Architect-Senior-US-Technology | ServiceNow Architect | Senior | 6-9 years | US | 192 | Technology
Software Engineer-Intermediate-US-Technology | Software Engineer | Intermediate | 3-6 years | US | 124 | Technology
Software Engineer-Junior-US-Technology | Software Engineer | Junior | 0-3 years | US | 108 | Technology
Software Engineer-Lead-US-Technology | Software Engineer | Lead | 9-12 years | US | 153 | Technology
Software Engineer-Principal-US-Technology | Software Engineer | Principal | 12+ years | US | 166 | Technology
Software Engineer-Senior-US-Technology | Software Engineer | Senior | 6-9 years | US | 142 | Technology
Solution Architect-Intermediate-US-Technology | Solution Architect | Intermediate | 3-6 years | US | 189 | Technology
Solution Architect-Junior-US-Technology | Solution Architect | Junior | 0-3 years | US | 153 | Technology
Solution Architect-Lead-US-Technology | Solution Architect | Lead | 9-12 years | US | 258 | Technology
Solution Architect-Principal-US-Technology | Solution Architect | Principal | 12+ years | US | 316 | Technology
Solution Architect-Senior-US-Technology | Solution Architect | Senior | 6-9 years | US | 227 | Technology
Strategy-Analyst-US-Consulting | Strategy | Analyst | 0-1 years | US | 351 | Consulting
Strategy-Consultant-US-Consulting | Strategy | Consultant | 1-3 years | US | 388 | Consulting
Strategy-Manager-US-Consulting | Strategy | Manager | 5-7 years | US | 568 | Consulting
Technology-Managing Director-India-Consulting | Technology | Managing Director | 10-15 years | India | 180 | Consulting
Strategy-Principal-US-Consulting | Strategy | Principal | 15+ years | US | 750 | Consulting
Strategy-Senior Consultant-US-Consulting | Strategy | Senior Consultant | 3-5 years | US | 471 | Consulting
Strategy-Senior Manager-US-Consulting | Strategy | Senior Manager | 7-10 years | US | 647 | Consulting
System Administrator-Intermediate-US-Technology | System Administrator | Intermediate | 3-6 years | US | 114 | Technology
System Administrator-Junior-US-Technology | System Administrator | Junior | 0-3 years | US | 104 | Technology
System Administrator-Lead-US-Technology | System Administrator | Lead | 9-12 years | US | 142 | Technology
System Administrator-Principal-US-Technology | System Administrator | Principal | 12+ years | US | 151 | Technology
System Administrator-Senior-US-Technology | System Administrator | Senior | 6-9 years | US | 125 | Technology
Systems Engineer-Intermediate-US-Technology | Systems Engineer | Intermediate | 3-6 years | US | 124 | Technology
Systems Engineer-Junior-US-Technology | Systems Engineer | Junior | 0-3 years | US | 115 | Technology
Systems Engineer-Lead-US-Technology | Systems Engineer | Lead | 9-12 years | US | 157 | Technology
Systems Engineer-Principal-US-Technology | Systems Engineer | Principal | 12+ years | US | 166 | Technology
Systems Engineer-Senior-US-Technology | Systems Engineer | Senior | 6-9 years | US | 148 | Technology
Systems Implementation Consultant-Intermediate-US-Technology | Systems Implementation Consultant | Intermediate | 3-6 years | US | 143 | Technology
Systems Implementation Consultant-Junior-US-Technology | Systems Implementation Consultant | Junior | 0-3 years | US | 132 | Technology
Systems Implementation Consultant-Lead-US-Technology | Systems Implementation Consultant | Lead | 9-12 years | US | 217 | Technology
Systems Implementation Consultant-Principal-US-Technology | Systems Implementation Consultant | Principal | 12+ years | US | 258 | Technology
Systems Implementation Consultant-Senior-US-Technology | Systems Implementation Consultant | Senior | 6-9 years | US | 189 | Technology
Tech Consultant-Intermediate-US-Technology | Tech Consultant | Intermediate | 3-6 years | US | 132 | Technology
Tech Consultant-Junior-US-Technology | Tech Consultant | Junior | 0-3 years | US | 120 | Technology
Tech Consultant-Lead-US-Technology | Tech Consultant | Lead | 9-12 years | US | 180 | Technology
Tech Consultant-Principal-US-Technology | Tech Consultant | Principal | 12+ years | US | 189 | Technology
Tech Consultant-Senior-US-Technology | Tech Consultant | Senior | 6-9 years | US | 166 | Technology
Technical Analyst-Intermediate-US-Technology | Technical Analyst | Intermediate | 3-6 years | US | 117 | Technology
Technical Analyst-Junior-US-Technology | Technical Analyst | Junior | 0-3 years | US | 106 | Technology
Technical Analyst-Lead-US-Technology | Technical Analyst | Lead | 9-12 years | US | 164 | Technology
Technical Analyst-Principal-US-Technology | Technical Analyst | Principal | 12+ years | US | 177 | Technology
Technical Analyst-Senior-US-Technology | Technical Analyst | Senior | 6-9 years | US | 148 | Technology
Technical Architect-Intermediate-US-Technology | Technical Architect | Intermediate | 3-6 years | US | 145 | Technology
Technical Architect-Junior-US-Technology | Technical Architect | Junior | 0-3 years | US | 125 | Technology
Technical Architect-Lead-US-Technology | Technical Architect | Lead | 9-12 years | US | 201 | Technology
Technical Architect-Principal-US-Technology | Technical Architect | Principal | 12+ years | US | 223 | Technology
Technical Architect-Senior-US-Technology | Technical Architect | Senior | 6-9 years | US | 166 | Technology
Technical Consultant-Intermediate-US-Technology | Technical Consultant | Intermediate | 3-6 years | US | 120 | Technology
Technical Consultant-Junior-US-Technology | Technical Consultant | Junior | 0-3 years | US | 115 | Technology
Technical Consultant-Lead-US-Technology | Technical Consultant | Lead | 9-12 years | US | 174 | Technology
Technical Consultant-Principal-US-Technology | Technical Consultant | Principal | 12+ years | US | 189 | Technology
Technical Consultant-Senior-US-Technology | Technical Consultant | Senior | 6-9 years | US | 157 | Technology
Technical Writer-Intermediate-US-Technology | Technical Writer | Intermediate | 3-6 years | US | 106 | Technology
Technical Writer-Junior-US-Technology | Technical Writer | Junior | 0-3 years | US | 86 | Technology
Technical Writer-Lead-US-Technology | Technical Writer | Lead | 9-12 years | US | 142 | Technology
Technical Writer-Principal-US-Technology | Technical Writer | Principal | 12+ years | US | 151 | Technology
Technical Writer-Senior-US-Technology | Technical Writer | Senior | 6-9 years | US | 132 | Technology
Technical/Functional Team Lead-Intermediate-US-Technology | Technical/Functional Team Lead | Intermediate | 3-6 years | US | 127 | Technology
Technical/Functional Team Lead-Junior-US-Technology | Technical/Functional Team Lead | Junior | 0-3 years | US | 120 | Technology
Technical/Functional Team Lead-Lead-US-Technology | Technical/Functional Team Lead | Lead | 9-12 years | US | 172 | Technology
Technical/Functional Team Lead-Principal-US-Technology | Technical/Functional Team Lead | Principal | 12+ years | US | 189 | Technology
Technical/Functional Team Lead-Senior-US-Technology | Technical/Functional Team Lead | Senior | 6-9 years | US | 157 | Technology
Technology-Analyst-US-Consulting | Technology | Analyst | 0-1 years | US | 189 | Consulting
Technology-Consultant-US-Consulting | Technology | Consultant | 1-3 years | US | 194 | Consulting
Technology-Manager-US-Consulting | Technology | Manager | 5-7 years | US | 306 | Consulting
Technology-Managing Director-US-Consulting | Technology | Managing Director | 10-15 years | US | 383 | Consulting
Technology-Principal-US-Consulting | Technology | Principal | 15+ years | US | 383 | Consulting
Technology-Senior Consultant-US-Consulting | Technology | Senior Consultant | 3-5 years | US | 260 | Consulting
Technology-Senior Manager-US-Consulting | Technology | Senior Manager | 7-10 years | US | 342 | Consulting
Technology Analyst-Intermediate-US-Technology | Technology Analyst | Intermediate | 3-6 years | US | 140 | Technology
Technology Analyst-Junior-US-Technology | Technology Analyst | Junior | 0-3 years | US | 120 | Technology
Technology Analyst-Lead-US-Technology | Technology Analyst | Lead | 9-12 years | US | 164 | Technology
Technology Analyst-Principal-US-Technology | Technology Analyst | Principal | 12+ years | US | 177 | Technology
Technology Analyst-Senior-US-Technology | Technology Analyst | Senior | 6-9 years | US | 154 | Technology
Test Engineer-Intermediate-US-Technology | Test Engineer | Intermediate | 3-6 years | US | 114 | Technology
Test Engineer-Junior-US-Technology | Test Engineer | Junior | 0-3 years | US | 102 | Technology
Test Engineer-Lead-US-Technology | Test Engineer | Lead | 9-12 years | US | 147 | Technology
Test Engineer-Principal-US-Technology | Test Engineer | Principal | 12+ years | US | 156 | Technology
Test Engineer-Senior-US-Technology | Test Engineer | Senior | 6-9 years | US | 134 | Technology
UX Designer-Intermediate-US-Technology | UX Designer | Intermediate | 3-6 years | US | 166 | Technology
UX Designer-Junior-US-Technology | UX Designer | Junior | 0-3 years | US | 147 | Technology
UX Designer-Lead-US-Technology | UX Designer | Lead | 9-12 years | US | 239 | Technology
UX Designer-Principal-US-Technology | UX Designer | Principal | 12+ years | US | 272 | Technology
UX Designer-Senior-US-Technology | UX Designer | Senior | 6-9 years | US | 207 | Technology
Validation-Partner-US-Consulting | Validation | Partner | 15+ years | US | 750 | Consulting
Validation-Senior Manager-US-Consulting | Validation | Senior Manager | 7-10 years | US | 647 | Consulting
Validation-Manager-India-Consulting | Validation | Manager | 9-12 years | India | 161 | Consulting
Validation-Senior Consultant-India-Consulting | Validation | Senior Consultant | 6-9 years | India | 121 | Consulting
Validation-Consultant-India-Consulting | Validation | Consultant | 3-6 years | India | 104 | Consulting
Validation-Analyst-India-Consulting | Validation | Analyst | 1-3 years | India | 48 | Consulting
Human Capital-Principal-US-Consulting | Human Capital | Principal | 15+ years | US | 488 | Consulting
Human Capital-Senior Consultant-US-Consulting | Human Capital | Senior Consultant | 3-5 years | US | 326 | Consulting
Human Capital-Senior Manager-US-Consulting | Human Capital | Senior Manager | 7-10 years | US | 409 | Consulting
---
---
---
---
---
---
---
---
---
---
---
---
---
---
---
---
---
---
---
---
---
---
Tax Advisory-Partner-US-Tax | Tax Advisory | Partner | 12+ years | US | 625 | Tax
Tax Advisory-Managing Director-US-Tax | Tax Advisory | Managing Director | 12+ years | US | 575 | Tax
Tax Advisory-Senior Manager-US-Tax | Tax Advisory | Senior Manager | 9-12 years | US | 500 | Tax
Tax Advisory-Manager-US-Tax | Tax Advisory | Manager | 6-9 years | US | 365 | Tax
Tax Advisory-Senior Consultant-US-Tax | Tax Advisory | Senior Consultant | 3-6 years | US | 285 | Tax
Tax Advisory-Consultant-US-Tax | Tax Advisory | Consultant | 0-3 years | US | 185 | Tax
Tax Advisory-Principal-India-Tax | Tax Advisory | Principal | 12+ years | India | N/A | Tax
Tax Advisory-Managing Director-India-Tax | Tax Advisory | Managing Director | 12+ years | India | N/A | Tax
Tax Advisory-Senior Manager-India-Tax | Tax Advisory | Senior Manager | 9-12 years | India | 330 | Tax
Tax Advisory-Manager-India-Tax | Tax Advisory | Manager | 6-9 years | India | 240 | Tax
Tax Advisory-Senior Consultant-India-Tax | Tax Advisory | Senior Consultant | 3-6 years | India | 180 | Tax
Tax Advisory-Consultant-India-Tax | Tax Advisory | Consultant | 0-3 years | India | 120 | Tax

## Sheet2
2740749

## Assumptions
Team | Assumption
RTR
PTD
PTD-Warehouse & Logistics | 3PL Testing Scope - 3PL interfaces will be tested per variation per 3PL provider. Testing will not be carried out for each 3PL site (or Plants) 3PL resources also covers for XPS integration to integrate with the different carriers in scope Warehouse Automation resource is required to manage different integrations in scope - Cartonization, MES, Lotus (picking), etc. | Project 2 to run SAP report STOCKROOM_COMPLIANCE_CHECK (refer SAP Note 2882809) for warehouses in ECC to validate LE-WM functionality that falls outside the Stock Room Management scope. Review the fallowing functionality Cross-Docking, Yard Management, Wave Management, Value Added Services, Task & Resource Management, Decentral WM, and Warehouse Control Interface.
PTD-MFG | Staffing covers - PP, QM, PM & Planning PP -
PTP
OTC | Vistex upgrade will follow same project plan timeline and guidelines as S4.
Data
Development
Integration
OCM | - Training material development includes Quick Reference Guide modality for X number of estimated Remediate Processes and instructor-led and/or web-based training modality for X number of estimated Reimagine processes [insert total # of learning hrs or # of documents assumed this would include] - Training material development efforts assume permissible use of Claude AI, availability of Storyline articulate or similar simulation development/web-authoring tools provided by Project 2 -Any licensing requirement for developing & delivering training content (e.g., Storyline, SAP WalkMe Learning Arc) will be Project 2's responsibility - Training content will be limited to one global set of materials with no country/regional/site specific localizations - All communications and training materials will be developed in English; Project 2 is responsible for translating materials into local languages - Change and communications in a global hub with regional spoke OCM delivery model, with Deloitte support enabling the Global Hub and Project 2 support enabling both the Global Hub and the Regional OCM delivery - Project 2 owns development and delivery of external communications as needed. Consultant may support identification of external communications needs and tracking as part of overall communications plan - Project 2 will be primarily responsible for documenting/updating any Business Standard Operating Procedure (SOP) and Work Instruction (WI)
Analytics | 1. The current estimates are based on the assumption that SAP ODS will be remediated. SAP Business Data Cloud (BDC) is not accounted for in the current scope, as that decision will be made during the scoping phase. 2. No new reports will be built and no existing reports will be remediated. 3. 75 SAP ODS objects will be remediated. 4. 25 new SAP ODS objects will be built. 5. All other SAP ODS objects will be repointed to S/4HANA as-is, with no remediation efforts. 6. Project 2 will be responsible for any changes required in Databricks, Snowflake, or other downstream systems resulting from the SAP ODS changes.
Tax | Tax SAP and Vertex Scope - Implementation of Vertex O-Series with Vertex Accelerator for US and Canada Only - Migration of Tax Codes for all other countries in scope for 48 countries - Configuration of extended withholding tax codes for 48 countries - Brazil is out of scope DRC - Functional Scope - DRC AP/AR e-invoicing for Italy, Germany, Belgium - Brazil is out of scope - Relevant DRC SAP OSS notes inventory application with Basis team

## RICEFW Scope
ABAP Objects | Enhance Objects |  |  | ‘New’ RICEFW Objects |  |  | Total | As per RFP Page 11
| Low | Medium | High | Low | Medium | High
Reports | 6 | [5 empty] | 6 | ABAP Objects | Enhance Objects | ‘New’ RICEFW Objects | Total
Interfaces | 3 | [5 empty] | 2 | Reports | 5 | 28 | 33
Conversions | [6 empty] | 0 | Interfaces | 38 | 5 | 43
Enhancements | [5 empty] | 1 | 1 | Conversions | 30 | 16 | 46
Forms | 4 |  |  |  | 1 |  | 5 | Enhancements | 29 | 106 | 135
Total | 13 |  |  | 0 | 1 | 1 | 14 | Forms | 98 | 6 | 104
[8 empty] | Workflows | 36 | 16 | 52
[8 empty] | Fiori | 33 | 11 | 44
[8 empty] | Total | 269 | 188 | 457
56
[9 empty] | 16380 | 20736 | 13000
232.1429
5.1587

## RICEFW Details
# | Process Area | RICEFW Type | Category | No. of Objects | Complexity | Technology | RICEFW Description | Adopt | Report
[8 empty] | Enhance | Interface
[8 empty] | New | Conversion
Enhancement
Forms
Workflow

## Project 2 Staffing Needs (hidden)
[8 empty] | Prework | [8 empty] | Discover |  |  |  | Design | [15 empty] | MC1 |  |  |  |  | MC2 |  |  |  | MC3 |  |  |  |  | FPC
[25 empty] | Build | [13 empty] | SIT 1 |  |  |  | SIT 2 |  |  |  | UAT |  |  |  |  | Hypercare
[6 empty] | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28
[5 empty] | 6810 | FY27-P2 | FY27-P3 | FY27-P3 | FY27-P3 | FY27-P3 | FY27-P4 | FY27-P4 | FY27-P4 | FY27-P4 | FY27-P5 | FY27-P5 | FY27-P5 | FY27-P5 | FY27-P6 | FY27-P6 | FY27-P6 | FY27-P6 | FY27-P7 | FY27-P7 | FY27-P7 | FY27-P7 | FY27-P8 | FY27-P8 | FY27-P8 | FY27-P8 | FY27-P9 | FY27-P9 | FY27-P9 | FY27-P9 | FY27-P10 | FY27-P10 | FY27-P10 | FY27-P10 | FY27-P11 | FY27-P11 | FY27-P11 | FY27-P11 | FY27-P12 | FY27-P12 | FY27-P12 | FY27-P12 | FY27-P13 | FY27-P13 | FY27-P13 | FY27-P13 | FY28-P1 | FY28-P1 | FY28-P1 | FY28-P1 | FY28-P2 | FY28-P2 | FY28-P2 | FY28-P2 | FY28-P3 | FY28-P3 | FY28-P3 | FY28-P3 | FY28-P4 | FY28-P4 | FY28-P4 | FY28-P4 | FY28-P5 | FY28-P5 | FY28-P5 | FY28-P5 | FY28-P6 | FY28-P6 | FY28-P6 | FY28-P6 | FY28-P7 | FY28-P7 | FY28-P7 | FY28-P7 | FY28-P8 | FY28-P8
Process or Enabling | Team | Business/IT | Role Name | Location | Total Hours | time axis 2026-07-20 to 2027-12-27
Enabling | PMO | Business | Business PMO |  | 332 |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
Enabling | PMO | IT | IT PMO |  | 776 |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20
Process | Cross | IT | Solution Architect |  | 626 |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
Process | OTC | IT | Order Fullfilment and GATP SME |  | 264 | 2026-10-05: 4; 2026-10-12: 4; 2026-10-19: 4; 2026-10-26: 4; 2026-11-02: 8; 2026-11-09: 8; 2026-11-16: 8; 2026-11-23: 8; 2026-11-30: 8; 2026-12-07: 8; 2026-12-14: 8; 2026-12-21: 8; 2026-12-28: 8; 2027-01-04: 8; 2027-01-11: 8; 2027-01-18: 8; 2027-01-25: 8; 2027-02-01: 8; 2027-02-08: 8; 2027-02-15: 8; 2027-02-22: 8; 2027-03-01: 8; 2027-03-08: 8; 2027-03-15: 8; 2027-03-22: 8; 2027-03-29: 8; 2027-04-05: 8; 2027-04-12: 8; 2027-04-19: 8; 2027-04-26: 8; 2027-05-03: 8; 2027-05-10: 8; 2027-05-17: 8; 2027-05-24: 8; 2027-05-31: 4; 2027-06-07: 4
Process | PTP | Business | Procurement SME |  | 162 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 2
Process | PTP | IT | IT - Procurement |  | 266 | 2026-10-05: 4; 2026-10-12: 4; 2026-10-19: 4; 2026-10-26: 4; 2026-11-02: 8; 2026-11-09: 8; 2026-11-16: 8; 2026-11-23: 8; 2026-11-30: 8; 2026-12-07: 8; 2026-12-14: 8; 2026-12-21: 8; 2026-12-28: 8; 2027-01-04: 8; 2027-01-11: 8; 2027-01-18: 8; 2027-01-25: 8; 2027-02-01: 8; 2027-02-08: 8; 2027-02-15: 8; 2027-02-22: 8; 2027-03-01: 8; 2027-03-08: 8; 2027-03-15: 8; 2027-03-22: 8; 2027-03-29: 8; 2027-04-05: 8; 2027-04-12: 8; 2027-04-19: 8; 2027-04-26: 8; 2027-05-03: 8; 2027-05-10: 8; 2027-05-17: 8; 2027-05-24: 8; 2027-05-31: 4; 2027-06-07: 4; 2027-06-14: 2
Process | PTD | Business | Manufacturing/QM SME |  | 394 |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 4 | 4
Process | PTD | Business | Logistics SME |  | 394 |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 4 | 4
Process | PTD | IT | Manufacturing/QM IT SME |  | 788 |  |  | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 8 | 8
Process | PTD | IT | Logistics IT SME |  | 788 |  |  | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 8 | 8
Enabling | Technology | IT | Technology Lead |  | 200 | 2026-10-05: 4; 2026-10-12: 4; 2026-10-19: 4; 2026-10-26: 4; 2026-11-02: 4; 2026-11-09: 4; 2026-11-16: 4; 2026-11-23: 4; 2026-11-30: 8; 2026-12-07: 8; 2026-12-14: 8; 2026-12-21: 8; 2026-12-28: 8; 2027-01-04: 8; 2027-01-11: 8; 2027-01-18: 8; 2027-01-25: 8; 2027-02-01: 8; 2027-02-08: 8; 2027-02-15: 8; 2027-02-22: 8; 2027-03-01: 8; 2027-03-08: 4; 2027-03-15: 4; 2027-03-22: 4; 2027-03-29: 4; 2027-04-05: 4; 2027-04-12: 4; 2027-04-19: 4; 2027-04-26: 4; 2027-05-03: 4; 2027-05-10: 4; 2027-05-17: 4; 2027-05-24: 4; 2027-05-31: 4; 2027-06-07: 4
Enabling | Technology | IT | Basis Lead |  | 100 | 2026-10-05: 2; 2026-10-12: 2; 2026-10-19: 2; 2026-10-26: 2; 2026-11-02: 2; 2026-11-09: 2; 2026-11-16: 2; 2026-11-23: 2; 2026-11-30: 4; 2026-12-07: 4; 2026-12-14: 4; 2026-12-21: 4; 2026-12-28: 4; 2027-01-04: 4; 2027-01-11: 4; 2027-01-18: 4; 2027-01-25: 4; 2027-02-01: 4; 2027-02-08: 4; 2027-02-15: 4; 2027-02-22: 4; 2027-03-01: 4; 2027-03-08: 2; 2027-03-15: 2; 2027-03-22: 2; 2027-03-29: 2; 2027-04-05: 2; 2027-04-12: 2; 2027-04-19: 2; 2027-04-26: 2; 2027-05-03: 2; 2027-05-10: 2; 2027-05-17: 2; 2027-05-24: 2; 2027-05-31: 2; 2027-06-07: 2
Enabling | Data | Business | Data Lead |  | 468 | 2026-10-12: 4; 2026-10-19: 4; 2026-10-26: 4; 2026-11-02: 4; 2026-11-09: 4; 2026-11-16: 4; 2026-11-23: 4; 2026-11-30: 16; 2026-12-07: 16; 2026-12-14: 16; 2026-12-21: 16; 2026-12-28: 16; 2027-01-04: 16; 2027-01-11: 16; 2027-01-18: 16; 2027-01-25: 16; 2027-02-01: 16; 2027-02-08: 16; 2027-02-15: 16; 2027-02-22: 16; 2027-03-01: 16; 2027-03-08: 16; 2027-03-15: 16; 2027-03-22: 16; 2027-03-29: 16; 2027-04-05: 16; 2027-04-12: 16; 2027-04-19: 16; 2027-04-26: 16; 2027-05-03: 16; 2027-05-10: 16; 2027-05-17: 16; 2027-05-24: 16; 2027-05-31: 16; 2027-06-07: 4; 2027-06-14: 4
Enabling | PTD | IT | Data IT SMEs |  | 468 | 2026-10-12: 4; 2026-10-19: 4; 2026-10-26: 4; 2026-11-02: 4; 2026-11-09: 4; 2026-11-16: 4; 2026-11-23: 4; 2026-11-30: 16; 2026-12-07: 16; 2026-12-14: 16; 2026-12-21: 16; 2026-12-28: 16; 2027-01-04: 16; 2027-01-11: 16; 2027-01-18: 16; 2027-01-25: 16; 2027-02-01: 16; 2027-02-08: 16; 2027-02-15: 16; 2027-02-22: 16; 2027-03-01: 16; 2027-03-08: 16; 2027-03-15: 16; 2027-03-22: 16; 2027-03-29: 16; 2027-04-05: 16; 2027-04-12: 16; 2027-04-19: 16; 2027-04-26: 16; 2027-05-03: 16; 2027-05-10: 16; 2027-05-17: 16; 2027-05-24: 16; 2027-05-31: 16; 2027-06-07: 4; 2027-06-14: 4
Enabling | Security | IT | Security Lead |  | 358 | 2026-10-26: 2; 2026-11-02: 2; 2026-11-09: 2; 2026-11-16: 2; 2026-11-23: 2; 2026-11-30: 8; 2026-12-07: 8; 2026-12-14: 8; 2026-12-21: 8; 2026-12-28: 8; 2027-01-04: 8; 2027-01-11: 8; 2027-01-18: 8; 2027-01-25: 8; 2027-02-01: 8; 2027-02-08: 8; 2027-02-15: 8; 2027-02-22: 8; 2027-03-01: 16; 2027-03-08: 16; 2027-03-15: 16; 2027-03-22: 16; 2027-03-29: 16; 2027-04-05: 16; 2027-04-12: 16; 2027-04-19: 16; 2027-04-26: 16; 2027-05-03: 16; 2027-05-10: 16; 2027-05-17: 16; 2027-05-24: 16; 2027-05-31: 16; 2027-06-07: 16; 2027-06-14: 4
Enabling | OCM | Business | Change Management Lead |  | 102 | 2026-10-12: 2; 2026-10-19: 2; 2026-10-26: 2; 2026-11-02: 2; 2026-11-09: 2; 2026-11-16: 2; 2026-11-23: 2; 2026-11-30: 2; 2026-12-07: 2; 2026-12-14: 2; 2026-12-21: 2; 2026-12-28: 2; 2027-01-04: 2; 2027-01-11: 2; 2027-01-18: 2; 2027-01-25: 2; 2027-02-01: 2; 2027-02-08: 2; 2027-02-15: 2; 2027-02-22: 2; 2027-03-01: 4; 2027-03-08: 4; 2027-03-15: 4; 2027-03-22: 4; 2027-03-29: 4; 2027-04-05: 4; 2027-04-12: 4; 2027-04-19: 4; 2027-04-26: 4; 2027-05-03: 4; 2027-05-10: 4; 2027-05-17: 4; 2027-05-24: 4; 2027-05-31: 4; 2027-06-07: 4; 2027-06-14: 2
Process | GTS | Business | Global Trade SME |  | 108 | 2026-11-02: 2; 2026-11-09: 2; 2026-11-16: 2; 2026-11-23: 2; 2026-11-30: 2; 2026-12-07: 2; 2026-12-14: 2; 2026-12-21: 2; 2026-12-28: 2; 2027-01-04: 4; 2027-01-11: 4; 2027-01-18: 4; 2027-01-25: 4; 2027-02-01: 4; 2027-02-08: 4; 2027-02-15: 4; 2027-02-22: 4; 2027-03-01: 4; 2027-03-08: 4; 2027-03-15: 4; 2027-03-22: 4; 2027-03-29: 4; 2027-04-05: 4; 2027-04-12: 4; 2027-04-19: 4; 2027-04-26: 4; 2027-05-03: 4; 2027-05-10: 4; 2027-05-17: 4; 2027-05-24: 4; 2027-05-31: 4; 2027-06-07: 2
Enabling | Snowflake | IT | Snowflake lead |  | 216 | 2026-11-02: 4; 2026-11-09: 4; 2026-11-16: 4; 2026-11-23: 4; 2026-11-30: 4; 2026-12-07: 4; 2026-12-14: 4; 2026-12-21: 4; 2026-12-28: 4; 2027-01-04: 8; 2027-01-11: 8; 2027-01-18: 8; 2027-01-25: 8; 2027-02-01: 8; 2027-02-08: 8; 2027-02-15: 8; 2027-02-22: 8; 2027-03-01: 8; 2027-03-08: 8; 2027-03-15: 8; 2027-03-22: 8; 2027-03-29: 8; 2027-04-05: 8; 2027-04-12: 8; 2027-04-19: 8; 2027-04-26: 8; 2027-05-03: 8; 2027-05-10: 8; 2027-05-17: 8; 2027-05-24: 8; 2027-05-31: 4; 2027-06-07: 4; 2027-06-14: 4
[5 empty] | Hours | 0 | 0 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 126 | 136 | 136 | 138 | 152 | 152 | 152 | 152 | 188 | 188 | 188 | 188 | 188 | 194 | 194 | 194 | 194 | 194 | 194 | 194 | 194 | 204 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 188 | 176 | 112 | 84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | FTEs | 0 | 0 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 0.95 | 3.15 | 3.4 | 3.4 | 3.45 | 3.8 | 3.8 | 3.8 | 3.8 | 4.7 | 4.7 | 4.7 | 4.7 | 4.7 | 4.85 | 4.85 | 4.85 | 4.85 | 4.85 | 4.85 | 4.85 | 4.85 | 5.1 | 4.7 | 4.7 | 4.7 | 4.7 | 4.7 | 4.7 | 4.7 | 4.7 | 4.7 | 4.7 | 4.7 | 4.7 | 4.4 | 2.8 | 2.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Staffing - Baseline (hidden)
Fees | #VALUE! |  | Technology | 19.17% | [38 empty] | Define |  |  |  | Template Validation and Delta Design | [18 empty] | MC1 | [5 empty] | MC2 | [5 empty] | MC3 |  | UAT |  |  |  |  | FPC
Hours | 39063 |  | Consulting | 66.04% | [49 empty] | Build | [13 empty] | ITC1 | [5 empty] | ITC2 | [7 empty] | Dry Run |  |  |  |  | Hypercare
RPH | #VALUE! |  | Tax | 4.124%
[118 empty] | P9 | P10 | P11 | P12 | P13 | P1 | P2 | P3 | P4 | P5 | P6 | P7 | P8 | P9 | P10 | P11 | P12 | P13 | P1 | P2 | P3 | P4 | P5 | P6 | P7 | P8
[22 empty] | FY26 | FY26 | FY26 | FY26 | FY26 | FY26 | FY26 | FY26 | FY26 | FY26 | FY26 | FY26 | FY26 | FY26 | FY26 | FY26 | FY26 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY27 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | FY28 | Start Date | 2026-01-11 | 2026-02-08 | 2026-03-08 | 2026-04-05 | 2026-05-03 | 2026-05-31 | 2026-06-28 | 2026-07-26 | 2026-08-23 | 2026-09-20 | 2026-10-18 | 2026-11-15 | 2026-12-13 | 2027-01-10 | 2027-02-07 | 2027-03-07 | 2027-04-04 | 2027-05-02 | 2027-05-30 | 2027-06-27 | 2027-07-25 | 2027-08-22 | 2027-09-19 | 2027-10-17 | 2027-11-14 | 2027-12-12
[13 empty] | #VALUE! | 39063 |  |  |  | Rate Information |  |  |  | FY26-P09 | FY26-P10 | FY26-P10 | FY26-P10 | FY26-P10 | FY26-P11 | FY26-P11 | FY26-P11 | FY26-P11 | FY26-P12 | FY26-P12 | FY26-P12 | FY26-P12 | FY26-P13 | FY26-P13 | FY26-P13 | FY26-P13 | FY27-P01 | FY27-P01 | FY27-P2 | FY27-P3 | FY27-P3 | FY27-P3 | FY27-P3 | FY27-P4 | FY27-P4 | FY27-P4 | FY27-P4 | FY27-P5 | FY27-P5 | FY27-P5 | FY27-P5 | FY27-P6 | FY27-P6 | FY27-P6 | FY27-P6 | FY27-P7 | FY27-P7 | FY27-P7 | FY27-P7 | FY27-P8 | FY27-P8 | FY27-P8 | FY27-P8 | FY27-P9 | FY27-P9 | FY27-P9 | FY27-P9 | FY27-P10 | FY27-P10 | FY27-P10 | FY27-P10 | FY27-P11 | FY27-P11 | FY27-P11 | FY27-P11 | FY27-P12 | FY27-P12 | FY27-P12 | FY27-P12 | FY27-P13 | FY27-P13 | FY27-P13 | FY27-P13 | FY28-P1 | FY28-P1 | FY28-P1 | FY28-P1 | FY28-P2 | FY28-P2 | FY28-P2 | FY28-P2 | FY28-P3 | FY28-P3 | FY28-P3 | FY28-P3 | FY28-P4 | FY28-P4 | FY28-P4 | FY28-P4 | FY28-P5 | FY28-P5 | FY28-P5 | FY28-P5 | FY28-P6 | FY28-P6 | FY28-P6 | FY28-P6 | FY28-P7 | FY28-P7 | FY28-P7 | FY28-P7 | FY28-P8 | FY28-P8 |  | End Date | 2026-02-07 | 2026-03-07 | 2026-04-04 | 2026-05-02 | 2026-05-30 | 2026-06-27 | 2026-07-25 | 2026-08-22 | 2026-09-19 | 2026-10-17 | 2026-11-14 | 2026-12-12 | 2027-01-09 | 2027-02-06 | 2027-03-06 | 2027-04-03 | 2027-05-01 | 2027-05-29 | 2027-06-26 | 2027-07-24 | 2027-08-21 | 2027-09-18 | 2027-10-16 | 2027-11-13 | 2027-12-11 | 2028-01-08 | 34899 | 0
Process or Enabling | Team | Sub-Team | Role Name | Location | Resource Cohort | Offering Portfolio | Offering | Deloitte Level | Blank | Phase / Work Team | Rate Helper (do not delete) | Client Role | Total Fees | Total Hours | Staffing Role | Years of Experience | Staffing Location | Rate Type | Role | Rate Card Level | Year 2 Rates | [96 empty] | FY26-P9 | FY26-P10 | FY26-P11 | FY26-P12 | FY26-P13 | FY27-P1 | FY27-P2 | FY27-P3 | FY27-P4 | FY27-P5 | FY27-P6 | FY27-P7 | FY27-P8 | FY27-P9 | FY27-P10 | FY27-P11 | FY27-P12 | FY27-P13 | FY28-P1 | FY28-P2 | FY28-P3 | FY28-P4 | FY28-P5 | FY28-P6 | FY28-P7 | FY28-P8 | Total | Check | time axis 2026-03-09 to 2027-12-27
Enabling | PMO | PMO | Project Sponsor | US | US Core | Enterprise Performance | SAP | Partner |  | PMO-PMO | Technology-Principal-US-Consulting | PMO - Technology | 0 | 0 | Technology - Principal | 15+ years | Onshore | Consulting | Technology | Principal | 383 | [96 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Enabling | PMO | PMO | Engagement Lead | US | US Core | Enterprise Performance | SAP | Managing Director |  | PMO-PMO | Technology-Managing Director-US-Consulting | PMO - Technology | 38300 | 100 | Technology - Managing Director | 10-15 years | Onshore | Consulting | Technology | Managing Director | 383 | 2026-08-03: 2; 2026-08-10: 2; 2026-08-17: 2; 2026-08-24: 2; 2026-08-31: 2; 2026-09-07: 2; 2026-09-14: 2; 2026-09-21: 2; 2026-09-28: 2; 2026-10-05: 2; 2026-10-12: 2; 2026-10-19: 2; 2026-10-26: 2; 2026-11-02: 2; 2026-11-09: 2; 2026-11-16: 2; 2026-11-23: 2; 2026-11-30: 2; 2026-12-07: 2; 2026-12-14: 2; 2026-12-21: 2; 2026-12-28: 2; 2027-01-04: 2; 2027-01-11: 2; 2027-01-18: 2; 2027-01-25: 2; 2027-02-01: 2; 2027-02-08: 2; 2027-02-15: 2; 2027-02-22: 2; 2027-03-01: 2; 2027-03-08: 2; 2027-03-15: 2; 2027-03-22: 2; 2027-03-29: 2; 2027-04-05: 2; 2027-04-12: 2; 2027-04-19: 2; 2027-04-26: 2; 2027-05-03: 2; 2027-05-10: 2; 2027-05-17: 2; 2027-05-24: 2; 2027-05-31: 2; 2027-06-07: 2; 2027-06-14: 2; 2027-06-21: 2; 2027-06-28: 2; 2027-07-05: 2; 2027-07-12: 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 0
Enabling | PMO | PMO | Malaysia Engagement Lead | Malaysia | US Core | Enterprise Performance | SAP | Managing Director |  | PMO-PMO | Technology-Managing Director-Malaysia-Consulting | PMO - Technology | 0 | 0 | Technology - Managing Director | #N/A | Nearshore | Consulting | Technology | Managing Director | 383 | [96 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Enabling | PMO | PMO | Project Manager | US | US Core | Enterprise Performance | SAP | Sr Manager |  | PMO-PMO | Technology-Senior Manager-US-Consulting | PMO - Technology | 547200 | 1600 | Technology - Senior Manager | 7-10 years | Onshore | Consulting | Technology | Senior Manager | 342 | 2026-08-03: 32; 2026-08-10: 32; 2026-08-17: 32; 2026-08-24: 32; 2026-08-31: 32; 2026-09-07: 32; 2026-09-14: 32; 2026-09-21: 32; 2026-09-28: 32; 2026-10-05: 32; 2026-10-12: 32; 2026-10-19: 32; 2026-10-26: 32; 2026-11-02: 32; 2026-11-09: 32; 2026-11-16: 32; 2026-11-23: 32; 2026-11-30: 32; 2026-12-07: 32; 2026-12-14: 32; 2026-12-21: 32; 2026-12-28: 32; 2027-01-04: 32; 2027-01-11: 32; 2027-01-18: 32; 2027-01-25: 32; 2027-02-01: 32; 2027-02-08: 32; 2027-02-15: 32; 2027-02-22: 32; 2027-03-01: 32; 2027-03-08: 32; 2027-03-15: 32; 2027-03-22: 32; 2027-03-29: 32; 2027-04-05: 32; 2027-04-12: 32; 2027-04-19: 32; 2027-04-26: 32; 2027-05-03: 32; 2027-05-10: 32; 2027-05-17: 32; 2027-05-24: 32; 2027-05-31: 32; 2027-06-07: 32; 2027-06-14: 32; 2027-06-21: 32; 2027-06-28: 32; 2027-07-05: 32; 2027-07-12: 32 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 96 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 96 | 0 | 0 | 0 | 0 | 0 | 0 | 1600 | 0
Enabling | PMO | PMO | Offshore Lead | India | USI | Enterprise Performance | SAP | Managing Director |  | PMO-PMO | Technology-Principal-India-Consulting | PMO - Technology | 36000 | 200 | Technology - Principal | 15+ years | Offshore | Consulting | Technology | Principal | 180 | 2026-08-03: 4; 2026-08-10: 4; 2026-08-17: 4; 2026-08-24: 4; 2026-08-31: 4; 2026-09-07: 4; 2026-09-14: 4; 2026-09-21: 4; 2026-09-28: 4; 2026-10-05: 4; 2026-10-12: 4; 2026-10-19: 4; 2026-10-26: 4; 2026-11-02: 4; 2026-11-09: 4; 2026-11-16: 4; 2026-11-23: 4; 2026-11-30: 4; 2026-12-07: 4; 2026-12-14: 4; 2026-12-21: 4; 2026-12-28: 4; 2027-01-04: 4; 2027-01-11: 4; 2027-01-18: 4; 2027-01-25: 4; 2027-02-01: 4; 2027-02-08: 4; 2027-02-15: 4; 2027-02-22: 4; 2027-03-01: 4; 2027-03-08: 4; 2027-03-15: 4; 2027-03-22: 4; 2027-03-29: 4; 2027-04-05: 4; 2027-04-12: 4; 2027-04-19: 4; 2027-04-26: 4; 2027-05-03: 4; 2027-05-10: 4; 2027-05-17: 4; 2027-05-24: 4; 2027-05-31: 4; 2027-06-07: 4; 2027-06-14: 4; 2027-06-21: 4; 2027-06-28: 4; 2027-07-05: 4; 2027-07-12: 4 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 0
Enabling | PMO | PMO | Offshore GDM | India | USI | Enterprise Performance | SAP | Sr Manager |  | PMO-PMO | Technology-Senior Manager-India-Consulting | PMO - Technology | 214400 | 1600 | Technology - Senior Manager | 7-10 years | Offshore | Consulting | Technology | Senior Manager | 134 | 2026-08-03: 32; 2026-08-10: 32; 2026-08-17: 32; 2026-08-24: 32; 2026-08-31: 32; 2026-09-07: 32; 2026-09-14: 32; 2026-09-21: 32; 2026-09-28: 32; 2026-10-05: 32; 2026-10-12: 32; 2026-10-19: 32; 2026-10-26: 32; 2026-11-02: 32; 2026-11-09: 32; 2026-11-16: 32; 2026-11-23: 32; 2026-11-30: 32; 2026-12-07: 32; 2026-12-14: 32; 2026-12-21: 32; 2026-12-28: 32; 2027-01-04: 32; 2027-01-11: 32; 2027-01-18: 32; 2027-01-25: 32; 2027-02-01: 32; 2027-02-08: 32; 2027-02-15: 32; 2027-02-22: 32; 2027-03-01: 32; 2027-03-08: 32; 2027-03-15: 32; 2027-03-22: 32; 2027-03-29: 32; 2027-04-05: 32; 2027-04-12: 32; 2027-04-19: 32; 2027-04-26: 32; 2027-05-03: 32; 2027-05-10: 32; 2027-05-17: 32; 2027-05-24: 32; 2027-05-31: 32; 2027-06-07: 32; 2027-06-14: 32; 2027-06-21: 32; 2027-06-28: 32; 2027-07-05: 32; 2027-07-12: 32 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 96 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 128 | 96 | 0 | 0 | 0 | 0 | 0 | 0 | 1600 | 0
Enabling | PMO | PMO | PMO Consultant | India | USI | Enterprise Performance | SAP | Jr Staff |  | PMO-PMO | Technology-Consultant-India-Consulting | PMO - Technology | 135000 | 2250 | Technology - Consultant | 1-3 years | Offshore | Consulting | Technology | Consultant | 60 | 2026-08-03: 45; 2026-08-10: 45; 2026-08-17: 45; 2026-08-24: 45; 2026-08-31: 45; 2026-09-07: 45; 2026-09-14: 45; 2026-09-21: 45; 2026-09-28: 45; 2026-10-05: 45; 2026-10-12: 45; 2026-10-19: 45; 2026-10-26: 45; 2026-11-02: 45; 2026-11-09: 45; 2026-11-16: 45; 2026-11-23: 45; 2026-11-30: 45; 2026-12-07: 45; 2026-12-14: 45; 2026-12-21: 45; 2026-12-28: 45; 2027-01-04: 45; 2027-01-11: 45; 2027-01-18: 45; 2027-01-25: 45; 2027-02-01: 45; 2027-02-08: 45; 2027-02-15: 45; 2027-02-22: 45; 2027-03-01: 45; 2027-03-08: 45; 2027-03-15: 45; 2027-03-22: 45; 2027-03-29: 45; 2027-04-05: 45; 2027-04-12: 45; 2027-04-19: 45; 2027-04-26: 45; 2027-05-03: 45; 2027-05-10: 45; 2027-05-17: 45; 2027-05-24: 45; 2027-05-31: 45; 2027-06-07: 45; 2027-06-14: 45; 2027-06-21: 45; 2027-06-28: 45; 2027-07-05: 45; 2027-07-12: 45 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 135 | 0 | 0 | 0 | 0 | 0 | 0 | 2250 | 0
Enabling | Solution Arch | Solution Arch | SAP Solution Architect | US | US Core | Enterprise Performance | SAP | Sr Manager |  | Solution Arch-Solution Arch | Technology-Senior Manager-US-Consulting | Solution Arch - Technology | 0 | 0 | Technology - Senior Manager | 7-10 years | Onshore | Consulting | Technology | Senior Manager | 342 | [96 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Enabling | Solution Arch | Solution Arch | SAP Solution Consultant | India | USI | Enterprise Performance | SAP | Senior Consultant |  | Solution Arch-Solution Arch | Technology-Manager-India-Consulting | Solution Arch - Technology | 222750 | 2250 | Technology - Manager | 5-7 years | Offshore | Consulting | Technology | Manager | 99 | 2026-08-03: 45; 2026-08-10: 45; 2026-08-17: 45; 2026-08-24: 45; 2026-08-31: 45; 2026-09-07: 45; 2026-09-14: 45; 2026-09-21: 45; 2026-09-28: 45; 2026-10-05: 45; 2026-10-12: 45; 2026-10-19: 45; 2026-10-26: 45; 2026-11-02: 45; 2026-11-09: 45; 2026-11-16: 45; 2026-11-23: 45; 2026-11-30: 45; 2026-12-07: 45; 2026-12-14: 45; 2026-12-21: 45; 2026-12-28: 45; 2027-01-04: 45; 2027-01-11: 45; 2027-01-18: 45; 2027-01-25: 45; 2027-02-01: 45; 2027-02-08: 45; 2027-02-15: 45; 2027-02-22: 45; 2027-03-01: 45; 2027-03-08: 45; 2027-03-15: 45; 2027-03-22: 45; 2027-03-29: 45; 2027-04-05: 45; 2027-04-12: 45; 2027-04-19: 45; 2027-04-26: 45; 2027-05-03: 45; 2027-05-10: 45; 2027-05-17: 45; 2027-05-24: 45; 2027-05-31: 45; 2027-06-07: 45; 2027-06-14: 45; 2027-06-21: 45; 2027-06-28: 45; 2027-07-05: 45; 2027-07-12: 45 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 135 | 0 | 0 | 0 | 0 | 0 | 0 | 2250 | 0
Process | OTC | OTC | Order Management | India | USI | Enterprise Performance | SAP | Senior Consultant |  | OTC-OTC | Technology-Senior Consultant-India-Consulting | OTC - Technology | 159750 | 2250 | Technology - Senior Consultant | 3-5 years | Offshore | Consulting | Technology | Senior Consultant | 71 | 2026-08-03: 45; 2026-08-10: 45; 2026-08-17: 45; 2026-08-24: 45; 2026-08-31: 45; 2026-09-07: 45; 2026-09-14: 45; 2026-09-21: 45; 2026-09-28: 45; 2026-10-05: 45; 2026-10-12: 45; 2026-10-19: 45; 2026-10-26: 45; 2026-11-02: 45; 2026-11-09: 45; 2026-11-16: 45; 2026-11-23: 45; 2026-11-30: 45; 2026-12-07: 45; 2026-12-14: 45; 2026-12-21: 45; 2026-12-28: 45; 2027-01-04: 45; 2027-01-11: 45; 2027-01-18: 45; 2027-01-25: 45; 2027-02-01: 45; 2027-02-08: 45; 2027-02-15: 45; 2027-02-22: 45; 2027-03-01: 45; 2027-03-08: 45; 2027-03-15: 45; 2027-03-22: 45; 2027-03-29: 45; 2027-04-05: 45; 2027-04-12: 45; 2027-04-19: 45; 2027-04-26: 45; 2027-05-03: 45; 2027-05-10: 45; 2027-05-17: 45; 2027-05-24: 45; 2027-05-31: 45; 2027-06-07: 45; 2027-06-14: 45; 2027-06-21: 45; 2027-06-28: 45; 2027-07-05: 45; 2027-07-12: 45 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 135 | 0 | 0 | 0 | 0 | 0 | 0 | 2250 | 0
Process | OTC | OTC | Order Management | India | USI | Enterprise Performance | SAP | Consultant |  | OTC-OTC | Technology-Consultant-India-Consulting | OTC - Technology | 0 | 0 | Technology - Consultant | 1-3 years | Offshore | Consulting | Technology | Consultant | 60 | [96 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Process | PTP | PTP Direct | Direct Procurement | India | USI | Enterprise Performance | SAP | Consultant |  | PTP-PTP Direct | Technology-Senior Consultant-India-Consulting | PTP Direct - Technology | 156555 | 2205 | Technology - Senior Consultant | 3-5 years | Offshore | Consulting | Technology | Senior Consultant | 71 | 2026-08-10: 45; 2026-08-17: 45; 2026-08-24: 45; 2026-08-31: 45; 2026-09-07: 45; 2026-09-14: 45; 2026-09-21: 45; 2026-09-28: 45; 2026-10-05: 45; 2026-10-12: 45; 2026-10-19: 45; 2026-10-26: 45; 2026-11-02: 45; 2026-11-09: 45; 2026-11-16: 45; 2026-11-23: 45; 2026-11-30: 45; 2026-12-07: 45; 2026-12-14: 45; 2026-12-21: 45; 2026-12-28: 45; 2027-01-04: 45; 2027-01-11: 45; 2027-01-18: 45; 2027-01-25: 45; 2027-02-01: 45; 2027-02-08: 45; 2027-02-15: 45; 2027-02-22: 45; 2027-03-01: 45; 2027-03-08: 45; 2027-03-15: 45; 2027-03-22: 45; 2027-03-29: 45; 2027-04-05: 45; 2027-04-12: 45; 2027-04-19: 45; 2027-04-26: 45; 2027-05-03: 45; 2027-05-10: 45; 2027-05-17: 45; 2027-05-24: 45; 2027-05-31: 45; 2027-06-07: 45; 2027-06-14: 45; 2027-06-21: 45; 2027-06-28: 45; 2027-07-05: 45; 2027-07-12: 45 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 135 | 0 | 0 | 0 | 0 | 0 | 0 | 2205 | 0
Process | PTP | PTP Direct | Direct Procurement | India | USI | Enterprise Performance | SAP | Consultant |  | PTP-PTP Direct | Technology-Consultant-India-Consulting | PTP Direct - Technology | 116100 | 1935 | Technology - Consultant | 1-3 years | Offshore | Consulting | Technology | Consultant | 60 | 2026-09-21: 45; 2026-09-28: 45; 2026-10-05: 45; 2026-10-12: 45; 2026-10-19: 45; 2026-10-26: 45; 2026-11-02: 45; 2026-11-09: 45; 2026-11-16: 45; 2026-11-23: 45; 2026-11-30: 45; 2026-12-07: 45; 2026-12-14: 45; 2026-12-21: 45; 2026-12-28: 45; 2027-01-04: 45; 2027-01-11: 45; 2027-01-18: 45; 2027-01-25: 45; 2027-02-01: 45; 2027-02-08: 45; 2027-02-15: 45; 2027-02-22: 45; 2027-03-01: 45; 2027-03-08: 45; 2027-03-15: 45; 2027-03-22: 45; 2027-03-29: 45; 2027-04-05: 45; 2027-04-12: 45; 2027-04-19: 45; 2027-04-26: 45; 2027-05-03: 45; 2027-05-10: 45; 2027-05-17: 45; 2027-05-24: 45; 2027-05-31: 45; 2027-06-07: 45; 2027-06-14: 45; 2027-06-21: 45; 2027-06-28: 45; 2027-07-05: 45; 2027-07-12: 45 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 135 | 0 | 0 | 0 | 0 | 0 | 0 | 1935 | 0
Process | PTD | Manufacturing | PTD Lead | India | USI | Enterprise Performance | SAP | Manager |  | PTD-Manufacturing | Technology-Manager-India-Consulting | Manufacturing - Technology | 198000 | 2000 | Technology - Manager | 5-7 years | Offshore | Consulting | Technology | Manager | 99 | 2026-08-03: 40; 2026-08-10: 40; 2026-08-17: 40; 2026-08-24: 40; 2026-08-31: 40; 2026-09-07: 40; 2026-09-14: 40; 2026-09-21: 40; 2026-09-28: 40; 2026-10-05: 40; 2026-10-12: 40; 2026-10-19: 40; 2026-10-26: 40; 2026-11-02: 40; 2026-11-09: 40; 2026-11-16: 40; 2026-11-23: 40; 2026-11-30: 40; 2026-12-07: 40; 2026-12-14: 40; 2026-12-21: 40; 2026-12-28: 40; 2027-01-04: 40; 2027-01-11: 40; 2027-01-18: 40; 2027-01-25: 40; 2027-02-01: 40; 2027-02-08: 40; 2027-02-15: 40; 2027-02-22: 40; 2027-03-01: 40; 2027-03-08: 40; 2027-03-15: 40; 2027-03-22: 40; 2027-03-29: 40; 2027-04-05: 40; 2027-04-12: 40; 2027-04-19: 40; 2027-04-26: 40; 2027-05-03: 40; 2027-05-10: 40; 2027-05-17: 40; 2027-05-24: 40; 2027-05-31: 40; 2027-06-07: 40; 2027-06-14: 40; 2027-06-21: 40; 2027-06-28: 40; 2027-07-05: 40; 2027-07-12: 40 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 0
Process | PTD | Manufacturing | Planning / APO | India | USI | Enterprise Performance | SAP | Sr Consultant |  | PTD-Manufacturing | Technology-Senior Consultant-India-Consulting | Manufacturing - Technology | 159750 | 2250 |  |  |  | Consulting | Technology | Senior Consultant | 71 | 2026-08-03: 45; 2026-08-10: 45; 2026-08-17: 45; 2026-08-24: 45; 2026-08-31: 45; 2026-09-07: 45; 2026-09-14: 45; 2026-09-21: 45; 2026-09-28: 45; 2026-10-05: 45; 2026-10-12: 45; 2026-10-19: 45; 2026-10-26: 45; 2026-11-02: 45; 2026-11-09: 45; 2026-11-16: 45; 2026-11-23: 45; 2026-11-30: 45; 2026-12-07: 45; 2026-12-14: 45; 2026-12-21: 45; 2026-12-28: 45; 2027-01-04: 45; 2027-01-11: 45; 2027-01-18: 45; 2027-01-25: 45; 2027-02-01: 45; 2027-02-08: 45; 2027-02-15: 45; 2027-02-22: 45; 2027-03-01: 45; 2027-03-08: 45; 2027-03-15: 45; 2027-03-22: 45; 2027-03-29: 45; 2027-04-05: 45; 2027-04-12: 45; 2027-04-19: 45; 2027-04-26: 45; 2027-05-03: 45; 2027-05-10: 45; 2027-05-17: 45; 2027-05-24: 45; 2027-05-31: 45; 2027-06-07: 45; 2027-06-14: 45; 2027-06-21: 45; 2027-06-28: 45; 2027-07-05: 45; 2027-07-12: 45 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 135 | 0 | 0 | 0 | 0 | 0 | 0 | 2250 | 0
Process | PTD | Manufacturing | PP/QM | India | USI | Enterprise Performance | SAP | Consultant |  | PTD-Manufacturing | Technology-Consultant-India-Consulting | Manufacturing - Technology | 0 | 0 |  |  |  | Consulting | Technology | Consultant | 60 | [96 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Process | PTD | Manufacturing | PP/QM | India | USI | Enterprise Performance | SAP | Sr Consultant |  | PTD-Manufacturing | Technology-Senior Consultant-India-Consulting | Manufacturing - Technology | 146970 | 2070 |  |  |  | Consulting | Technology | Senior Consultant | 71 | 2026-08-31: 45; 2026-09-07: 45; 2026-09-14: 45; 2026-09-21: 45; 2026-09-28: 45; 2026-10-05: 45; 2026-10-12: 45; 2026-10-19: 45; 2026-10-26: 45; 2026-11-02: 45; 2026-11-09: 45; 2026-11-16: 45; 2026-11-23: 45; 2026-11-30: 45; 2026-12-07: 45; 2026-12-14: 45; 2026-12-21: 45; 2026-12-28: 45; 2027-01-04: 45; 2027-01-11: 45; 2027-01-18: 45; 2027-01-25: 45; 2027-02-01: 45; 2027-02-08: 45; 2027-02-15: 45; 2027-02-22: 45; 2027-03-01: 45; 2027-03-08: 45; 2027-03-15: 45; 2027-03-22: 45; 2027-03-29: 45; 2027-04-05: 45; 2027-04-12: 45; 2027-04-19: 45; 2027-04-26: 45; 2027-05-03: 45; 2027-05-10: 45; 2027-05-17: 45; 2027-05-24: 45; 2027-05-31: 45; 2027-06-07: 45; 2027-06-14: 45; 2027-06-21: 45; 2027-06-28: 45; 2027-07-05: 45; 2027-07-12: 45 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 135 | 0 | 0 | 0 | 0 | 0 | 0 | 2070 | 0
Process | PTD | Logistics / Warehouse | MM/IM | India | USI | Enterprise Performance | SAP | Consultant |  | PTD-Logistics / Warehouse | Technology-Consultant-India-Consulting | Logistics / Warehouse - Technology | 124200 | 2070 |  |  |  | Consulting | Technology | Consultant | 60 | 2026-08-31: 45; 2026-09-07: 45; 2026-09-14: 45; 2026-09-21: 45; 2026-09-28: 45; 2026-10-05: 45; 2026-10-12: 45; 2026-10-19: 45; 2026-10-26: 45; 2026-11-02: 45; 2026-11-09: 45; 2026-11-16: 45; 2026-11-23: 45; 2026-11-30: 45; 2026-12-07: 45; 2026-12-14: 45; 2026-12-21: 45; 2026-12-28: 45; 2027-01-04: 45; 2027-01-11: 45; 2027-01-18: 45; 2027-01-25: 45; 2027-02-01: 45; 2027-02-08: 45; 2027-02-15: 45; 2027-02-22: 45; 2027-03-01: 45; 2027-03-08: 45; 2027-03-15: 45; 2027-03-22: 45; 2027-03-29: 45; 2027-04-05: 45; 2027-04-12: 45; 2027-04-19: 45; 2027-04-26: 45; 2027-05-03: 45; 2027-05-10: 45; 2027-05-17: 45; 2027-05-24: 45; 2027-05-31: 45; 2027-06-07: 45; 2027-06-14: 45; 2027-06-21: 45; 2027-06-28: 45; 2027-07-05: 45; 2027-07-12: 45 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 135 | 0 | 0 | 0 | 0 | 0 | 0 | 2070 | 0
Enabling | Development | Development | Development Lead | India | USI | Enterprise Performance | SAP | Sr Consultant |  | Development-Development | Solution Architect-Lead-India-Technology | Development - Solution Architect | 111600 | 1800 | Solution Architect - Lead | 9-12 years | Offshore | Technology | Solution Architect | Lead | 62 | 2026-09-21: 45; 2026-09-28: 45; 2026-10-05: 45; 2026-10-12: 45; 2026-10-19: 45; 2026-10-26: 45; 2026-11-02: 45; 2026-11-09: 45; 2026-11-16: 45; 2026-11-23: 45; 2026-11-30: 45; 2026-12-07: 45; 2026-12-14: 45; 2026-12-21: 45; 2026-12-28: 45; 2027-01-04: 45; 2027-01-11: 45; 2027-01-18: 45; 2027-01-25: 45; 2027-02-01: 45; 2027-02-08: 45; 2027-02-15: 45; 2027-02-22: 45; 2027-03-01: 45; 2027-03-08: 45; 2027-03-15: 45; 2027-03-22: 45; 2027-03-29: 45; 2027-04-05: 45; 2027-04-12: 45; 2027-04-19: 45; 2027-04-26: 45; 2027-05-03: 45; 2027-05-10: 45; 2027-05-17: 45; 2027-05-24: 45; 2027-05-31: 45; 2027-06-07: 45; 2027-06-14: 45; 2027-06-21: 45 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 0
Enabling | Development | Development | ABAP Developer | India | USI | Enterprise Performance | SAP | Consultant |  | Development-Development | Systems Implementation Consultant-Senior-India-Technology | Development - Systems Implementation Consultant | 73440 | 1530 | Systems Implementation Consultant - Senior | 6-9 years | Offshore | Technology | Systems Implementation Consultant | Senior | 48 | 2026-10-19: 45; 2026-10-26: 45; 2026-11-02: 45; 2026-11-09: 45; 2026-11-16: 45; 2026-11-23: 45; 2026-11-30: 45; 2026-12-07: 45; 2026-12-14: 45; 2026-12-21: 45; 2026-12-28: 45; 2027-01-04: 45; 2027-01-11: 45; 2027-01-18: 45; 2027-01-25: 45; 2027-02-01: 45; 2027-02-08: 45; 2027-02-15: 45; 2027-02-22: 45; 2027-03-01: 45; 2027-03-08: 45; 2027-03-15: 45; 2027-03-22: 45; 2027-03-29: 45; 2027-04-05: 45; 2027-04-12: 45; 2027-04-19: 45; 2027-04-26: 45; 2027-05-03: 45; 2027-05-10: 45; 2027-05-17: 45; 2027-05-24: 45; 2027-05-31: 45; 2027-06-07: 45 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 90 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1530 | 0
Enabling | Data | Data | Data Consultant | India | USI | Enterprise Performance | SAP | Senior Manager |  | Data-Data | Data Integration Architect-Senior-India-Technology | Data - Data Integration Architect | 85260 | 1740 | Data Integration Architect - Senior | 6-9 years | Offshore | Technology | Data Integration Architect | Senior | 49 | 2026-10-05: 45; 2026-10-12: 45; 2026-10-19: 45; 2026-10-26: 45; 2026-11-02: 45; 2026-11-09: 45; 2026-11-16: 45; 2026-11-23: 45; 2026-11-30: 45; 2026-12-07: 45; 2026-12-14: 45; 2026-12-21: 45; 2026-12-28: 45; 2027-01-04: 45; 2027-01-11: 45; 2027-01-18: 45; 2027-01-25: 45; 2027-02-01: 45; 2027-02-08: 45; 2027-02-15: 45; 2027-02-22: 45; 2027-03-01: 45; 2027-03-08: 45; 2027-03-15: 45; 2027-03-22: 45; 2027-03-29: 45; 2027-04-05: 45; 2027-04-12: 45; 2027-04-19: 45; 2027-04-26: 45; 2027-05-03: 45; 2027-05-10: 45; 2027-05-17: 45; 2027-05-24: 45; 2027-05-31: 45; 2027-06-07: 45; 2027-06-14: 24; 2027-06-21: 24; 2027-06-28: 24; 2027-07-05: 24; 2027-07-12: 24 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 138 | 72 | 0 | 0 | 0 | 0 | 0 | 0 | 1740 | 0
Enabling | Data | Data | Data Consultant | India | USI | Enterprise Performance | SAP | Manager |  | Data-Data | Data Integration Architect-Senior-India-Technology | Data - Data Integration Architect | 85260 | 1740 | Data Integration Architect - Senior | 6-9 years | Offshore | Technology | Data Integration Architect | Senior | 49 | 2026-10-05: 45; 2026-10-12: 45; 2026-10-19: 45; 2026-10-26: 45; 2026-11-02: 45; 2026-11-09: 45; 2026-11-16: 45; 2026-11-23: 45; 2026-11-30: 45; 2026-12-07: 45; 2026-12-14: 45; 2026-12-21: 45; 2026-12-28: 45; 2027-01-04: 45; 2027-01-11: 45; 2027-01-18: 45; 2027-01-25: 45; 2027-02-01: 45; 2027-02-08: 45; 2027-02-15: 45; 2027-02-22: 45; 2027-03-01: 45; 2027-03-08: 45; 2027-03-15: 45; 2027-03-22: 45; 2027-03-29: 45; 2027-04-05: 45; 2027-04-12: 45; 2027-04-19: 45; 2027-04-26: 45; 2027-05-03: 45; 2027-05-10: 45; 2027-05-17: 45; 2027-05-24: 45; 2027-05-31: 45; 2027-06-07: 45; 2027-06-14: 24; 2027-06-21: 24; 2027-06-28: 24; 2027-07-05: 24; 2027-07-12: 24 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 138 | 72 | 0 | 0 | 0 | 0 | 0 | 0 | 1740 | 0
Enabling | Data | Data | Data Lead | India | USI | Enterprise Performance | SAP | Sr Consultant |  | Data-Data | Data Integration Architect-Lead-India-Technology | Data - Data Integration Architect | 35360 | 680 | Data Integration Architect - Lead | 9-12 years | Offshore | Technology | Data Integration Architect | Lead | 52 | 2026-10-19: 20; 2026-10-26: 20; 2026-11-02: 20; 2026-11-09: 20; 2026-11-16: 20; 2026-11-23: 20; 2026-11-30: 20; 2026-12-07: 20; 2026-12-14: 20; 2026-12-21: 20; 2026-12-28: 20; 2027-01-04: 20; 2027-01-11: 20; 2027-01-18: 20; 2027-01-25: 20; 2027-02-01: 20; 2027-02-08: 20; 2027-02-15: 20; 2027-02-22: 20; 2027-03-01: 20; 2027-03-08: 20; 2027-03-15: 20; 2027-03-22: 20; 2027-03-29: 20; 2027-04-05: 20; 2027-04-12: 20; 2027-04-19: 20; 2027-04-26: 20; 2027-05-03: 20; 2027-05-10: 20; 2027-05-17: 20; 2027-05-24: 20; 2027-05-31: 20; 2027-06-07: 20 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 680 | 0
Enabling | Security | Security | Engagement Lead | US | US Core | Cyber | Enterprise Security | Managing Director |  | Security-Security | Cyber Security -Managing Director-US-Consulting | Security - Cyber Security | 0 | 0 | Cyber Security - Managing Director |  | Onshore | Consulting | Cyber Security | Managing Director | 437 | [96 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Enabling | Security | Security | Security Lead | India | USI | Cyber | Enterprise Security | Manager |  | Security-Security | Cyber Security -Manager-India-Consulting | Security - Cyber Security | 13462 | 106 | Cyber Security - Manager |  | Offshore | Consulting | Cyber Security | Manager | 127 | 2026-08-31: 4; 2026-09-07: 4; 2026-09-14: 4; 2026-09-21: 4; 2026-09-28: 4; 2026-10-05: 4; 2026-10-12: 4; 2026-10-19: 2; 2026-10-26: 2; 2026-11-02: 2; 2026-11-09: 2; 2026-11-16: 2; 2026-11-23: 2; 2026-11-30: 2; 2026-12-07: 2; 2026-12-14: 2; 2026-12-21: 2; 2026-12-28: 2; 2027-01-04: 2; 2027-01-11: 2; 2027-01-18: 2; 2027-01-25: 2; 2027-02-01: 2; 2027-02-08: 2; 2027-02-15: 2; 2027-02-22: 2; 2027-03-01: 2; 2027-03-08: 2; 2027-03-15: 2; 2027-03-22: 2; 2027-03-29: 2; 2027-04-05: 2; 2027-04-12: 2; 2027-04-19: 2; 2027-04-26: 2; 2027-05-03: 2; 2027-05-10: 2; 2027-05-17: 2; 2027-05-24: 2; 2027-05-31: 2; 2027-06-07: 2; 2027-06-14: 2; 2027-06-21: 2; 2027-06-28: 2; 2027-07-05: 2; 2027-07-12: 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 16 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 106 | 0
Enabling | Security | Security | Security Consultant | India | USI | Cyber | Enterprise Security | Sr Consultant |  | Security-Security | Cyber Security -Senior Consultant-India-Consulting | Security - Cyber Security | 215280 | 2070 | Cyber Security - Senior Consultant |  | Offshore | Consulting | Cyber Security | Senior Consultant | 104 | 2026-08-31: 45; 2026-09-07: 45; 2026-09-14: 45; 2026-09-21: 45; 2026-09-28: 45; 2026-10-05: 45; 2026-10-12: 45; 2026-10-19: 45; 2026-10-26: 45; 2026-11-02: 45; 2026-11-09: 45; 2026-11-16: 45; 2026-11-23: 45; 2026-11-30: 45; 2026-12-07: 45; 2026-12-14: 45; 2026-12-21: 45; 2026-12-28: 45; 2027-01-04: 45; 2027-01-11: 45; 2027-01-18: 45; 2027-01-25: 45; 2027-02-01: 45; 2027-02-08: 45; 2027-02-15: 45; 2027-02-22: 45; 2027-03-01: 45; 2027-03-08: 45; 2027-03-15: 45; 2027-03-22: 45; 2027-03-29: 45; 2027-04-05: 45; 2027-04-12: 45; 2027-04-19: 45; 2027-04-26: 45; 2027-05-03: 45; 2027-05-10: 45; 2027-05-17: 45; 2027-05-24: 45; 2027-05-31: 45; 2027-06-07: 45; 2027-06-14: 45; 2027-06-21: 45; 2027-06-28: 45; 2027-07-05: 45; 2027-07-12: 45 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 135 | 0 | 0 | 0 | 0 | 0 | 0 | 2070 | 0
Enabling | Security | Security | Project Manager | India | USI | Cyber | Enterprise Security | Sr Manager |  | Security-Security | Cyber Security -Senior Manager-India-Consulting | Security - Cyber Security | 7452 | 46 |  |  | Offshore | Consulting | Cyber Security | Senior Manager | 162 | [96 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 46 | 0 | bar: 2026-08-31 to 2027-07-12
Enabling | OCM | OCM | OCM Executive | US | US Core | Human Capital | OWC | Managing Director |  | OCM-OCM | Human Capital-Managing Director-US-Consulting | OCM - Human Capital | 1952 | 4 |  |  |  | Consulting | Human Capital | Managing Director | 488 | [96 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | bar: 2027-04-05; 2027-04-26; 2027-05-17; 2027-06-07
Enabling | OCM | OCM | OCM SME | US | US Core | Human Capital | OWC | Sr Manager |  | OCM-OCM | Human Capital-Senior Manager-US-Consulting | OCM - Human Capital | 29448 | 72 |  |  |  | Consulting | Human Capital | Senior Manager | 409 | 2027-04-05: 6; 2027-04-12: 6; 2027-04-19: 6; 2027-04-26: 6; 2027-05-03: 6; 2027-05-10: 6; 2027-05-17: 6; 2027-05-24: 6; 2027-05-31: 6; 2027-06-07: 6; 2027-06-14: 6; 2027-06-21: 6 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 24 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72 | 0
Enabling | OCM | OCM | OCM Lead | US | US Core | Human Capital | OWC | Sr Consultant |  | OCM-OCM | Human Capital-Senior Consultant-US-Consulting | OCM - Human Capital | 88020 | 270 |  |  |  | Consulting | Human Capital | Senior Consultant | 326 | 2027-04-05: 45; 2027-04-12: 45; 2027-04-19: 45; 2027-04-26: 45; 2027-05-03: 45; 2027-05-10: 45 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180 | 90 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 270 | 0
Enabling | OCM | OCM | OCM Support | India | USI | Human Capital | OWC | Consultant |  | OCM-OCM | Human Capital-Consultant-India-Consulting | OCM - Human Capital | 54450 | 450 |  |  |  | Consulting | Human Capital | Consultant | 121 | 2027-04-19: 45; 2027-04-26: 45; 2027-05-03: 45; 2027-05-10: 45; 2027-05-17: 45; 2027-05-24: 45; 2027-05-31: 45; 2027-06-07: 45; 2027-06-14: 45; 2027-06-21: 45 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 180 | 180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 450 | 0
Process | GTS | GTS | Quality Review | US | Tax | Tax | Tax Technology Consulting | Partner |  | GTS-GTS | Tax Advisory-Principal/Partner/ Managing Director-US-Tax | GTS - Tax Advisory | #VALUE! | 9 | Tax Advisory - Principal/Partner/ Managing Director | #N/A | Onshore | Tax | Tax Advisory | Principal/Partner/ Managing Director | combination not found | [96 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | bar: 2026-10-26; 2026-11-30; 2026-12-28; 2027-01-25; 2027-02-22; 2027-03-29; 2027-04-26; 2027-05-31; 2027-06-28
Process | GTS | GTS | Workstream Lead | US | Tax | Tax | Tax Technology Consulting | Sr Manager |  | GTS-GTS | Tax Advisory-Senior Manager-US-Tax | GTS - Tax Advisory | 14000 | 28 | Tax Advisory - Senior Manager | #N/A | Onshore | Tax | Tax Advisory | Senior Manager | 500 | [96 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 4 | 4 | 4 | 3 | 2 | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | bar: 2026-10-05 to 2027-01-25; 2027-02-15 to 2027-02-22; 2027-03-22 to 2027-03-29; 2027-04-19 to 2027-04-26; 2027-05-17 to 2027-05-31; 2027-06-21 to 2027-06-28
Process | GTS | GTS | GTA Regulatory | US | Tax | Tax | Tax Technology Consulting | Manager |  | GTS-GTS | Tax Advisory-Manager-US-Tax | GTS - Tax Advisory | 16060 | 44 | Tax Advisory - Manager | #N/A | Onshore | Tax | Tax Advisory | Manager | 365 | 2026-10-05: 2; 2026-10-12: 2; 2026-10-19: 2; 2026-11-02: 2; 2026-11-09: 2; 2026-11-16: 2; 2026-11-23: 2; 2026-12-07: 2; 2026-12-14: 2; 2026-12-21: 2; 2027-01-11: 2; 2027-01-18: 2; 2027-02-15: 2; 2027-02-22: 2; 2027-03-22: 2; 2027-03-29: 2; 2027-04-19: 2; 2027-04-26: 2; 2027-05-24: 2; 2027-05-31: 2; 2027-06-21: 2; 2027-06-28: 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 6 | 6 | 4 | 4 | 4 | 4 | 4 | 2 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 0
Process | GTS | GTS | USI Consultant - Compliance | India | Tax | Tax | Tax Technology Consulting | Consultant |  | GTS-GTS | Tax Advisory-Senior Consultant-India-Tax | GTS - Tax Advisory | 275400 | 1530 | Tax Advisory - Senior Consultant | #N/A | Offshore | Tax | Tax Advisory | Senior Consultant | 180 | 2026-10-05: 45; 2026-10-12: 45; 2026-10-19: 45; 2026-10-26: 45; 2026-11-02: 45; 2026-11-09: 45; 2026-11-16: 45; 2026-11-23: 45; 2026-11-30: 45; 2026-12-07: 45; 2026-12-14: 45; 2026-12-21: 45; 2026-12-28: 45; 2027-01-04: 45; 2027-01-11: 45; 2027-01-18: 45; 2027-01-25: 45; 2027-02-01: 45; 2027-02-08: 45; 2027-02-15: 45; 2027-02-22: 45; 2027-03-01: 45; 2027-03-08: 45; 2027-03-15: 45; 2027-03-22: 30; 2027-03-29: 30; 2027-04-05: 30; 2027-04-12: 30; 2027-04-19: 30; 2027-04-26: 30; 2027-05-03: 30; 2027-05-10: 30; 2027-05-17: 30; 2027-05-24: 30; 2027-05-31: 30; 2027-06-07: 30; 2027-06-14: 30; 2027-06-21: 30; 2027-06-28: 30 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 180 | 180 | 180 | 180 | 180 | 150 | 120 | 120 | 120 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 1530 | 0
Enabling | Snowflake | Snowflake | Engagement Lead | US | US Core | AI & Engineering | AI & Data | Principal |  | Snowflake-Snowflake | Technology-Principal-US-Consulting | Snowflake - Technology | 5745 | 15 |  |  | Onshore | Consulting | Technology | Principal | 383 | 2027-01-04: 1; 2027-01-11: 0; 2027-01-18: 1; 2027-01-25: 0; 2027-02-01: 1; 2027-02-08: 0; 2027-02-15: 1; 2027-02-22: 0; 2027-03-01: 1; 2027-03-08: 0; 2027-03-15: 1; 2027-03-22: 0; 2027-03-29: 1; 2027-04-05: 0; 2027-04-12: 1; 2027-04-19: 0; 2027-04-26: 1; 2027-05-03: 0; 2027-05-10: 1; 2027-05-17: 0; 2027-05-24: 1; 2027-05-31: 0; 2027-06-07: 1; 2027-06-14: 0; 2027-06-21: 1; 2027-06-28: 0; 2027-07-05: 1; 2027-07-12: 0; 2027-07-19: 1
Enabling | Snowflake | Snowflake | Project Lead | US | US Core | AI & Engineering | AI & Data | Sr Manager |  | Snowflake-Snowflake | Technology-Senior Manager-US-Consulting | Snowflake - Technology | 0 | 0 |  |  |  | Consulting | Technology | Senior Manager | 342 | 2027-01-04: 0; 2027-01-11: 0; 2027-01-18: 0; 2027-01-25: 0; 2027-02-01: 0; 2027-02-08: 0; 2027-02-15: 0; 2027-02-22: 0; 2027-03-01: 0; 2027-03-08: 0; 2027-03-15: 0; 2027-03-22: 0; 2027-03-29: 0; 2027-04-05: 0; 2027-04-12: 0; 2027-04-19: 0; 2027-04-26: 0; 2027-05-03: 0; 2027-05-10: 0; 2027-05-17: 0; 2027-05-24: 0; 2027-05-31: 0; 2027-06-07: 0; 2027-06-14: 0; 2027-06-21: 0; 2027-06-28: 0; 2027-07-05: 0; 2027-07-12: 0; 2027-07-19: 0
Enabling | Snowflake | Snowflake | Reporting & Data Lead | US | US Core | AI & Engineering | AI & Data | Manager |  | Snowflake-Snowflake | Technology-Manager-US-Consulting | Snowflake - Technology | 96390 | 315 |  |  |  | Consulting | Technology | Manager | 306 | 2027-01-04: 45; 2027-01-11: 45; 2027-01-18: 45; 2027-01-25: 45; 2027-02-01: 45; 2027-02-08: 45; 2027-02-15: 45; 2027-02-22: 0; 2027-03-01: 0; 2027-03-08: 0; 2027-03-15: 0; 2027-03-22: 0; 2027-03-29: 0; 2027-04-05: 0; 2027-04-12: 0; 2027-04-19: 0; 2027-04-26: 0; 2027-05-03: 0; 2027-05-10: 0; 2027-05-17: 0; 2027-05-24: 0; 2027-05-31: 0; 2027-06-07: 0; 2027-06-14: 0; 2027-06-21: 0; 2027-06-28: 0; 2027-07-05: 0; 2027-07-12: 0
Enabling | Snowflake | Snowflake | Reporting Engineer | US | US Core | AI & Engineering | AI & Data | Analyst |  | Snowflake-Snowflake | Developer/Coder-Junior-US-Technology | Snowflake - Developer/Coder | 0 | 0 |  |  |  | Technology | Developer/Coder | Junior | 108 | 2027-01-04: 0; 2027-01-11: 0; 2027-01-18: 0; 2027-01-25: 0; 2027-02-01: 0; 2027-02-08: 0; 2027-02-15: 0; 2027-02-22: 0; 2027-03-01: 0; 2027-03-08: 0; 2027-03-15: 0; 2027-03-22: 0; 2027-03-29: 0; 2027-04-05: 0; 2027-04-12: 0; 2027-04-19: 0; 2027-04-26: 0; 2027-05-03: 0; 2027-05-10: 0; 2027-05-17: 0; 2027-05-24: 0; 2027-05-31: 0; 2027-06-07: 0; 2027-06-14: 0; 2027-06-21: 0; 2027-06-28: 0; 2027-07-05: 0; 2027-07-12: 0
Enabling | Snowflake | Snowflake | Offshore Lead | India | USI | AI & Engineering | AI & Data | Manager |  | Snowflake-Snowflake | Developer/Coder-Lead-India-Technology | Snowflake - Developer/Coder | 9828 | 234 |  |  |  | Technology | Developer/Coder | Lead | 42 | 2027-01-11: 9; 2027-01-18: 9; 2027-01-25: 9; 2027-02-01: 9; 2027-02-08: 9; 2027-02-15: 9; 2027-02-22: 9; 2027-03-01: 9; 2027-03-08: 9; 2027-03-15: 9; 2027-03-22: 9; 2027-03-29: 9; 2027-04-05: 9; 2027-04-12: 9; 2027-04-19: 9; 2027-04-26: 9; 2027-05-03: 9; 2027-05-10: 9; 2027-05-17: 9; 2027-05-24: 9; 2027-05-31: 9; 2027-06-07: 9; 2027-06-14: 9; 2027-06-21: 9; 2027-06-28: 9; 2027-07-05: 9
Enabling | Snowflake | Snowflake | Reporting Engineer | India | USI | AI & Engineering | AI & Data | Sr Consultant |  | Snowflake-Snowflake | Developer/Coder-Senior-India-Technology | Snowflake - Developer/Coder | 46620 | 1260 |  |  |  | Technology | Developer/Coder | Senior | 37 | 2027-01-04: 45; 2027-01-11: 45; 2027-01-18: 45; 2027-01-25: 45; 2027-02-01: 45; 2027-02-08: 45; 2027-02-15: 45; 2027-02-22: 45; 2027-03-01: 45; 2027-03-08: 45; 2027-03-15: 45; 2027-03-22: 45; 2027-03-29: 45; 2027-04-05: 45; 2027-04-12: 45; 2027-04-19: 45; 2027-04-26: 45; 2027-05-03: 45; 2027-05-10: 45; 2027-05-17: 45; 2027-05-24: 45; 2027-05-31: 45; 2027-06-07: 45; 2027-06-14: 45; 2027-06-21: 45; 2027-06-28: 45; 2027-07-05: 45; 2027-07-12: 45
Enabling | Snowflake | Snowflake | Reporting Engineer | India | USI | AI & Engineering | AI & Data | Consultant |  | Snowflake-Snowflake | Developer/Coder-Intermediate-India-Technology | Snowflake - Developer/Coder | 41760 | 1305 |  |  |  | Technology | Developer/Coder | Intermediate | 32 | 2027-01-04: 45; 2027-01-11: 45; 2027-01-18: 45; 2027-01-25: 45; 2027-02-01: 45; 2027-02-08: 45; 2027-02-15: 45; 2027-02-22: 45; 2027-03-01: 45; 2027-03-08: 45; 2027-03-15: 45; 2027-03-22: 45; 2027-03-29: 45; 2027-04-05: 45; 2027-04-12: 45; 2027-04-19: 45; 2027-04-26: 45; 2027-05-03: 45; 2027-05-10: 45; 2027-05-17: 45; 2027-05-24: 45; 2027-05-31: 45; 2027-06-07: 45; 2027-06-14: 45; 2027-06-21: 45; 2027-06-28: 45; 2027-07-05: 45; 2027-07-12: 45; 2027-07-19: 45
Enabling | Snowflake | Snowflake | Data Engineer | India | USI | AI & Engineering | AI & Data | Consultant |  | Snowflake-Snowflake | Developer/Coder-Intermediate-India-Technology | Snowflake - Developer/Coder | 0 | 0 |  |  |  | Technology | Developer/Coder | Intermediate | 32 | 2027-02-15: 0; 2027-02-22: 0; 2027-03-01: 0; 2027-03-08: 0; 2027-03-15: 0; 2027-03-22: 0; 2027-03-29: 0; 2027-04-05: 0; 2027-04-12: 0; 2027-04-19: 0; 2027-04-26: 0; 2027-05-03: 0; 2027-05-10: 0
Enabling | Snowflake | Snowflake | Reporting Engineer | India | USI | AI & Engineering | AI & Data | Analyst |  | Snowflake-Snowflake | Developer/Coder-Junior-India-Technology | Snowflake - Developer/Coder | 25875 | 1035 |  |  |  | Technology | Developer/Coder | Junior | 25 | 2027-02-15: 45; 2027-02-22: 45; 2027-03-01: 45; 2027-03-08: 45; 2027-03-15: 45; 2027-03-22: 45; 2027-03-29: 45; 2027-04-05: 45; 2027-04-12: 45; 2027-04-19: 45; 2027-04-26: 45; 2027-05-03: 45; 2027-05-10: 45; 2027-05-17: 45; 2027-05-24: 45; 2027-05-31: 45; 2027-06-07: 45; 2027-06-14: 45; 2027-06-21: 45; 2027-06-28: 45; 2027-07-05: 45; 2027-07-12: 45; 2027-07-19: 45
[10 empty] | - | --- | - | [8 empty] | 0 | [96 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0%
[22 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 290 | 335 | 335 | 335 | 425 | 425 | 425 | 515 | 515 | 605 | 605 | 670 | 670 | 670 | 670 | 670 | 670 | 670 | 670 | 670 | 670 | 670 | #REF! | #REF! | #REF! | #REF! | 670 | 670 | 670 | 670 | 670 | 670 | 670 | 670 | 670 | 670 | 670 | 670 | 670 | 670 | 670 | 670 | 670 | 670 | 670 | 670 | 670 | 670 | 670 | 563 | 563 | 518 | 518 | 518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 960 | 1610 | 2240 | 2680 | 2680 | 2680 | 2680 | 2680 | 2680 | 2680 | 2680 | 2466 | 1554 | 0 | 0 | 0 | 0 | 0 | 0 | 30270
[22 empty] | 30270 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 290 | 335 | 335 | 335 | 425 | 425 | 425 | 515 | 515 | 605 | 605 | 670 | 670 | 670 | 670 | 670 | 670 | 670 | 670 | 670 | 670 | 670 | #REF! | #REF! | #REF! | #REF! | 670 | 670 | 670 | 670 | 670 | 670 | 670 | 670 | 670 | 670 | 670 | 670 | 670 | 670 | 670 | 670 | 670 | 670 | 670 | 670 | 670 | 670 | 670 | 563 | 563 | 518 | 518 | 518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109059 | 167357 | 204032 | 225652 | 225652 | 225652 | 225652 | 225652 | 225652 | 225652 | 225652 | 215136 | 145095 | 0 | 0 | 0 | 0 | 0 | 0 | 2645895