## Slide 1
SA Readout Summary – Project 2
Solution Complexity |  | Other Offerings | 
Deployment Timeline |  | Staffing & Resource | 
Solution Complexity |  | 
Solution Scope |  | The current proposal is to migrate Project 2 existing ECC solution to S4 Solution scope in the response includes Finance, Customer Sales and Service, Warehouse and Logistics, Procurement, Service Management and Warranty, Manufacturing, Quality , Plant Maintenance, Data and Development teams. Infra, Boundary Apps , Change Management and Data Analytics & Reporting Platforms are out of scope for Deloitte and owned by Client Process scope is adequately captured in the response document Timelines are adequately planned in the response document The response has required Deloitte Tools and Accelerators called out including GenAI tools
Integration Scope |  | • The integration between various source and boundary systems are adequately captured in the response document
Geographic Scope |  | • The response documents lacks clarity on the geographic scope. Needs to be included.
Staffing & Resource Mix |  | 
Solution Coverage |  | Lack of clarity on MDG and GTS E4H scope, dependencies, and timeline impacts on the Brownfield+ migration. Assumptions, RACI, and any required timeline adjustments need to be assessed and documented Including ~8,000 defects and ~400 objects within the current Build phase effort (~32K hours) poses significant delivery risk. Development effort allocation should be revisited and phased appropriately across activities and project stages.
Resource Mix/Coverage |  | Onsite-offshore mix stands at 17.5% and 82.5%. Suggest increasing onsite coverage Overall and USI Bulge Ratio at 0.76 and 1.05 are below than the benchmark of 1.6 and 1.9, respectively. Need to adjust staffing mix to meet the Bulge ratio benchmarks.
USI/DC Leverage |  | Recommend to leverage USDC & ARDC resources for better US coverage and cost efficiency
Staffing Estimates vs Actual |  | USI MD and SM staffing hours % (0.16, 1.4) are below benchmarks %(0.3, 2.5), adjust to increase the hours Revise the ramp-up and ramp-down plan across teams to align resources with phase-wise scope and workload.

## Slide 2
SA Readout Summary
Other Recommendations
MDG and GTS scope should be explicitly defined to ensure alignment on deliverables, ownership, and expected outcomes. Current Finance staffing appears insufficient given that Group Reporting, Treasury, and Margin Analysis are also within scope. Additional resourcing should be considered to mitigate delivery risk. Stockroom Management is proposed for Warehousing; a detailed fit-gap assessment is recommended to identify any functionalities supported in the current landscape that may not be available in the target solution. Performance Testing and Stress Testing scope, assumptions should be further detailed to ensure clear expectations and adequate planning. Please have the COE team review and validate the efficiency of the tools called out in the response document.
Other Offerings
Staffing included for Tax, Cyber (Security), Human Capital (OCM) and EFA

## Slide 3
NextGen Estimation Vs Staffing Model
Teams | NextGen Hours | Staffing Plan Hours | Delta
Data | 8,593 | 23655 | 15062
Deployment (Cutover) | 788 | 4365 | 3577
Development | 99,754 | 100855 | 1101
Functional | 79995 | 187680 | 107685
Infrastructure | 17,030 |  | -17030
Organizational Change Management | 15,388 | 24488 | 9100
Project Management | 11,218 | 14322 | 3104
Security & Controls | 11,095 | 16256 | 5161
Testing | 4834 | 4040 | -794
Grand Total | 2,48,695 | 375661 | 
Notes:
Overall, Staffing plan exceeds NextGen estimate by ~ 126K hours
Data and Functional efforts show significant variance vs NextGen estimates
Average RICEFW development effort currently stands at ~180 hrs/object, this is below the required benchmark (~250 hrs/object). Need to revisit development efforts and staffing.