## Slide 1
SA Readout Summary – Project 3 (PM Impl)
Solution Complexity |  | Other Offerings | 
Deployment Timeline |  | Staffing & Resource | 
Solution Complexity |  | 
Solution Scope |  | Response document adequately captures scope details for areas of Process, Security, OCM and Testing GenAI Assets are part of the response and adequately documented Need to adequately further capture scope for areas of Analytics and Development – in terms of number and complexity of RICEFWs as part of the response document The response document lacks clarity regarding the delineation of responsibilities between Deloitte and the client, need to add the same Scope assumptions are missing or need to be updated for areas of – Basis being out of scope and Additional functional stream support for EAM enablement (FIN/MM etc.)
Integration Scope |  | Tech Integration scope is adequately captured in response document
Geographic Scope |  | Geographic scope includes Project 3 Indiana, Project 3 Ohio and Project 3 Lighting and is called out in the response
Staffing & Resource Mix |  | 
Solution Coverage |  | The documentation doesn't provide clarity on the scope of reporting, analytics, UI5, and Fiori. It doesn't outline key solutions/deliverables considered in scope for these areas of work. Need to update response document accordingly Historical data reporting needs are not clear, need to include details if in scope or not with supporting assumptions Real time reporting needs are not explicitly mentioned, need to call out if in scope Batch scheduling requirements are not clearly called out, if any applicable for PM process scope area
Resource Mix/Coverage |  | Onsite – Offshore (Including ARDC) mix at 21.2% : 78.8%, is fine USI Bulge at 0.88 is much lesser than the benchmark of 1.9. Need to fix the same
USI/DC Leverage |  | Staffing leverages ARDC/Mexico resources in addition to USI. However, hours per period need to be updated to 180 from 160 currently baked in staffing model
Staffing Estimates vs Actual |  | Overall total staffing hours are higher than NextGen estimation hours, please refer to slide # 3 for detailed comparison USI SM hours at 0.012 % are much lesser to the benchmark of 2% – 2.5%. Need to increase USI SM hours in staffing model as per benchmark Section 9.7 of the client RFP specification calls for staffing a full time Test Manager; however, staffing(pricing model) does not reflect this role, need to add the same

## Slide 2
SA Readout Summary - Project 3 (PM Impl)
Deployment
Recommend adding a high-level overall timeline view depicting the releases and parallel upgrade timelines, as part of Response document The number of cutover cycles outlined in the response document is considered adequate in relation to the project scope/test cycles planned Security, Data and OCM timelines are not well defined and not in line with scope, please update Security role design scope is not called out and testing timelines and not included in project scope Hypercare timelines are sufficient to ensure there is a smooth transition, as mentioned in Response content
Other Offerings
Staffing plan includes hours for EFA, OCM and Security
Recommendations
• There are no assumptions on the Technology - Dev side in the Assumptions Table of the RFP response. A strong recommendation is to add/improve Assumptions on the points not clear • Reporting/Analytics is factored into the staffing, however, is not clearly called out in the response and estimated too in NextGen. Need to add Analytics scope details to Response and fix NextGen estimates for the same • Staffing from other streams integrating with/supporting EAM - Assumptions need to be called out. E.g. Any additional Finance or Project System set up required etc.

## Slide 3
NextGen Estimation Vs Staffing Model
Teams | NextGen Hours | Staffing Hours | Delta
Data (Migration, MDG and Analytics) | 3011 | 14365 | 11354
Deployment (Cutover) | 1920 | 3080 | 1160
Development | 18493 | 20165 | 1672
Functional | 12977 | 14445 | 1468
Infrastructure | 3674 | 200 | -3474
Organizational Change Management | 8024 | 8578 | 554
Project Management | 3292 | 3056.0 | -236
Security & Controls | 3747 | 7615 | 3868
Testing | 9732 | 0 | -9732
Grand Total | 64871 | 71504 | 
Notes:
Overall, total staffing hours are higher than total estimated NextGen hours by ~10%. However, for specific teams there is major variance between estimated vs staffing hours that need to be checked and adjusted
NextGen estimates for Data do not include Analytics scope inputs leading to major variance in NextGen Vs Staffing hours (which has Analytics efforts baked in). Need to add Analytics scope inputs to NextGen estimation and further revisit staffing hours for Data teams
Basis/Infra scope inputs for NextGen need to be removed/disabled as this is out of scope
OCM efforts seem to be on the higher side both in estimation and staffing, considering scope of implementation is majorly for PM/EAM Module. Need to be revisited
Security hours in staffing are much higher than estimated, need to check the estimation inputs and/or staffing roles planned for this team
Need to add Testing Lead Role in Staffing plan, currently this is missing