## Slide 1
SA Readout Summary – Project 1
Solution Complexity |  | Other Offerings | 
Deployment Timeline |  | Staffing & Resource | 
Solution Complexity |  | 
Solution Scope |  | The current proposal is to do S4HANA Greenfield implementation for Project 1 to regulate their Life science pharma manufacturing Solution scope in the response indicate Order to Cash, Record to Report, Procure to pay, Forecast to schedule and Plan to Deliver Interface objects are not adequately scoped in for MES,LIMS, Payroll, External Tax application, Banking Portals integrations through SAP BTP CPI with S/4 The statutory and legal compliance requirements need to be scoped. FP&A, Group reporting and consolidation requirements need to be clearly called out Identify the scope of Ariba within the project to ensure that stakeholders understand the functionalities in the procurement and supply chain processes MDG Scope needs to be added. Solution for Direct Procurement and Indirect Procurement needs to be added Need to add detailed information on RACI and Key Assumption as part of response Sales/Pre-sales integration with front-end systems (SFDC) is not clear
Integration Scope |  | • Recommend to add adequate details on Scope and Assumptions around Integration scope with MES, LIMS & QM in S4.Ariba, P2P & Finance integration are at high level. Need more details.
Geographic Scope |  | • US & Japan
Staffing & Resource Mix |  | 
Solution Coverage |  | • Recommend adding detailed RICEFW scope in the response • Data Cleansing scope & profiling are not in scope. P2P & Finance integration is at high level. Need more details.
Resource Mix/Coverage |  | Onsite-offshore mix stands at 22% and 77%, looks fine USI Bulge Ratio at 1.18 is lower than the benchmark of 1.9, need to revisit and adjust
USI/DC Leverage |  | Recommend to leverage USDC & ARDC resources in addition to USI for better US coverage and cost efficiency Recommend to leverage Delivery Pools across Development, Data and Infrastructure threads
Staffing Estimates vs Actual |  | USI MD Hours are estimated at 0.16%. USI MD hours would be in range of 0.2 to 0.3% USI SM Hours are 1.37% versus Benchmark of 2.5% Resources for IMO Integration with Japan is very minimal in the staffing. Security staffing is very minimal & this needs to updated in the pricing It is highly recommended to add one senior consultant at least across the implementation timelines No staffing for Ariba, Treasury, Asset Management & Tax in the Pricing

## Slide 2
SA Readout Summary – Project 1
Observations/Recommendations
The response lacks clarity regarding whether the solution will be hosted on the cloud or on-premises Mock and SIT cycles are adequate as per the timelines for US S4 implementation but not for IMO integration with Japan Exclusions are not called out in the response The post-go-live support model for EWM and SCM is light and may not provide enough coverage for stabilization and issue resolution. Batch scheduling requirements & Real time reporting needs are not explicitly mentioned Infrastructure hours estimated in Pricing Model (1710 hours) are very less, It is highly recommended to add one senior consultant at least across the implementation timelines Revisit testing roles in staffing as they are minimal Security hours in staffing model are higher than estimated. Please revisit Gen AI enabled capabilities are updated under activities & deliverables phase wise in the response
Other Offerings
NA

## Slide 3
NextGen Estimation Vs Staffing Model
Notes:
Functional, Development & Data hours from Pricing model are higher than the NextGen hours
No Testing hours or testing lead captured in Pricing model. Revisit and update accordingly
Security and Cutover roles needs to be revisited in the staffing
PMO and Training hours in Pricing Model are slightly less
Teams | NextGen Hours | Staffing Hours | Delta
Cutover | 1605 | 3285 | 1680
Data | 1970 | 5670 | 3700
Development | 14316 | 15480 | 1164
Functional | 24098 | 34915 | 10817
Infrastructure | 3039 | 1710 | -1329
PMO | 7067 | 6759 | -308
Security & Controls | 4826 | 7869 | 3043
Testing | 9513 | 0 | -9513
Training | 6461 | 5970 | -491
Total | 72894 | 81658 |